Standard Form Project Agreement

(hub Build Only Projects)

Version 1: July 2018

BUILD ONLY DEVELOPMENT AGREEMENT

between

[AUTHORITY]

and

[HUBCO]

[Project]

[Date]

hub TEMPLATE PROJECT AGREEMENT – BUILD ONLY PROJECTS

VERSION 1

IMPORTANT NOTICE

This template project agreement is intended for use on projects where hubco is not adopting responsibility for the design or specification of the Works except perhaps in relation to a specified hubco Deisgned Portion.

Users should be aware of the following points:-

- This Template Project Agreement for Build Only Projects is based on the Template Project Agreement for D&B Projects but amended such that hubco is not responsible for the design or specification of the Works except to the extent that the design or specification of any hubco Designed Portion is produced or to be produced by or on behalf of hubco.

- Changes to the Template Project Agreement, other than project specific and minor drafting (such as completion of time periods) or to reflect the issues discussed at paragraph 5 below, require prior approval of the SFT.  Normally approval will only be given to changes required to reflect changing guidance or demonstrable changing market circumstances.

- Where there will be more than one user of the Facility, one authority (from among the Relevant Participants (as defined in the TPA)) will be lead authority.  Only the lead authority will enter into agreement with hubco.  The lead authority will in turn have appropriate back to back contractual arrangements (including leases) with the other users.  hubco will be required to procure collateral warranties in favour of the other authorities as well as those in favour of the lead authority.

- The Schedule to this Template Project Agreement contains standard form collateral warranties and sample certificates.  They are included as templates and their use is not mandatory but justification for deviations from the suggested form must be provided to the SFT if they are not used.

- The Template Project Agreement contains a number of footnotes which identify certain key issues which parties will need to consider when using it.  This is not an exhaustive list, and the agreement will therefore need to be analysed and reviewed in detail to ensure that it is tailored to the requirements of each project and that its terms (and their impact) are clearly understood by the parties.  Customisation should not however extend to parties seeking to change the substance of commercial terms or making unnecessary drafting amendments.

- This Template Project Agreement is not a replacement for independent, specialist advice and parties must ensure that they have taken appropriate legal, financial and technical advice before using this document.

- This Template Project Agreement should be used in conjunction with the Guidance issued/adopted by the Scottish Government and/or SFT from time to time.

- This Template Project Agreement assumes that the procuring Authority will adopt the use of a Project Bank Account as best practice following publication of SPPN 10/2016 or as required by the SPFM. Should a procuring Authority not wish to follow best practice or should the project fall outwith the scope of the SPFM, alternative drafting will be required in respect of payment. It is expected that the procuring Authority will set out its reasons for departing from best practice and it is reminded that the procuring Authority will still require to comply with the provisions of the Procurement Reform (Scotland) Act 2014.

- This notice and the footnotes should be removed as appropriate before finalisation of the document for issue for a specific project.

- Should you have any questions on the standard form please contact the SFT hub team (http://www.scottishfuturestrust.org.uk).

CONTENTS

Clause	Page

1	DEFINITIONS AND INTERPRETATION	1

2	EXECUTION AND DELIVERY OF DOCUMENTS	1

3	COMMENCEMENT AND DURATION	2

4	PROJECT DOCUMENTS	2

5	THE WORKS	3

6	GENERAL OBLIGATIONS AND RESPONSIBILITIES OF HUBCO	4

7	DISCLOSED DATA	4

8	REPRESENTATIVES	4

9	NATURE OF LAND INTERESTS	6

10	THE SITE	7

11	CONSENTS & PLANNING APPROVAL	7

12	THE DESIGN CONSTRUCTION AND COMMISSIONING PROCESS	9

13	RIGHT OF ACCESS OF AUTHORITY'S REPRESENTATIVE	12

14	PROGRAMME AND DATES FOR COMPLETION	14

15	EQUIPMENT	15

16	PRE-COMPLETION COMMISSIONING AND COMPLETION	15

17	DEFECTS	18

18	POST COMPLETION COMMISSIONING	19

19	FOSSILS AND ANTIQUITIES	20

20	QUALITY ASSURANCE	22

21	INFORMATION TECHNOLOGY	24

22	DELAY EVENTS	25

23	RELIEF EVENTS	28

24	FORCE MAJEURE	30

25	CHANGES IN LAW	32

26	VARIATION PROCEDURE	32

27	PAYMENT	33

28	VAT	41

29	CONSTRUCTION INDUSTRY TAX DEDUCTION SCHEME	43

30	RECORDS AND OPEN BOOK ACCOUNTING	44

31	AUTHORITY EVENTS OF DEFAULT	45

32	HUBCO DEFAULT	45

33	TERMINATION RESULTING FROM FORCE MAJEURE	48

34	CORRUPT GIFTS AND PAYMENTS	49

35	CONSEQUENCES OF TERMINATION	51

36	INDEMNITIES	54

37	TAX ON PAYMENTS INDEMNITY PAYMENTS	57

38	WARRANTIES	57

39	INSURANCE	58

40	EXCLUSIONS AND LIMITATIONS ON LIABILITY	63

41	INTELLECTUAL PROPERTY	66

42	DISPUTE RESOLUTION PROCEDURE	67

43	ASSIGNATION AND SUBCONTRACTING	67

44	MITIGATION	70

45	DATA PROTECTION	70

46	CONFIDENTIALITY	71

47	FREEDOM OF INFORMATION	75

48	INFORMATION AND AUDIT ACCESS	76

49	NOTICES	77

50	NO WAIVER	78

51	NO AGENCY	79

52	ENTIRE AGREEMENT	79

53	THIRD PARTY RIGHTS	79

54	SEVERABILITY	79

55	CONFLICTS OF AGREEMENTS	79

56	COSTS AND EXPENSES	80

57	GOVERNING LAW AND JURISDICTION	80

58	FURTHER ASSURANCE	80

59	COUNTERPARTS AND DELIVERY	80

SCHEDULE	82

PART 1 - DEFINITIONS AND INTERPRETATION	82

PART 2 - COMPLETION DOCUMENTS	101

PART 3 - KEY WORKS PERSONNEL	103

PART 4 - LAND MATTERS	104

PART 5 - CONSTRUCTION MATTERS	105

PART 6 - THE PROGRAMME	124

PART 7 - REVIEW PROCEDURE	125

PART 8 - COLLATERAL AGREEMENTS	133

PART 9 - OUTLINE COMMISSIONING PROGRAMME	153

PART 10 - EQUIPMENT	154

PART 11 - DEVELOPMENT AMOUNT ANALYSIS	161

PART 12 - INSURANCE REQUIREMENTS	162

PART 13 - VARIATION PROCEDURE	175

PART 14 - RECORD PROVISIONS	182

PART 15 - DISPUTE RESOLUTION PROCEDURE	186

PART 16 - CERTIFICATES	191

PART 17 - COMMERCIALLY SENSITIVE INFORMATION	195

PART 18 - LIQUIDATED DAMAGES	196

PART 19 – NOT USED	197

PART 20 – PROJECT BANK ACCOUNT	198

PART 21 – NOT USED	201

PART 22 – DETAILS OF PROCESSING OF PERSONAL DATA	202

BETWEEN:

(1)	[                    ] (the "Authority"); and

(2)	[                    ] LIMITED (registered under number [                    ]) whose registered office is [                    ] ("hubco").

WHEREAS:

(A)	The Authority requires the construction of [ l ], more fully defined in the Works.

(B)	The Authority and hubco are parties to the Territory Partnering Agreement which establishes a long-term strategic partnership within the [ l ] [hub] territory between hubco and inter alios the Authority.

(C)	Pursuant to the Territory Partnering Agreement the Authority and hubco have agreed to enter into this Agreement for the Works.

(D)	The Authority, hubco and the Contractor wish to adopt a mechanism which allows for payments in connection with the Project to be made to hubco, the Contractor and Sub-Contractors through the operation of a Project Bank Account.

NOW IT IS HEREBY AGREED as follows:-

PART 1: GENERAL

- 1DEFINITIONS AND INTERPRETATION

Schedule Part 1 (Definitions and Interpretation) shall apply.

- 2EXECUTION AND DELIVERY OF DOCUMENTS

  - On or prior to execution of this Agreement:-

    - hubco shall deliver to the Authority the documents referred to in Section 1 (Documents to be delivered by hubco) of Schedule Part 2 (Completion Documents) (unless the requirement to deliver any such document is waived by the Authority by written notice to hubco); and

    - the Authority shall deliver to hubco the documents referred to in Section 2 (Documents to be delivered by the Authority) of Schedule Part 2 (Completion Documents) (unless the requirement to deliver any such document is waived by hubco by written notice to the Authority).

  - By the earlier of:

    - ten (10) Business Days after the date of appointment of a particular Key Sub-Contractor; and

    - a particular Key Sub-Contractor commencing sub-contract works on Site and/or commencing any off-site fabrication related to the relevant Sub-Contract, hubco shall obtain and deliver to the Authority:

      - the relevant Key Sub-Contractor Collateral Agreement (subject to any reasonable amendments requested by the Key Sub-Contractor and approved by the Authority) validly executed in self proving form by the relevant Key Sub-Contractor, hubco and the Contractor;

      - a certified copy of the Sub-Contract between the Contractor and the relevant Key Sub-Contractor relative to the same, validly executed in a self proving form by the relevant Key Sub-Contractor and the Contractor; and

      - evidence (in the form of an insurance broker’s “To Whom it May Concern” letter or certificate) that the relevant Key Sub-Contractor has professional indemnity insurance (or, where indicated, product liability insurance) in a sum not less than the amount set out in clause [ l ] of the Construction Contract or such other amount as may be approved by the Authority.

- 3COMMENCEMENT AND DURATION

This Agreement and the rights and obligations of the parties, shall commence on the Execution Date and, without prejudice to Clause 35.4, shall terminate on the Termination Date.

- 4PROJECT DOCUMENTS

  - hubco shall perform its obligations under, and observe all of the provisions of, the Project Documents to which it is a party and shall not:-

    - terminate or agree to the termination of all or part of any Project Document;

    - make or agree to any material variation of any Project Document;

    - in any material respect depart from its obligations (or waive or allow to lapse any rights it may have in a material respect), or procure that others in any material respect depart from their obligations (or waive or allow to lapse any rights they may have in a material respect), under any Project Document; or

    - enter into (or permit the entry into by any other person of) any agreement replacing all or part of (or otherwise materially and adversely affecting the interpretation of) any Project Document,

unless the proposed course of action (and any relevant documentation) has been submitted to the Authority's Representative for review under Schedule Part 7 (Review Procedure) and either (i) there has been no objection in accordance with paragraph 3.2 of Schedule Part 7 (Review Procedure) within twenty (20) Business Days of receipt by the Authority's Representative of the submission of the proposed course of action (and any relevant documentation), or such shorter period as may be agreed by the parties; or (ii) hubco is acting in accordance with the comments of the Authority as provided in paragraph 4.2 of Schedule Part 7 (Review Procedure); and, in the circumstances specified in Clause 4.1.1, hubco has complied with Clause 43 (Assignation and Sub-contracting).

Delivery

  - Without prejudice to the provisions of this Clause 4 (Project Documents), if at any time an amendment is made to any Project Document, or hubco enters into a new Project Document (or any agreement which affects the interpretation or application of any Project Document), hubco shall deliver to the Authority a conformed copy of each such amendment or agreement within ten (10) Business Days of the date of its execution or creation, certified as a true copy by an officer of hubco.

- 5THE WORKS

Scope

  - Subject to, and in accordance with, the provisions of this Agreement, hubco shall perform its duties under this Agreement at its own cost and risk without recourse to the Authority except as otherwise expressly provided in this Agreement.

General standards

  - hubco shall at its own cost be solely responsible for procuring that the Works are at all times performed:-

    - [subject to Clause 11.4], in compliance with all Law and Consents (including without limitation the giving of notices under such Consents) and so as not to prejudice the renewal of any such Consents, provided always, hubco shall not be responsible for ensuring that the design or specification of the Works (other than design or specification of the hubco Designed Portion, to the extent that design or specification has been or is to be carried out by or on behalf of hubco) complies with Law or the Consents;

    - in a manner that is not likely to be injurious to health or to cause damage to property;

    - in a manner consistent with the Quality Plans;

    - [except to the extent expressly stated to the contrary in the Authority's Construction Requirements, in compliance with all applicable NHS Requirements;]

    - in a manner consistent with the Authority discharging its statutory duties and other functions undertaken by it as the same may be notified to hubco from time to time; and

    - in so far as not in conflict with an express obligation of hubco under this Agreement, or where in relation to a matter there is no express obligation or standard imposed on hubco under this Agreement, in accordance with Good Industry Practice.

In the event that any ambiguity, uncertainty, dispute or discrepancy arises in the nature and scope of hubco's obligations under this Clause 5.2 (General Standards), the provisions of this Clause 5.2 (General Standards) will be given meaning and have effect in descending order of precedence set out in this Clause 5.2 (General Standards).

Authority Undertaking

  - The Authority undertakes to hubco that it shall not wilfully impede hubco in the performance of its obligations under this Agreement (having regard always to the interactive nature of the activities of the Authority and of hubco and to the Authority's and any Community Services Provider's use of the Facilities to provide the relevant Community Services and any other operations or activities carried out by the Authority or other Community Services Provider on or at the Site for the purposes contemplated by this Agreement and any other of the Authority's or other Community Services Provider's statutory functions).

Co-operation

  - Each party agrees to co-operate, at its own expense, with the other party in the fulfilment of the purposes and intent of this Agreement.  To avoid doubt, neither party shall be under any obligation to perform any of the other's obligations under this Agreement.

- 6GENERAL OBLIGATIONS AND RESPONSIBILITIES OF HUBCO

hubco Parties

  - Subject to the provision of Clause 23.1.6 hubco shall not be relieved or excused of any responsibility, liability or obligation under this Agreement by the appointment of any hubco Party.  hubco shall, as between itself and the Authority, be responsible for the selection, pricing, performance, acts, defaults, omissions, breaches and negligence of all hubco Parties.  All references in this Agreement to any act, default, omission, breach or negligence of hubco shall be construed accordingly to include any such act, default, omission, breach or negligence of a hubco Party.

Safety

  - hubco shall in carrying out the Works have full regard for the safety of all persons on the Site (whether lawfully or not) and shall keep the Site, the Works and the Facilities in an orderly state, appropriate in accordance with Good Industry Practice, to avoid danger to such persons.

- 7DISCLOSED DATA

  - hubco will not be responsible for the content of the Disclosed Data.

  - If hubco (in its capacity as a build only contractor) becomes aware of any inaccuracy, error, omission, defect or inadequacy in the Disclosed Data, hubco will notify the Authority's Representative.

  - If hubco (in its capacity as a build only contractor) becomes aware of any discrepancy or divergence between the Disclosed Data and the Authority's Construction Requirements, hubco will notify the Authority's Representative who will issue instructions to rectify, alter or modify the Authority's Construction Requirements to resolve the issue.

  - Any rectification, alteration and / or modification of the Authority's Construction Requirements pursuant to Clause 7.3 shall be deemed to be an Authority Works Variation and the provisions of Schedule Part 13 (Variation Procedure) shall apply as if such instruction were a Variation Enquiry issued by the Authority in accordance with the provisions of Section 2 of Schedule Part 13 (Variation Procedure).

- 8REPRESENTATIVES

Representatives of the Authority

  - The Authority's Representative shall be [          ] or such other person appointed pursuant to this Clause 8.  The Authority's Representative shall exercise the functions and powers of the Authority in relation to the Works which are identified in this Agreement as functions or powers to be carried out by the Authority's Representative.  The Authority's Representative shall also exercise such other functions and powers of the Authority under this Agreement as may be notified to hubco from time to time.

  - The Authority's Representative shall be entitled at any time, by notice to hubco, to authorise any other person to exercise the functions and powers of the Authority delegated to him pursuant to this Clause, either generally or specifically.  Any act of any such person shall, for the purposes of this Agreement, constitute an act of the Authority's Representative and all references to the "Authority's Representative" in this Agreement (apart from this Clause) shall be taken as references to such person so far as they concern matters within the scope of such person's authority.

  - The Authority may by notice to hubco change the Authority's Representative.  The Authority shall (as far as practicable) consult with hubco prior to the appointment of any replacement for the Authority's Representative, taking account of the need for liaison and continuity in respect of the Project.  Such change shall have effect on the date specified in the written notice (which date shall, other than in the case of emergency, be such date as will not cause material inconvenience to hubco in the execution of its obligations under this Agreement).

  - During any period when no Authority's Representative has been appointed (or when the Authority's Representative is unable through illness, incapacity or any other reason whatsoever to carry out or exercise his functions under this Agreement) the Authority shall carry out the functions which would otherwise be performed by the Authority's Representative.

  - No act or omission of the Authority, the Authority's Representative or any officer, employee or other person engaged by the Authority shall, except as otherwise expressly provided in this Agreement:-

    - in any way relieve or absolve hubco from, modify, or act as a waiver or personal bar of, any liability, responsibility, obligation or duty under this Agreement; or

    - in the absence of an express order or authorisation under Schedule Part 13 (Variation Procedure), constitute or authorise a Variation.

  - Except as previously notified in writing before such act by the Authority to hubco, hubco and hubco's Representative shall be entitled to treat any act of the Authority's Representative which is authorised by this Agreement as being expressly authorised by the Authority and hubco and hubco's Representative shall not be required to determine whether an express authority has in fact been given.

Representative of hubco

  - hubco's Representative shall be [	] or such other person appointed pursuant to Clause 8.8.  hubco's Representative shall have full authority to act on behalf of hubco for all purposes of this Agreement.  Except as previously notified in writing before such act by hubco to the Authority, the Authority and the Authority's Representative shall be entitled to treat any act of hubco's Representative in connection with this Agreement as being expressly authorised by hubco and the Authority and the Authority's Representative shall not be required to determine whether any express authority has in fact been given.

  - hubco may by notice to the Authority change hubco’s Representative.  Where hubco wishes to do so it shall by written notice to the Authority propose a substitute for approval, taking account of the need for liaison and continuity in respect of the Project.  Such appointment shall be subject to the approval of the Authority (not to be unreasonably withheld or delayed).

  - hubco's Key Works Personnel are identified in Schedule Part 3 (Key Works Personnel).  hubco shall, as far as it is within hubco's control, ensure that such persons retain their involvement in the Works and, in particular, will not, for the duration of the Works require or request any of them to be involved in any other project on behalf of hubco or any of the Shareholders or its or their Associated Companies if, in the reasonable opinion of the Authority, this would adversely affect the Project.

PART 2: LAND ISSUES

- 9NATURE OF LAND INTERESTS

Access During Construction

  - From the Execution Date until the Actual Completion Date or (if earlier) the Termination Date, the Authority shall grant to hubco and hubco Parties or procure that hubco and the hubco Parties are granted:-

    - access to the Site; and

    - the Ancillary Rights,

in each case subject only to the Reserved Rights, the Title Conditions and the Authority’s rights under this Agreement and solely for the purposes of implementing the Works and carrying out hubco's Pre-Completion Commissioning.

Access Following Construction

  - After the occurrence of the Actual Completion Date the Authority shall grant to hubco and hubco Parties or procure that hubco and hubco Parties are granted access to the Facilities subject only to the Reserved Rights, the Title Conditions and the provisions of this Agreement and solely for the purposes of:-

    - carrying out hubco's Post Completion Commissioning during the period permitted therefor and subject to the terms of the Final Commissioning Programme;

    - remedying of Defects pursuant to Clause 17 (Defects) during the Defects Liability Period and the period of [                    ] months specified in Clause 17.2; and

    - the carrying out of Snagging Matters during the period specified therefor in Clause 16.13.

Extent of Access

  - The rights referred to at Clauses 9.1 (Access During Construction) and 9.2 (Access Following Construction) shall not operate or be deemed to operate as a lease of the Facilities or the Site or any part of the Facilities or the Site and hubco shall not have or be entitled to exclusive possession (save to the extent expressly included within the Ancillary Rights) or any estate, right, title or interest in and to the Site or the Facilities but shall occupy the Site as a licensee only.

  - The rights referred to at Clauses 9.1 (Access During Construction) and 9.2 (Access Following Construction) are personal to hubco and the hubco Parties.

  - hubco shall procure that:-

    - all Works carried out at the Site by or on behalf of hubco (whether before, during or after the completion of the Works) shall be carried out in a manner which does not breach any of the Title Conditions or Reserved Rights; and

    - there shall be no action, or omission to act by hubco or a hubco Party, which shall give rise to a right for any person to obtain title to the Site or any part of it.

- 10THE Site

  - The Authority is solely responsible for the extent, adequacy and location of the Site, Site Conditions and the condition of any existing buildings, structures and works on, over or under the Site.

  - Without prejudice to any other obligation of hubco under this Agreement, hubco shall be deemed to have:-

    - satisfied itself as to the rights of access to and through the Site granted hereunder and any accommodation it may require for the purposes of fulfilling its obligations under this Agreement (such as additional land or buildings outside the Site) without prejudice to hubco’s rights under this Agreement in respect of a breach by the Authority of its obligations under Clause 9.1 and/or Clause 9.2;

    - satisfied itself as to the precautions, times and methods of working necessary to prevent any nuisance or interference, whether public or private, being caused to any third parties; and

    - satisfied itself as to the conditions, burdens, restrictions and reservations set out in the Title Conditions and the Reserved Rights.

  - Not used.

  - Not used.

  - Without prejudice to Clause 17, following the Actual Completion Date hubco shall be responsible for the costs of cleaning up and/or otherwise dealing with any Contamination which subsequently occurs on any part(s) of the Sites (whether arising from a source on or off Site) to the extent that such Contamination has been caused by hubco either by a breach of its obligations under this Agreement or otherwise due to its act or omission in carrying out the Project Operations and shall reimburse the Authority within [ ] Business Days in respect of all Direct Losses resulting from such Contamination.

- 11CONSENTS & PLANNING APPROVAL

  - hubco shall be responsible for:-

    - obtaining the hubco Consents; and

    - [subject to Clause 11.4], implementing each Consent within the period of its validity in accordance with its terms, provided always, hubco shall not be responsible for ensuring that the design or specification of the Works (other than design or specification of the hubco Designed Portion, to the extent that design or specification has been or is to be carried out by or on behalf of hubco) complies with the Consents.

- [Authority to include any project specific provisions relating to planning agreements etc.  NB: costs associated with such agreements should be for the account of hubco.]

  - In the event that:

    - a Consent that has been granted is subsequently amended, repealed, revoked or otherwise ceases to be in full force and effect in accordance with its terms as a consequence of any action by a Relevant Authority;

    - affected persons are entitled to claim compensation for the adverse effects of such action under a statutory scheme of compensation; and

    - hubco is not entitled in its own name to claim under that scheme but the Authority is so entitled,

- the Authority must use all reasonable endeavours, at the request, and at the cost of hubco, to claim or to include within its claim such sums as hubco acting reasonably requests and shall pay to hubco the part of any compensation that it receives under that scheme that relates to the sums claimed at the request of hubco.

  - The Authority shall (i) obtain all Consents (which are not hubco Consents) which may be required for the performance of the Works in sufficient time to allow hubco to comply with the Programme and (ii) ensure that such Consents are maintained.

  - [The Authority shall be responsible for discharging, implementing and/or complying with the Authority Planning Conditions by the dates/during the periods specified in the table forming Part C of Section 1 of Schedule Part 5 (Construction Matters).]

PART 3: DESIGN AND CONSTRUCTION

- 12THE DESIGN CONSTRUCTION AND COMMISSIONING PROCESS

Overall Responsibility

  - hubco shall carry out the Works:-

    - in accordance with the Authority's Construction Requirements;

    - in accordance with hubco's Proposals; and

    - in accordance with the terms of this Agreement.

  - To avoid doubt, the obligations in Clauses 12.1.1, 12.1.2 and 12.1.3 are independent obligations.  In particular:-

    - the fact that hubco has complied with hubco's Proposals shall not be a defence to an allegation that hubco has not complied with the Authority's Construction Requirements; and

    - the fact that hubco has complied with the Authority's Construction Requirements shall not be a defence to an allegation that hubco has failed to comply with hubco's Proposals.

Design responsibility

  - Where the Works include a hubco Designed Portion, hubco shall complete the design for the hubco Designed Portion, including the selection of any specifications for the kinds and standards of the materials, goods and workmanship to be used in the hubco Designed Portion so far as not described or stated in the Authority’s Construction Requirements or hubco’s Proposals. Insofar as the design of the hubco Designed Portion is comprised in hubco’s Proposals, in what hubco is to complete in accordance with this Clause 12.3 and any further design that hubco is required to carry out as a consequence of an Authority Works Variation, hubco warrants that it has used, and will continue to use, the degree of skill and care in the design of the hubco Designed Portion that would reasonably be expected of a competent professional designer experienced in carrying out design activities of a similar nature, scope and complexity to those comprised in the hubco Designed Portion.

Corporate Identity and Signage

  - The parties acknowledge that the Authority may, from time to time during the Construction Phase, be required to procure the erection of hoarding, site boards, plaques and/or other signage in connection with the Project.  Accordingly:-

    - where requested by the Authority acting reasonably, hubco shall procure the erection and maintenance of such hoarding, site boards, plaques and/or other signage as the Authority may require; and

    - the size, design, information disclosed, position and materials used in connection with such hoarding, site boards, plaques or other signage shall be approved by the Authority, such approval not to be unreasonably withheld[; and

    - [for the purposes of this Clause 12.4 (Corporate Identity and Signage), the Authority shall be deemed to be acting reasonably where any proposals made by it and/or any approvals exercised by it conform with any relevant guidance issued to NHS Boards by the Scottish Government Health Directorate (or any successor Department) in relation to such matters whether by Executive Letter or otherwise].

Authority design approval

  - The Authority confirms that, as at the date of this Agreement, it has reviewed such of hubco's Proposals (insofar as they relate to the hubco Designed Portion) as have been initialled by the Authority and that, subject to any qualifications and/or comments notified by the Authority to hubco in writing and set out in [                    ] such proposals satisfy the Authority's requirements in respect of Operational Functionality, so far as can reasonably be determined given the level of detail of hubco Design Data which has been disclosed to the Authority.

  - hubco shall develop and finalise the design and specification of the hubco Designed Portion and the Authority shall review the Reviewable Design Data in accordance with Schedule Part 7 (Review Procedure) and the provisions of this Clause 12.6:-

    - hubco shall submit the Reviewable Design Data and the design of any Variations (insofar as they relate to the hubco Designed Portion) developed in accordance with the procedure set out in the Schedule Part 13 (Variation Procedure) to the Authority's Representative for review under Schedule Part 7 (Review Procedure).  hubco shall not commence or permit the commencement of construction of the part or parts of the Facilities to which such Reviewable Design Data relates until it has submitted the appropriate Reviewable Design Data and either it is confirmed by the Authority's Representative that hubco is entitled to proceed with construction in accordance with paragraph 3.3 of Schedule Part 7 (Review Procedure) or hubco is:-

(a)	disputing the status of such Reviewable Design Data pursuant to paragraph 1.3.1 or paragraph 4.3 of Schedule Part 7 (Review Procedure); and

(b)	proceeding at risk pursuant to paragraph 1.3.2 of Schedule Part 7 (Review Procedure).

    - with effect from the date at which any item of Reviewable Design Data is or becomes an Approved RDD Item in accordance with Schedule Part 7 (Review Procedure), such Approved RDD Item shall for the purposes of this Agreement be deemed to have satisfied the requirements of the Authority in the manner and to the extent set out in the Appendix to Schedule Part 7 (Review Procedure);

    - hubco shall allow the Authority’s Representative, at any time, a reasonable opportunity to view any items of hubco Design Data, which shall be made available to the Authority’s Representative as soon as practicable following receipt of any written request from the Authority’s Representative; and

    - hubco shall procure that the Contractor establishes and maintains a computerised design database which hubco and the Authority's Representative may access remotely by computer to view drawings comprised within the hubco Design Data (including Reviewable Design Data) and electronically store and/or print copies of such hubco Design Data. In the event of the Authority's Representative being unable to access such design database, hubco shall procure that it is made available for inspection by the Authority's Representative, or any other person authorised by the Authority's Representative.

- Rectification of hubco’s Proposals

  - Without prejudice to Clause 12.1, if it should be found that hubco’s Proposals (insofar as they relate to the hubco Designed Portion) do not fulfil the Authority’s Construction Requirements (insofar as they relate to the hubco Designed Portion), hubco shall at its own expense and in accordance with Clause 12.8 below, amend hubco’s proposals (insofar as they relate to the hubco Designed Portion) and rectify the hubco Designed Portion or any part affected.  Such amendment and rectification shall have the effect that:-

    - hubco’s Proposals (insofar as they relate to the hubco Designed Portion) shall satisfy the Authority’s Construction Requirements (insofar as they relate to the hubco Designed Portion);

    - following the amendment or rectification, the structural, mechanical and electrical performance of the hubco Designed Portion will be of an equivalent standard of performance to that set out in hubco’s Proposals prior to their amendment or rectification (for the purpose of this comparison disregarding the fault which required the amendment or rectification to be made).

  - Where Clause 12.7 applies, hubco shall submit its proposal for amending hubco’s Proposals (insofar as they relate to the hubco Designed Portion) and rectifying the hubco Designed Portion (or any part affected) to the Authority’s Representative for review under Schedule Part 7 (Review Procedure) and shall not amend hubco’s Proposals (insofar as they relate to the hubco Designed Portion) or commence or allow the commencement of the rectification of the hubco Designed Portion (or any part affected) until it is permitted to proceed in accordance with Schedule Part 7 (Review Procedure).

- Responsibility for Authority’s Construction Requirements and Authority Design Data

  - hubco is not responsible for the content of the Authority's Construction Requirements or the Authority Design Data, and hubco is not responsible for verifying the adequacy of any design contained within the Authority's Construction Requirements and/or the Authority Design Data.

  - If hubco (in its capacity as a build only contractor) becomes aware of any inaccuracy, error, omission, defect or inadequacy in the Authority's Construction Requirements and/or the Authority Design Data, or aware of any discrepancy or divergence within or between the Authority's Construction Requirements, the Authority Design Data and/or Law then, to the extent that the inaccuracy, error, omission, defect, inadequacy, discrepancy or divergence is not dealt with in the Authority's Construction Requirements, hubco will notify the Authority's Representative who will issue instructions to rectify, alter or modify the Authority's Construction Requirements and/or Authority Design Data to resolve the issue.

  - Any rectification, alteration or modification of the Authority's Construction Requirements and/or the Authority Design Data pursuant to 12.10 shall be treated as an Authority Works Variation and the provisions of Schedule Part 13 (Variation Procedure) shall apply as if such instruction were a Variation Enquiry issued by the Authority in accordance with the provisions of Section 2 of Schedule Part 13 (Variation Procedure).

- Provision of Information by the Authority

  - On or before the Execution Date, the Authority shall without charge to hubco supply hubco with all designs and specifications necessary for the carrying out and completion of the Works (other than hubco Design Data [and designs and specifications referred to in the Information Release Schedule]) including, without limitation, all drawings and information necessary for the setting out of the Works.

  - [The Authority shall without charge to hubco ensure that designs and specifications referred to in the Information Release Schedule are supplied to hubco at the times stated in the Information Release Schedule. The Authority and hubco may agree to vary any times stated in the Information Release Schedule (such agreement not to be unreasonably withheld or delayed).]

- Building Information Modelling

  - hubco and the Authority shall each promptly take all steps necessary to carry out and complete their respective obligations pursuant to the BIM Protocol.

- 13RIGHT OF ACCESS OF AUTHORITY'S REPRESENTATIVE

Access to the Site

  - hubco shall procure that:-

    - subject to complying with all relevant safety procedures, which shall include any relevant construction phase plans and health and safety plans for the construction of the Facilities, the Contractor's Site Rules from time to time and any reasonable directions with regard to site safety that may be issued by or on behalf of the Contractor's Site Manager from time to time, the Authority's Representative shall have unrestricted access at all reasonable times during normal working hours to:-

      - view the Works at the Site on reasonable prior notice appropriate to the circumstances, provided that the notice procedures in this Clause above shall not apply to the right of access for the Authority's Representative and his staff and visitors to the office and other facilities provided at the Site for his use; and

      - subject to obtaining the consent of the relevant manufacturer or supplier (which hubco agrees to use all reasonable endeavours to obtain), visit any site or workshop where materials, plant or Equipment are being manufactured, prepared or stored for use in the Works for the purposes of general inspection and of attending any test or investigation being carried out in respect of the Works;

    - the Authority's Representative shall have such rights of access to the Site in an emergency as he (acting reasonably) considers suitable in the circumstances; and

    - monthly progress meetings and site meetings are held and that the Authority's Representative shall have the right to attend such monthly progress meetings and site meetings and to attend such other meetings as the Authority's Representative may reasonably request.

Increased monitoring

  - If, following any viewing, visit or inspection made pursuant to Clause 13.1.1 (Access to the Site), it is discovered that there are Defects in the Works or that hubco has failed to comply with the Authority's Construction Requirements or hubco's Proposals, the Authority's Representative may (without prejudice to any other right or remedy available to the Authority) by notice to hubco increase the level of monitoring of hubco until such time as hubco shall have demonstrated to the satisfaction of the Authority that it is capable of performing and will perform all its obligations to the Authority under this Agreement.  hubco shall compensate the Authority for any reasonable additional costs incurred as a result of such increased monitoring.

Right to Open Up

  - Subject to Clause 13.4, the Authority's Representative shall have the right at any time prior to the Actual Completion Date to request hubco to open up and inspect any part or parts of the Works where the Authority's Representative reasonably believes that such part or parts of the Works is or are defective and hubco shall comply with such request.

  - Prior to exercising his right pursuant to Clause 13.3 above, the Authority's Representative shall notify hubco of his intention to exercise such right, setting out detailed reasons.

  - If, following the exercise by the Authority's Representative of his right pursuant to Clause 13.3, the inspection shows that the relevant part or parts of the Works are not defective then Clause 22.3.4 shall apply.

  - If, following the exercise by the Authority's Representative of his right pursuant to Clause 13.3, the inspection shows that the relevant part or parts of the Works is or are defective , hubco shall rectify and make good such Defect(s) and any consequence of such rectification and/or making good Defect(s) shall be carried out by hubco at no cost to the Authority and hubco shall not be entitled to any extension of time in relation to such rectification and making good of the Works.

  - If, following the exercise by the Authority's Representative of his right pursuant to Clause 13.3, the Authority's Representative is of the opinion that the inspection shows that the relevant part or parts of the Works is or are defective and hubco does not agree with such opinion, the matter shall be determined in accordance with Schedule Part 15 (Dispute Resolution Procedure).

  - Without prejudice to the rights of the Authority's Representative pursuant to this Clause 13 (Rights of Access of Authority’s Representative) the parties acknowledge that the exercise of such rights shall not in any way affect the obligations of hubco under this Agreement save as expressly set out in this Clause 13 (Rights of Access of Authority’s Representative).

Safety During Construction

  - The provisions of Section 2 (Safety During Construction) of Schedule Part 5 (Construction Matters) shall apply to matters of safety.

- 14Programme and Dates for Completion

  - Dates for Completion

hubco shall complete the Works by the Completion Date.

  - Liquidated Damages for Delay

If the Actual Completion Date is not achieved by or on the Completion Date, then hubco shall immediately become liable to pay or allow to the Authority (whether by payment, set-off or deduction), on demand, liquidate and ascertained damages at the rate calculated in accordance with Schedule Part 18 (Liquidated and Ascertained Damages) for each day from and including the Completion Date until but excluding the Actual Completion Date ("Liquidated Damages").

  - Genuine Pre-Estimate

The Authority and hubco agree that the Liquidated Damages represent a genuine and reasonable pre-estimate of the losses, damages, costs and expenses that the Authority would suffer or incur as a result of any such delay in completion of the Works.

  - Authority Waiver

The right of the Authority to recover Liquidated Damages may only be waived by written notice from the Authority to hubco.

  - Liquidated Damages Held Unenforceable

In the event that the right of the Authority to recover Liquidated Damages pursuant to Clause 14.2 (Liquidated Damages for Delay) is held to be unenforceable in whole or in part and the Authority is therefore not entitled to the relevant Liquidated Damages in respect of any delay to the Works, the Authority and hubco specifically acknowledge and agree that the Authority shall be entitled to recover damages at Law which would otherwise have been payable in respect of the consequences of any delay in obtaining the Certificate of Completion on the Completion Date.

  - Effect of Liquidated Damages

The payment or allowance by hubco of Liquidated Damages or damages pursuant to Clause 14.5 to the Authority pursuant to this Clause 14 (Programme and Dates for Completion) shall not relieve hubco of any other of its duties, liabilities or obligations under this Agreement.

The Programme

  - Any Programme submitted in accordance with the provisions set out below shall be prepared in accordance with Good Industry Practice and shall be in sufficient detail so as to enable the Authority's Representative to monitor the progress including all commissioning activities and likely future progress of the Works.

  - The initial Programme is set out at Schedule  (The Programme).  Any change to the Programme shall only be made in accordance with this Clause 14 (Programme and Dates for Completion) and Schedule Part 7 (Review Procedure).  hubco shall promptly submit to the Authority's Representative a copy of any version of the Programme varied in accordance with this Clause 14 (Programme and Dates for Completion) and Schedule Part 7 (Review Procedure).

  - If it appears to the Authority's Representative at any time that the actual progress of the Works has significantly fallen behind the Programme, then the Authority's Representative shall be entitled to require hubco to submit to the Authority's Representative a report identifying the reasons for the delay and, unless the event causing the delay is still subsisting and it is not possible to predict with any certainty when the delay might come to an end, require hubco (at the Authority's option):-

    - to produce and submit to the Authority's Representative in accordance with Schedule Part 7 (Review Procedure) a revised Programme showing the manner and the periods in which the Works will be carried out to ensure completion; and/or

    - to produce and submit to the Authority's Representative in accordance with Schedule Part 7 (Review Procedure) a revised Programme showing the steps which are to be taken to eliminate or reduce the delay.

Early completion

  - Notwithstanding that the Works may have been completed in accordance with this Agreement, the Actual Completion Date may only occur on a date on or after the Completion Date unless the Authority, in its absolute discretion, agrees otherwise in writing.

  - hubco shall notify the Authority's Representative if at any time the actual progress of the Works is significantly ahead of the Programme such that hubco anticipates that the Actual Completion Date could occur earlier than the Completion Date, in which case the Authority's Representative shall be entitled to require hubco to produce and submit to the Authority's Representative a revised Programme showing the manner and the periods in which the Works will be carried out and what the revised date for completion would be to enable:-

    - the Authority to consider (at its absolute discretion) whether to agree an earlier date for completion if requested by hubco to do so; and

    - the parties to consider what modifications (if any) will be required to the Agreement in order to accommodate such earlier date for completion if agreed to by the Authority pursuant to Clause 14.11.

- 15EQUIPMENT

  - Equipment

The parties shall comply with the terms of Schedule Part 10 (Equipment).

- 16PRE-COMPLETION Commissioning AND COMPLETION

  - Not less than [                    ] months before the Completion Date the Authority shall provide hubco with a draft of the Final Commissioning Programme as jointly developed by the Authority and hubco in accordance with the provisions of Clauses 16.2 and 16.3.  hubco shall provide the Authority with comments on the draft Final Commissioning Programme submitted to it within [                    ].  The parties shall, within [                    ] Business Days of receipt by the Authority of hubco's comments agree the terms of the Final Commissioning Programme provided that the Authority may by prior notice to hubco change the scope and time of the Authority's Commissioning and reimburse hubco its reasonable costs incurred as a result of such change in scope or time.  If the parties are unable to agree the Final Commissioning Programme or the change in scope or time of the Authority's Commissioning by [                    ] the matter shall be referred for determination in accordance with Schedule Part 15 (Dispute Resolution Procedure).

  - The Final Commissioning Programme shall be in accordance with the Outline Commissioning Programme and shall impose no greater or more onerous obligations on the Authority than those set out in the Outline Commissioning Programme (unless otherwise agreed by the Authority in its absolute discretion).  The Final Commissioning Programme shall then replace the Outline Commissioning Programme.  Where this Agreement refers to an obligation being in accordance with or pursuant to the Final Commissioning Programme, such reference shall, prior to the replacement of the relevant Outline Commissioning Programme with the relevant Final Commissioning Programme, be deemed to be a reference to the obligation being in accordance with or pursuant to the relevant Outline Commissioning Programme.

  - The Final Commissioning Programme shall describe the steps necessary, the party responsible for taking each of such steps and the timing and sequence of each of such steps to ensure:-

    - that hubco's Pre-Completion Commissioning and the Authority's Commissioning will not delay the Actual Completion Date from occurring by the Completion Date; and

    - that hubco's Post Completion Commissioning and the Authority's Post Completion Commissioning is completed by the Commissioning End Date.

  - The parties shall procure that the steps that they are responsible for carrying out and completing pursuant to the Final Commissioning Programme include, [in the case of hubco's activities, the activities described at paragraph [                    ] of the Authority's Construction Requirements].

  - hubco shall notify the Authority's Representative of the date when hubco (acting reasonably) considers that the Works will be complete in accordance with the Authority's Construction Requirements and this Agreement not less than [                    ] months prior to such anticipated completion.

Commissioning prior to Completion Date

  - hubco shall:-

    - undertake hubco's Pre-Completion Commissioning in accordance with the Final Commissioning Programme; and

    - permit the Authority to undertake the Authority's Commissioning including [permitting specialist contractors engaged by the Authority to deliver and install Equipment] on such dates as agreed between the Authority and hubco, in accordance with the Final Commissioning Programme,

and the Authority shall undertake the Authority's Commissioning in accordance with the Final Commissioning Programme and so as not to cause material damage to the Works.

  - hubco shall give written notice to the Authority and the Authority's Representative of the commencement of hubco's Pre-Completion Commissioning and shall ensure that the Authority's Representative is invited to witness all of, and is provided with all information they may reasonably require in relation to, hubco's Pre-Completion Commissioning and that the Authority's Representative is invited to comment on hubco's Pre-Completion Commissioning.

  - hubco shall (or shall procure that the Contractor shall) give the Authority access to the Works at such times as may be set out in the Final Commissioning Programme to enable the Authority to undertake the Authority's Commissioning in accordance with the Final Commissioning Programme for the period prior to completion.  When exercising such rights the Authority shall comply with all relevant safety procedures, which shall include any relevant construction phase plans and health and safety plans for the construction of the Facilities, the Contractor's Site Rules from time to time and any reasonable directions with regard to site safety that may be issued by or on behalf of the Contractor's Site Manager from time to time.

Pre-Completion inspection

  - hubco shall give the Authority's Representative not less than [                    ] Business Days' notice and not more than [                    ] Business Days' notice of the date upon which hubco considers that the Works will be complete and the tests on completion to be performed in accordance with the Final Commissioning Programme will be carried out.  [Following receipt of the notice specified in this Clause 16.9 (Pre-Completion Inspection)] the Authority's Representative shall be entitled to inspect the Works on the date or dates reasonably specified by hubco in accordance with this Clause 16.9 (Pre-Completion Inspection), and to attend any of the tests on completion.  hubco shall, if so requested, accompany the Authority's Representative on any such inspection.

Pre-Completion matters

  - The Authority's Representative shall, within [                    ] Business Days of any inspection made pursuant to Clause 16.9 (Pre-Completion Inspection), notify hubco of any outstanding matters (including, without limitation, the repetition of any of the tests on completion which are required to be carried out and passed in accordance with the Final Commissioning Programme) which are required to be attended to before the Works can be considered to be complete in accordance with the Authority's Construction Requirements and hubco's Proposals.  hubco shall attend to such matters and shall, if necessary, give the Authority's Representative further notices in accordance with Clause 16.9 (Pre-Completion Inspection), (but dealing only with matters raised in the notification under this Clause 16.10) so that the procedures in Clause 16.9 (Pre-Completion Inspection) and this Clause 16.10 )Pre-Completion Matters) are repeated as often as may be necessary to ensure that all outstanding matters in relation to the Works are attended to.

Completion Certificate

  - Subject to Clause 14.10 the Authority's Representative shall, when he is satisfied, acting reasonably, that completion has occurred in accordance with this Agreement, issue a Certificate of Completion to that effect stating the date upon which, in his opinion, the Actual Completion Date occurred.  Subject to Clauses 16.14 and 16.15, the issue of the Certificate of Completion shall, in the absence of manifest error, bad faith or fraud, be conclusive evidence that the Actual Completion Date has occurred on the date stated in such certificate.

  - The Authority's Representative shall issue the Certificate of Completion notwithstanding that there are Snagging Matters.  Where there are Snagging Matters, the Authority's Representative shall, within [  ] Business Days of the date of issue of the Certificate of Completion, issue a Snagging Notice which shall specify the Snagging Matters and an estimate of the cost of rectifying such Snagging Matters.

  - Following the issue of a Snagging Notice, hubco shall, in consultation with the Authority's Representative and in such manner as to cause as little disruption as reasonably practicable to the Authority's Post Completion Commissioning and the Authority's use of the Facilities, rectify all Snagging Matters within [                    ] Business Days of the issue of the Snagging Notice.

  - If, within [                    ] Business Days of the issue of the Snagging Notice hubco has failed to rectify the Snagging Matters specified in the Snagging Notice the Authority may by itself (or engage others to) carry out the works necessary to rectify the Snagging Matters, at the risk and cost of hubco.

  - The issue of the Certificate of Completion shall in no way affect the obligations of hubco under this Agreement including in respect of any Defects.

As-built specification

  - Within forty (40) Business Days after the issue of the Certificate of Completion, hubco shall provide to the Authority a copy of the as-built building specification of the hubco Designed Portion, together with all [drawings relating to the hubco Designed Portion].

- 17DEFECTS

hubco to Make Good

  - hubco shall procure that all Defects which are present or shall appear in the Works during the Defects Liability Period for the Works shall be made good by hubco to the standards required by this Agreement within a reasonable time.  The Authority and hubco, both acting reasonably, shall agree a programme for access for this purpose with the intention to cause the least practicable disruption to users of the Facilities.

Schedule of Defects

  - Without prejudice to Clause 17.1 (hubco to Make Good), not later than [    ] Business Days after the expiry of the Defects Liability Period, the Authority shall procure that the Authority's Representative shall prepare a schedule of Defects ("Schedule of Defects") specifying any Defects apparent as at the date of expiry of the Defects Liability Period which have not been made good by hubco by such date in accordance with Clause 17.1 and shall deliver such Schedule of Defects to hubco.  Subject always to Clause 17.3 (hubco Failure to Comply), hubco shall, at its own expense, as soon as reasonably practicable after the date of issue of such Schedule of Defects (and in any event within a period of [     ] of such date) make good all such Defects.

hubco Failure to Comply

  - Where hubco fails to comply with the provisions of Clause 17.1 (hubco to Make Good) or Clause 17.2 (Schedule of Defects), the Authority may appoint or instruct any third party contractor to execute and complete the remedial, repair or other works as may be necessary to make good any Defect, in which event hubco shall reimburse the Authority, on demand, its reasonable costs of doing so.

Certificate of Making Good Defects

  - Without prejudice to hubco's continuing obligations under this Agreement, when, following the Actual Completion Date, all Defects in the Schedule of Defects have been made good, the Authority's Representative shall issue a statement to that effect to hubco (a "Certificate of Making Good Defects").

Liability

  - Following the expiry of the Defects Liability Period, hubco shall be liable to the Authority for the reasonable costs of, and reasonably foreseeable expenses properly incurred in, procuring the repair of Defects.  For the avoidance of doubt, the provisions of this Clause 17 shall not be construed as limiting or excluding in any way the Authority's general right to claim damages for any breach of this Agreement by hubco.

Limitation

  - For the avoidance of doubt, the provisions of this Clause 17 shall not in any manner or way serve to limit, reduce, satisfy, discharge, negate, avoid or otherwise affect the obligations and/or liability (including in respect of Defects) of hubco to the Authority specified or referred to elsewhere in this Agreement.

- 18Post Completion Commissioning

Commissioning

  - hubco and the Authority shall, within [                    ] Business Days following the Actual Completion Date, respectively undertake and complete hubco's Post Completion Commissioning and the Authority's Post Completion Commissioning, in accordance with the Final Commissioning Programme.  Both parties shall, at all times, and in particular in the period between the Actual Completion Date and the Commissioning End Date, use reasonable endeavours to assist the other party to ensure compliance with the Final Commissioning Programme.

Information

  - hubco shall ensure that the Authority's Representative is provided with all the information he may reasonably require in relation to hubco's Post Completion Commissioning and the Authority shall ensure that hubco is provided with all information hubco may reasonably require in relation to the Authority's Post Completion Commissioning.

  - If the Authority's Representative, acting reasonably, makes any comment in relation to the carrying out of hubco's Post Completion Commissioning, such comments shall be taken into account by hubco and if hubco, acting reasonably, makes any comment in relation to the carrying out of the Authority's Post Completion Commissioning, such comment shall be taken into account by the Authority.

  - [On the occurrence of the Commissioning End Date the Authority's Representative shall issue the Commissioning Completion Certificate.]

Operational Manuals

  - hubco shall provide to the Authority:

    - at least [  ] weeks prior to the anticipated Actual Completion Date, [  ] [paper/electronic] copies of a draft operation and maintenance manual relating to the hubco Designed Portion in sufficient detail to allow the Authority to plan for the safe and efficient operation of the facilities;

    - on or before the Actual Completion Date, [  ] [paper/electronic] copies of a final draft operation and maintenance manual relating to the hubco Designed Portion in sufficient detail to allow the Authority to operate and use the Facilities safely and efficiently;

    - within [  ] weeks following the Actual Completion Date, the principal operation and maintenance manual relating to the hubco Designed Portion;

in each case including all manufacturers' instructions relating to Equipment installed by hubco and [Authority to list any other manuals required] relating to the hubco Designed Portion.

  - hubco shall provide to the Authority such information after the Actual Completion Date as relates to any Snagging Matters or rectification of Defects as is reasonably necessary to allow for the updating of any of the items listed in Clause 18.5.

  - On termination of this Agreement (howsoever arising) prior to the provision by hubco in accordance with Clause 18.5 of the items listed therein, hubco shall within [  ] Business Days of such termination provide a copy of any operating and maintenance manual relating to the hubco Designed Portion not yet provided (completed as appropriate to the date of termination) to the Authority.

- 19Fossils and Antiquities

Property

  - As between the parties, all fossils, antiquities, and other objects having artistic, historic or monetary value and human remains which may be found on or at the Site are or shall become, upon discovery, the absolute property of the Authority.

Discovery

  - Upon the discovery of any such item during the course of the Works, hubco shall:-

    - immediately notify the Authority's Representative of such discovery;

    - take all steps not to disturb the object and, if necessary, cease any Works in so far as the carrying out of such Works would endanger the object or prevent or impede its excavation; and

    - take all necessary steps to preserve the object in the same position and condition in which it was found.

Action

  - The Authority shall procure that the Authority's Representative promptly, and in any event within [                    ] Business Days of receipt of notice pursuant to Clause 19.2.1, issues an instruction to hubco specifying what action the Authority's Representative requires hubco to take in relation to such discovery.

  - hubco shall promptly and diligently comply with any instruction issued by the Authority's Representative referred to in Clause 19.3 above (except and to the extent that such instruction constitutes a Authority Works Variation pursuant to Clause 19.6 below in which case the provisions of Schedule Part 13 (Variation Procedure) shall apply), at its own cost.

  - If directed by the Authority's Representative, hubco shall allow representatives of the Authority to enter the Site for the purposes of removal or disposal of such discovery provided that such entry shall be subject to the Authority complying with all relevant safety procedures, which shall include any relevant health and safety plans for the construction of the Facilities, the Contractor's Site Rules from time to time and any reasonable directions with regard to site safety that may be issued by or on behalf of the Contractor's Site Manager from time to time.

  - If in relation to such discovery, the Authority requires hubco to carry out works (being any work of alteration, addition, demolition or extension or Variation in the Works) which are not works which would be necessary for the purpose of compliance with Law (insofar as it relates to any design or specification for which hubco is responsible in relation to the hubco Designed Portion) or any Consents (insofar as they relate to any design or specification for which hubco is responsible in relation to the hubco Designed Portion), such works shall be deemed to be a Authority Works Variation and the provisions of Schedule Part 13 (Variation Procedure) shall apply as if such instruction were a Variation Enquiry issued by the Authority in accordance with the provisions of Section 2 of Schedule Part 13 (Variation Procedure).

PART 4: QUALITY ASSURANCE

- 20Quality Assurance

Quality Plans and Systems

  - hubco shall procure that all aspects of the Works are the subject of quality management systems in accordance with the provisions of this Clause 20 (Quality Assurance).

  - The quality management systems referred to in Clause 20.1 above shall be reflected in appropriate Quality Plans, the standard of which shall be consistent with BS EN ISO 9001 or 9002 (as the case may be) or any equivalent standard which is generally recognised as having replaced them (or either of them).

  - Without limitation to the generality of Clause 20.2, there shall be:

    - a hubco Designed Portion Design Quality Plan (if applicable); and

    - a Construction Quality Plan,

- provided that the hubco Designed Portion Design Quality Plan and the Construction Quality Plan may be incorporated into one document.

  - hubco shall procure that the Works are carried out in compliance with the Quality Plans.  All Quality Plans shall be submitted to the Authority's Representative in accordance with Schedule Part 7 (Review Procedure) and hubco shall not be entitled to implement or procure the implementation of any Quality Plan unless hubco is entitled to proceed with such implementation pursuant to Schedule Part 7 (Review Procedure).

  - hubco shall implement the quality management systems referred to in Clause 20.1 and shall procure that:

    - the Contractor implements the hubco Designed Portion Design Quality Plan (if applicable); and

    - the Contractor implements the Construction Quality Plan.

  - Where any aspect of the Works is performed by more than one contractor or sub-contractor, then the provisions of this Clause 20 (Quality Assurance) (in so far as relevant or appropriate to the activities to be performed by such contractor or sub-contractor) shall apply in respect of each of such contractors or sub-contractors, and references in this Clause 20 (Quality Assurance) to the "Contractor" shall be construed accordingly.  To avoid doubt, this Clause shall not be construed as requiring sub-contractors of the Contractor to have their own quality plans but only to comply with the hubco Designed Portion Design Quality Plan (if applicable) and the Construction Quality Plan.

  - hubco shall from time to time submit to the Authority's Representative in accordance with Schedule Part 7 (Review Procedure) any changes to any of the Quality Plans required for such Quality Plan to continue to comply with the requirements set out in Clause 20.2.  The Authority's Representative may raise comments on any such proposed change only on the grounds set out in paragraph 3.7 of Schedule Part 7 (Review Procedure).

  - If there is no objection under Schedule Part 7 (Review Procedure) to a change to any Quality Plan proposed pursuant to Clause 20.7, the Quality Plan shall be amended to incorporate such change.

Quality Manuals and Procedures

  - If any Quality Plan refers to, relies on or incorporates any quality manual or procedure, then such quality manual or procedure or the relevant parts of it shall be submitted to the Authority's Representative at the time that the relevant Quality Plan or part of (or change to) a Quality Plan is submitted in accordance with Schedule Part 7 (Review Procedure), and the contents of such quality manual or procedure shall be taken into account in the consideration of the relevant Quality Plan or part of (or change to) a Quality Plan in accordance with Schedule Part 7 (Review Procedure).

Quality Management

  - hubco shall maintain a quality management system which shall:-

    - ensure the effective operation of the quality systems described in this Clause 20 (Quality Assurance);

    - cause an audit of the quality systems at regular intervals and the findings of such audit will be reported to the Authority's Representative;

    - require review of all quality systems at intervals agreed with the Authority's Representative to ensure their continued suitability and effectiveness;

    - require liaison with the Authority's Representative on all matters relating to quality management; and

    - require production of reports and their delivery to hubco.

Quality Monitoring

  - The Authority's Representative may carry out audits of hubco's quality management system (including all relevant Quality Plans and any quality manuals and procedures) to establish that hubco is complying with Clauses 20.1 and 20.3. The Authority's Representative may carry out such audits at approximate intervals of three (3) months and may carry out other periodic monitoring, spot checks and auditing of hubco's quality management systems.  hubco shall procure that the Authority's Representative shall have an equivalent right in respect of the Contractor’s quality management services.  hubco shall co-operate and shall procure that any Sub-Contractor co-operates with the Authority's Representative including providing him with all information and documentation which he reasonably requires in connection with his rights under this Clause.

PART 5: INFORMATION TECHNOLOGY

- 21Information Technology

[PROJECT SPECIFIC]

PART 6: DELAY EVENTS, RELIEF EVENTS AND FORCE MAJEURE

- 22Delay Events

  - If, at any time, hubco becomes aware that there will be (or is likely to be) a delay in completion of the Works, hubco shall forthwith give notice to the Authority's Representative to that effect specifying the relevant delay or impediment.  In relation to any such delay or impediment if the Authority's Representative is satisfied, or it is determined in accordance with Schedule Part 15 (Dispute Resolution Procedure), that such delay or impediment has arisen as a result of the occurrence of a Delay Event, then, subject to Clause 23.4 (Mitigation) the Authority's Representative shall allow hubco an extension of time equal to the delay or impediment caused by such Delay Event (taking into account reasonably foreseeable consequences of the Delay Event) and shall revise the Completion Date.

  - If hubco is (or claims to be) affected by a Delay Event:-

    - it shall (and shall procure that the hubco Parties shall) take and continue to take all reasonable steps to eliminate or mitigate the consequences of such an event upon the performance of its obligations under this Agreement and, where relevant, resume performance of its obligations affected by the Delay Event as soon as practicable; and

    - it shall neither be relieved from liability under this Agreement nor entitled to any extension of time for the purpose of Clause 22.1 (Delay Event) to the extent that it is delayed or impeded due to its failure (if any) to comply with its obligations under Clause 22.2.1 above.

  - For the purposes of this Agreement, a Delay Event means any of the following to the extent in each case that there will be (or is likely to be) a delay in completion of the Works:-

    - an Authority's Works Variation initiated by an Authority's Works Variation Enquiry in accordance with paragraph 2 of Section 2 of Schedule Part 13 (Variation Procedure) in relation to which hubco has issued a response pursuant to paragraph 3.2.2(b) of Section 2 of Schedule Part 13 (Variation Procedure) specifying and providing evidence that implementation of the Authority's Works Variation would delay the completion of the Facilities if this has been agreed between the parties or determined to be the case in accordance with Schedule Part 15 (Dispute Resolution Procedure);

    - any breach by the Authority and/or any Authority Party of any of the Authority's express obligations under this Agreement to the extent in each case that any such breach is not caused, or contributed to, by hubco or any hubco Party;

    - the execution of works on the Site not forming part of this Agreement by the Authority or any contractors employed by the Authority;

    - opening up of the Works pursuant to Clauses 13.3 to 13.7 (inclusive) (Right to open up) where such Works are not subsequently found to be defective (unless it is agreed or determined in accordance with Schedule Part 15 (Dispute Resolution Procedure) that the opening up of the Works was reasonable in the light of other defects previously discovered by the Authority);

    - Force Majeure;

    - a Relief Event;

    - the suspension by hubco pursuant to Clause 27.9 of any or all obligations as a result of the non-payment by the Authority of sums properly due to hubco under this Agreement;

    - any inaccuracy, error, omission, defect or inadequacy in the Disclosed Data referred to in Clause 7.2;

    - any discrepancy or divergence between the Disclosed Data and the Authority’s Construction Requirements referred to in Clause 7.3;

    - any matters for which the Authority is responsible under Clause 10.1;

    - any inaccuracy, error, omission, defect or inadequacy in the Authority's Construction Requirements and/or the Authority Design Data referred to in Clause 12.10; or

    - any discrepancy or divergence within or between the Authority’s Construction Requirements, the Authority Design Data and/or Law referred to in Clause 12.10.

  - Without prejudice to the generality of Clause 22 (Delay Events), hubco shall give notice in writing to the Authority's Representative as soon as it (or the Contractor) can reasonably foresee a Delay Event occurring or, if the same is not reasonably foreseeable, as soon as it (or the Contractor) shall become aware of a Delay Event.  hubco shall within [           ] Business Days after such notification, give further written details to the Authority's Representative which shall include:-

    - a statement of which Delay Event the claim is based upon;

    - details of the circumstances from which the Delay Event arises;

    - details of the contemporary records which hubco will maintain to substantiate its claim for extra time;

    - details of the consequences (whether direct or indirect, financial or non-financial) which such Delay Event may have upon completion of the Facilities; and

    - details of any measures which hubco proposes to adopt to mitigate the consequences of such Delay Event.

  - As soon as possible but in any event within [          ] Business Days of hubco (or the Contractor) receiving, or becoming aware of, any supplemental information which may further substantiate or support hubco's claim then, provided that the Completion Date has not otherwise been revised pursuant to Clause 22.7, hubco shall submit further particulars based on such information to the Authority's Representative.

  - The Authority's Representative shall, after receipt of written details under Clause 22.4, or of further particulars under Clause 22.5, be entitled by notice in writing to require hubco to provide such further supporting particulars as he may reasonably consider necessary.  hubco shall afford the Authority's Representative reasonable facilities for investigating the validity of hubco's claim including, without limitation, on-site inspection.

  - Subject to the provisions of this Clause, the Authority's Representative shall revise the Completion Date in accordance with Clause 22.1 (Delay Events) as soon as reasonably practicable and in any event within [                    ] Business Days of the later of:-

    - the date of receipt by the Authority's Representative of hubco's notice given in accordance with Clause 22.4 and the date of receipt of any further particulars (if such are required under Clause 22.6), whichever is the later; and

    - the date of receipt by the Authority's Representative of any supplemental information supplied by hubco in accordance with Clause 22.5 and the date of receipt of any further particulars (if such are required under Clause 22.6), whichever is the later.

- If hubco has failed to comply with the requirements as to the giving of notice under Clause 22.4, or has failed to maintain records or afford facilities for inspection to the Authority's Representative, then hubco shall not be entitled to any extension of time (and the Completion Date shall not be revised) in respect of any period of delay by hubco in giving notice or providing information under Clause 22.4 and/or to the extent that its failure to maintain records or afford facilities for inspection to the Authority’s Representative has prevented the Authority’s Representative from assessing the consequences of the Delay Event.

  - If:-

    - the Authority's Representative declines to fix a revised Completion Date; or

    - hubco considers that a different Completion Date should be fixed; or

    - there is a disagreement as to whether a Delay Event has occurred,

- then hubco shall be entitled to refer the matter for determination in accordance with Schedule Part 15 (Dispute Resolution Procedure).

Compensation

  - If the Delay Event is a "Compensation Event", hubco's sole right to compensation shall be as provided for in Clauses 22.9 to 22.13 inclusive.  To avoid doubt, no other Delay Event shall entitle hubco to receive any compensation save as otherwise expressly provided in Schedule Part 13 (Variation Procedure) in the case of a Delay Event referred to in Clause 22.3.1.

  - For the purposes of Clause 22.9, a Compensation Event means;

    - any Delay Event referred to in Clause 22.3.2 (Breach), Clause 22.3.3 (Execution of non-project related works), Clause 22.3.4 (Opening up of Works) or Clause 22.3.7 (Suspension for non-payment), for which, in each case, it has been agreed or determined pursuant to this Clause 22 that hubco is entitled to an extension of time;

    - in the period prior to the Actual Completion Date, in circumstances where there is no delay in completion of the Works, ]any breach by the Authority and/or any Authority Party of any of the Authority's express obligations under this Agreement to the extent that such breach is not caused, or contributed to, by hubco or any hubco Party;

    - any inaccuracy, error, omission, defect or inadequacy in the Disclosed Data referred to in Clause 7.2;

    - any discrepancy or divergence between the Disclosed Data and the Authority’s Construction Requirements referred to in Clause 7.3;

    - any matters for which the Authority is responsible under Clause 10.1;

    - any inaccuracy, error, omission, defect or inadequacy in the Authority's Construction Requirements and/or the Authority Design Data referred to in Clause 12.10; or

    - any discrepancy or divergence within or between the Authority’s Construction Requirements, the Authority Design Data and/or Law referred to in Clause 12.10.

  - Subject to Clause 22.12, if it is agreed, or determined, that there has been a Compensation Event, and hubco has incurred loss (including loss of revenue) and/or expense as a direct result of such Compensation Event, hubco shall be entitled to such compensation as would place hubco in no better or no worse position than it would have been in had the relevant Compensation Event not occurred.  hubco shall promptly provide the Authority's Representative with any additional information he may require in order to determine the amount of such compensation.

  - hubco shall take all reasonable steps so as to minimise the loss or expense referred to in Clause 22.11 in relation to any Compensation Event and any compensation payable shall:-

    - exclude any amounts incurred or to be incurred as a result of any failure of hubco (or any hubco Party) to comply with this Clause 22.12; and

    - be reduced by any amount which hubco has recovered or will recover under any insurance policy (or would have recovered if it had complied with the requirements of this Agreement or of any policy of insurance required under this Agreement) which amount, to avoid doubt, shall not include any excess or deductibles or any amount over the maximum amount insured applicable to any such insurance policy.

  - The amount of any compensation due to hubco under Clause 22.11 shall be agreed between the parties or, failing agreement, determined pursuant to Schedule Part 15 (Dispute Resolution Procedure), and such compensation shall be payable within [twenty (20)] Business Days of written demand by hubco following agreement or determination of the amount due.

- 23Relief Events

  - For the purposes of this Agreement, subject to Clause 23.4 (Mitigation), Relief Events mean any of the following events:-

    - fire, explosion, lightning, storm, tempest, flood, bursting or overflowing of water tanks, apparatus or pipes, ionising radiation (to the extent it does not constitute Force Majeure), earthquake, riot or civil commotion;

    - failure by any statutory undertaker, utility company, local authority or other like body to carry out works or provide services;

    - accidental loss or damage to the Works and/or Facilities or any roads servicing the same;

    - blockade or embargo falling short of Force Majeure;

    - the discovery of fossils, antiquities and human remains requiring action in accordance with Clause 19 (Fossils and Antiquities); or

    - official or unofficial strike, lockout, go slow or other dispute in each case generally affecting the construction or building maintenance industry (or a significant sector of that industry),

provided in each case that such event does not arise (directly or indirectly) as a result of any wilful act or default of the party claiming relief and/or (i) in the case of hubco claiming relief, any hubco Party and (ii) in the case of the Authority claiming relief, any Authority Party.

  - Subject to Clauses 23.3 and 23.4, no right of termination shall arise under this Agreement by reason of any failure by a party to perform any of its obligations under this Agreement to the extent that such failure to perform occurs because of the occurrence of a Relief Event (and, to avoid doubt, and without prejudice to Clause 23.9 (No Compensation), unless expressly stated to the contrary in this Agreement, it is acknowledged that all other rights and obligations of the parties under this Agreement remain unaffected by the occurrence of a Relief Event).

  - Without prejudice to hubco's rights under Clause 22(Delay Events), hubco shall only be relieved of its obligations under Clauses 12 (The Design, Construction and Commissioning Process), 13 (Right of Access of Authority's Representative), 14 (Programme and Dates for Completion), 16 (Pre-Completion Commissioning and Completion) and 22 (Delay Events) by Delay Events in accordance with Clause 22 (Delay Events).

Mitigation

  - Where a party is (or claims to be) affected by a Relief Event:-

    - it shall take all reasonable steps to mitigate the consequences of such an event upon the performance of its obligations under this Agreement, resume performance of its obligations affected by the Relief Event as soon as practicable and use all reasonable endeavours to remedy its failure to perform; and

    - it shall not be entitled to rely upon the relief afforded to it pursuant to Clause 23.2 of this Agreement to the extent that it is not able to perform, or has not in fact performed, its obligations under this Agreement due to its failure (if any) to comply with its obligations under Clause 23.4.1 above.

  - The party claiming relief shall serve written notice on the other party within five (5) Business Days of it becoming aware of the relevant Relief Event.  Such initial notice shall give sufficient details to identify the particular event claimed to be a Relief Event.

  - A subsequent written notice shall be served by the party claiming relief on the other party within a further five (5) Business Days of the notice referred to in Clause 44 (Mitigation) which shall contain such relevant information relating to the failure to perform (or delay in performing) as is available, including (without limitation) the effect of the Relief Event on the ability of the party to perform, the action being taken in accordance with Clause 44 (Mitigation), the date of the occurrence of the Relief Event and an estimate of the period of time required to overcome it (and/or its effects).

  - The party claiming relief shall notify the other as soon as the consequences of the Relief Event have ceased and of when performance of its affected obligations can be resumed.

  - If, following the issue of any notice referred to in Clause 23.6, the party claiming relief receives or becomes aware of any further information relating to the Relief Event (and/or any failure to perform), it shall submit such further information to the other party as soon as reasonably possible.

  - To avoid doubt, the occurrence of a Relief Event shall not entitle hubco to any compensation.

- 24Force Majeure

  - For the purposes of this Agreement, Force Majeure means any of the following events or circumstances:-

    - war, civil war, armed conflict or terrorism; or

    - nuclear Contamination unless in any case hubco and/or any hubco Party is the source or the cause of the Contamination; or

    - chemical or biological Contamination of the Works and/or the Facilities and/or the Site from any of the events referred to in Clause 24.1.1 above; or

    - pressure waves caused by devices travelling at supersonic speeds,

which directly causes either party to be unable to comply with all or a material part of its obligations under this Agreement.

  - Subject to Clauses 24.3 and 24.4 the party claiming relief shall be relieved from liability under this Agreement to the extent that by reason of the Force Majeure it is not able to perform its obligations under this Agreement.  For the avoidance of doubt (but without prejudice to Clause 33 (Termination Resulting from Force Majeure)) the Authority shall not be entitled to terminate this Agreement for a hubco Event of Default if such hubco Event of Default arises from an event of Force Majeure.

  - Where a party is (or claims to be) affected by an event of Force Majeure:-

    - it shall take all reasonable steps to mitigate the consequences of such an event upon the performance of its obligations under this Agreement, resume performance of its obligations affected by the event of Force Majeure as soon as practicable and use all reasonable endeavours to remedy its failure to perform; and

    - it shall not be relieved from liability under this Agreement to the extent that it is not able to perform, or has not in fact performed, its obligations under this Agreement due to its failure (if any) to comply with its obligations under Clause 24.3.1.

  - Without prejudice to hubco's rights under Clause 22 (Delay Events), hubco shall only be relieved from its obligations under Clauses 12 (The Design, Construction and Commissioning Process), 13 (Right of Access of Authority's Representative), 14 (Programme and Dates for Completion) and 22 (Delay Events) by Delay Events in accordance with Clause 22 (Delay Events).

  - The party claiming relief shall serve written notice on the other party within five (5) Business Days of it becoming aware of the relevant event of Force Majeure.  Such initial notice shall give sufficient details to identify the particular event claimed to be an event of Force Majeure.

  - A subsequent written notice shall be served by the party claiming relief on the other party within a further five (5) Business Days which shall contain such relevant information relating to the failure to perform (or delay in performing) as is available, including (without limitation) the effect of the event of Force Majeure on the ability of the party to perform, the action being taken in accordance with Clause 24.3, the date of the occurrence of the event of Force Majeure and an estimate of the period of time required to overcome it (and/or its effects).

  - The party claiming relief shall notify the other as soon as the consequences of the event of Force Majeure have ceased and of when performance of its affected obligations can be resumed.

  - If, following the issue of any notice referred to in Clause 24.6, the party claiming relief receives or becomes aware of any further information relating to the event of Force Majeure (and/or any failure to perform), it shall submit such further information to the other party as soon as reasonably possible.

Modifications

  - The parties shall endeavour to agree any modifications to the Agreement which may be equitable having regard to the nature of an event or events of Force Majeure.  Schedule Part 15 (Dispute Resolution Procedure) shall not apply to a failure of the Authority and hubco to reach agreement pursuant to this Clause 24.9.

Consequences of termination

  - Without prejudice to Clause 35.7, the occurrence of an event of Force Majeure shall not entitle hubco to any compensation.

- PART 7:	CHANGES IN LAW & VARIATIONS

- 25Changes in Law

General

  - hubco shall take all steps necessary to ensure that the Project Operations are performed in accordance with the terms of this Agreement (including, without limitation, Clause 5.2.1 (Compliance with applicable law)) following any Change in Law.

Variation to be agreed

  - Either party may give notice to the other of the need for a Variation which is necessary in order to enable hubco to comply with any Change in Law in which event:

    - the parties shall meet within [                    ] Business Days to consult in respect of the effect of the Change in Law and any Variation required as a consequence; and

    - within [                    ] Business Days of the meeting referred to in Clause 25.2.1 above the Authority's Representative shall, if a Variation is required in order to comply with the Change in Law, issue a Variation Enquiry and the relevant provisions of Part 13 of the Schedule (Variation Procedure) shall apply except that:

    - hubco may give notice to the Authority's Representative that it objects to such a Variation Enquiry only on the grounds that the implementation of the Variation would not implement the Change in Law;

    - the Authority shall issue a Variation Confirmation in respect of the Variation in accordance with the relevant provisions of Part 13 of the Schedule (Variation Procedure);

    - the provisions of Clause 11 (Consents and Planning Approval) shall apply and, to avoid doubt, the provisions of paragraph 5 of Section 2 of Part 13 of the Schedule (Variation Procedure) shall not apply;

    - the Authority shall not be entitled to withdraw any Variation Enquiry or Variation Confirmation issued in accordance with this Clause 25.2; and

    - not used.

- 26VARIATION PROCEDURE

The provisions of Schedule Part 13 (Variation Procedure) shall have effect in respect of Variations except as otherwise expressly provided in this Agreement.

PART 8: FINANCIAL

- 27PAYMENT

Development Amount

    - The Authority shall, in accordance with the provisions of this Clause 27, pay to hubco the Development Amount in consideration of the performance by hubco of its obligations under this Agreement in accordance with this Agreement.

    - The Development Amount shall be a lump sum fixed price for the carrying out of hubco's obligations under the Agreement and shall not be altered or adjusted in any way whatsoever (and hubco shall not be entitled to any payment in respect of the Works or this Agreement) except in accordance with the express provisions of this Agreement.

Project Development Fee

    - The Authority shall pay the Project Development Fee to hubco. The due date for payment of the Project Development Fee shall be the date of the Authority’s receipt of the relevant invoice. Within five (5) days after the due date for payment the Authority's Representative shall issue a payment notice detailing the sum that the payer considers to be or to have been due at the payment due date and the basis on which that sum is calculated. The final date for payment shall be 5 days after the due date.

Applications for Payment

  - No later than each Application Date, hubco shall make an application ("Application for Payment") to the Authority’s Representative for an interim certificate of payment in respect of that Relevant Month.  Each Application for Payment shall be in accordance with Clause 27.3 below and include such supporting information and documentation as is reasonably required by the Authority in order to prepare and issue an Interim Certificate (as defined in Clause 27.5).  The payment due date for an interim Certificate (as defined in Clause 27.5) in respect of a Relevant Month shall be the Application Date (the "Due Date").

Form of Application

  - Without prejudice to Clause 27.4 (Value of Goods and Materials), each Application for Payment shall specify:

    - the cumulative value claimed by hubco of Works properly executed up to the end of the Relevant Month as set out in Schedule Part 11 (Development Amount Analysis) as amended from time to time in accordance with this Agreement;

    - the cumulative amount of any other payments to which hubco claims to be entitled under this Agreement up to the end of the Relevant Month;

    - where Clause 27.6 applies the applicable Retention; and

    - the amount hubco considers is due on the Due Date and the basis upon which that amount has been calculated including a breakdown of the cumulative value of Works properly executed up to the end of the Relevant Month by specific reference to each of the elements set out in the Development Amount Analysis; and

    - the breakdown of the amount hubco considers is due on the Due Date into the separate amounts that hubco considers to be due to:

      - hubco in accordance with this Agreement but excluding the amounts due under Clause 27.3.5(b), (c) and (d) and, for the avoidance of doubt, the Project Development Fee;

      - the Contractor in accordance with the Construction Contract but excluding the amounts due under Clause 27.3.5(c) and (d);

      - each PBA Sub-Contractor in accordance with its Sub-Contract; and

      - each Non-PBA Sub=Contractor in accordance with its Sub-Contract.

Value of Goods and Materials

  - If an Application for Payment includes any amount in respect of payment for goods or materials before incorporation thereof in the Works, the following provisions shall apply:

    - hubco shall provide the Authority with proof that property in such goods or materials is vested in hubco;

    - hubco shall ensure that the goods or materials are set apart from other goods or materials at the place where they are manufactured or stored and that they are clearly identified as being the property of the Authority without damaging or defacing them, and shall provide proof of compliance with this requirement.  hubco shall bear the risk of loss or damage to such materials or goods;

    - unless and until hubco has complied with Clauses  27.4.1 and 27.4.2 above, hubco shall not be entitled to any payment in respect of such goods or materials;

    - such goods or materials shall become the property of the Authority upon payment therefor;

    - hubco shall permit the Authority, the Authority's Representative and any other persons authorised by the Authority at any time upon reasonable notice to inspect the materials or goods which have become the property of the Authority and shall grant or procure the grant of access to the Authority, the Authority's Representative and any other person authorised by the Authority for such purpose to the premises where such goods or materials may be located;

    - payment by the Authority for such goods or materials shall not prejudice the rights of the Authority in relation to goods or materials which are not in accordance with this Agreement.

Issue of Interim Certificate

  - Within two (2) Business Days (which, for the purposes of this Clause 27.5 only shall include bank holidays in Edinburgh) of the Due Date, the Authority’s Representative shall issue an interim certificate of payment (an "Interim Certificate") setting out the sum that the Authority or the Authority's Representative considers to be or to have been due at the Due Date, and the basis on which that sum is calculated, including:

    - the cumulative value of Works properly executed as at the end of the Relevant Month in question;

    - the cumulative value of any Variation instructed in accordance with Clause 26 (Variation Procedure); and

    - the cumulative amount of any other payments to which hubco is entitled under this Agreement as at the end of the Relevant Month in question to the extent not paid under another provision of this Agreement;

LESS

    - where Clause 27.6 applies, the applicable Retention;

    - any sums due from hubco to the Authority or deductions to be made under this Agreement; and

    - the amounts certified for payment in Interim Certificates previously issued,

and stating the balance (if any) due from the Authority to hubco or from hubco to the Authority.

It is immaterial that the sum referred to in this Clause 27.5 may be zero. If hubco fails submit an Application for Payment and supporting information and documentation in accordance with Clause 27.2 and Clause 27.3 above in respect of a Relevant Month by the relevant Application Date then the sum referred to in this Clause 27.5 shall be zero.  If the Authority fails to give an Interim Certificate in accordance with Clause 27.5, and hubco have given an Application for Payment in accordance with Clause 27.2 and 27.3, the sum to be paid by the Authority shall, subject to any Pay Less Notice given under Clause 27.11, be the sum specified in the Application for Payment.

  - Retention

    - Not used.

    - The Authority shall be entitled to deduct and retain [        ] per cent ([ ]%) of the total aggregate amounts specified in Clause 27.5 to 27.5.3 from time to time (provided that credit shall be given in respect of amounts retained previously) (the "Retention").

    - The following provisions shall apply to the Retention:-

      - the Authority shall owe no fiduciary duty to hubco in respect of the Retention;

      - any interest earned on the Retention shall be permanently retained by the Authority;

      - no later than 10 Business Days after the Actual Completion Date, the Authority shall pay to hubco one-half of the Retention deducted and retained (less any amounts or liabilities duly paid or incurred by the Authority in accordance with Clause 27.6.4);

      - no later than 10 Business Days after the issue of the Certificate of Making Good Defects, the Authority shall pay to hubco the balance of the Retention deducted and retained (less any amounts or liabilities duly paid or incurred by the Authority in accordance with Clause 27.6.4); and

      - the Authority shall not hold the Retention in the Project Bank Account.

    - In the event that hubco fails to comply with its obligations under Clause 17 (Defects) to rectify a Defect, the Authority shall be entitled to deduct from the balance of the Retention from time to time such amounts as are equal to the costs, reasonably and properly incurred by the Authority in rectifying, or procuring the rectification of any such Defect.

    - Not used.

    - Not used.

Non-Compliant Works

  - By each Interim Certificate the Authority gives notice to hubco specifying the amount of the payment proposed to be made and the basis upon which it is calculated.  For the avoidance of doubt, no sum shall be included in any Interim Certificate if, in the reasonable opinion of the Authority, any Works to which the Interim Certificate relates do not comply with the provisions of this Agreement, in which event the amount relating to such non-compliant Works shall be omitted from such Interim Certificate and such sum shall only be included in an Interim Certificate following rectification of such Works by hubco to the satisfaction of the Authority (acting reasonably).

Date for payment

  - Following receipt of an Interim Certificate from the Authority, hubco shall within two (2) Business Days of the date of issue of such Interim Certificate, submit an invoice to the Authority for the amount certified in such Interim Certificate together with a Payment Instruction.  The final date for payment of such amount (the "Final Date") shall be seven (7) Business Days after the Authority’s receipt of hubco’s invoice and Payment Instruction.

Right to suspend

  - Without prejudice to any other rights and remedies which hubco may possess, if:-

    - the Authority fails to pay any sum due pursuant to Clause 27.8 by the Final Date; and

    - it has not given a notice pursuant to Clause 27.11 in respect of such sum: and

    - such failure continues for a period of seven (7) days after hubco has given to the Authority written notice of its intention to suspend performance of any or all of its obligations under this agreement and the ground or grounds on which it is intended to suspend performance,

then hubco may, following the expiry of such seven (7) day period, suspend performance of any or all of its obligations under this Agreement until payment in full of the sum payable occurs.

27.9A.1	Where hubco exercises its right of suspension under Clause 29.9.3, it shall be entitled to a reasonable amount in respect of costs and expenses reasonably incurred by it as a result of the exercise of the right.

29.9A.2 	Applications in respect of any such costs and expenses shall be made to the Authority and hubco shall with its Application for Payment provided for in Clause 27.2, in the month following the month in which the right arose, submit such details of the costs and expenses as are reasonably necessary to enable hubco's entitlement to be ascertained

  - Statement of Final Account and issue of Payment Certificate

    - Without prejudice to Clause 27.2 (Applications for Payment), within [one month] of the date of issue of the Certificate of Completion, hubco shall submit to the Authority's Representative a statement of final account and supporting documents showing in detail the value in accordance with this Agreement of all work executed and all further sums which hubco considers to be due to it in respect of the Works in accordance with this Agreement.

    - If hubco has not submitted a statement of final account to the Authority's Representative by the date [one month] after the date on which it was required to do so pursuant to Clause 27.10.1, the Authority's Representative may give notice to hubco in writing that if such a statement of final account is not prepared and submitted by hubco after a further [one month] the Authority's Representative may do so itself.  Upon the expiry of that [one month] period of notice or within [one month] of the issue of the Certificate of Making Good Defects, whichever is the later, (if hubco has not prepared and submitted a statement of final account and supporting documents) the Authority's Representative may prepare a statement of final account and issue it to hubco.

    - The due date for payment of the final account shall be within [          ] Business Days after whichever is the later of (i) the date of issue of the Certificate of Making Good Defects, (ii) receipt of hubco's statement of final account pursuant to Clause 27.10.1 or (iii) the Authority issuing a statement of final account under Clause 27.10.2 the “Payment Certificate Due Date”).  Within 5 days of the Payment Certificate Due Date the Authority's Representative shall issue to hubco a certificate (a "Payment Certificate") stating the sum that the Authority or the Authority's Representative considers to be or have been due at the Payment Certificate Due Date and the basis on which that sum is calculated including the value in accordance with this Agreement, of all Works carried out by hubco and all the sums due to hubco in accordance with this Agreement less the sum of the amounts already certified by Interim Certificates and all sums due from hubco to the Authority or deductions to be made under this Agreement, and showing the balance payable from hubco to the Authority or from the Authority to hubco, as the case may be.  It is immaterial that the sum referred to in this Clause 27.10.3 may be zero.

- 27.10.3A If the Authority fails to issue the Payment Certificate in accordance with Clause 27.10.3, and if hubco have submitted a hubco statement of final account pursuant to Clause 27.10.1, hubco's statement of final account shall take effect as if it were the Payment Certificate.

- 27.10.3B If the Payment Certificate under Clause 27.10.3 provides that hubco requires to make a payment to the Authority, the Authority may recover the same as a debt.

    - Following receipt of a Payment Certificate hubco shall submit an invoice to the Authority for the amount certified in such Payment Certificate.  The final date for payment of such amount (the "Payment Certificate Final Date") shall be fifteen (15) Business Days after the Authority’s receipt of hubco’s invoice.

    - A Payment Certificate issued pursuant to this Clause 27.10 shall at the expiry of one month after it is issued (save in respect of fraud) have effect in any proceedings arising out of or in connection with this Agreement as:

      - conclusive evidence that all and only such extensions of time, if any, as are due have been given; and

      - conclusive evidence that the payment to hubco of all and any additions to or increases in the Development Amount shall be in full and final settlement of all and any claims which hubco has or may have arising out of or in connection with this Agreement or in relation to the Works whether such claims may be for breach of contract, in delict, for breach of statutory duty or otherwise.

  - Pay Less Notice

- If the Authority intends in good faith to pay less than the sum notified pursuant to a Payment Certificate or Interim Certificate (or Application for Payment if the final sentence of Clause 27.5 applies), the Authority or the Authority’s Representative shall, at least four (4) Business Days before the Final Date or Payment Certificate Final Date give a notice (a “Pay Less Notice”) to hubco. Such Pay Less Notice shall specify both the sum that it considers to be due to hubco at the date the Pay Less Notice is given and the basis on which that sum has been calculated. It is immaterial that the sum referred to in this Clause 27.11 may be zero.

Revised Payment Instruction

27.11A	If the Authority gives a Pay Less Notice to hubco in accordance with Clause 27.11, then hubco shall submit a Revised Payment Instruction to the Authority by no later than the date falling one (1) Business Day prior to the Final Date.

27.11B	If hubco does not comply with Clause 27.11A then the PBA Beneficiary Amounts shall be deemed to be reduced on an equal pro rata basis based on the difference between the amount certified in an Interim Certificate and the amount specified as considered by the Authority to be due pursuant to a Pay Less Notice issued in accordance with Clause 27.11 (a “Deemed Allocation”).

Adjustments to Certificates

  - If any sum shall become due to hubco under this Agreement otherwise than for work executed, the amount thereof shall (provided hubco has submitted an Application for Payment therefore in accordance with Clause 27.2) be included in the next Interim Certificate.  If any sum shall become payable under this Agreement by hubco to the Authority, whether by deduction from the Development Amount or otherwise, the same shall become due on the date on which hubco receives a written demand for the same from the Authority and shall be paid by hubco to the Authority within twenty (20) Business Days (being the final date for payment) of such written demand or, at the option of the Authority, the amount thereof may be deducted from the next Interim Certificate (or Application for Payment if the final sentence of Clause 27.5 applies) and (if necessary) from subsequent Interim Certificates (or Applications for Payment if the final sentence of Clause 27.5 applies).

Correction of Certificates

  - The Authority may in any Interim Certificate or Payment Certificate make any correction or modification that should properly have been made in respect of any previous Interim Certificate.

Effect of Certificates

  - No certificate shall of itself be conclusive evidence that any design, works, materials or goods to which it relates are in accordance with this Agreement and, without prejudice to the generality of the foregoing, the issue of an Interim Certificate or of the Payment Certificate shall not prejudice any right of the Authority against hubco in respect of any defect in the Works (including the Authority's rights under Clause 17 (Defects)).

Manner of payment

  - Subject to Clause 27.15A, all payments under this Agreement shall be made in pounds sterling by electronic transfer of funds for value on the day in question to the bank account of the recipient (located in the United Kingdom) specified in the relevant invoice (or otherwise notified to the payer by the recipient), quoting the invoice number against which payment is made.

- 27.15A	Any sum due by the Authority pursuant to Clause 27.8 shall be made in pounds sterling by electronic transfer of funds for value on the day in question to the Project Bank Account, quoting the invoice number against which payment is made.  Payments made by the Authority into the Project Bank Account are deemed to be payments from the Authority to hubco in accordance with this Agreement.

Disputes

  - If either party (acting in good faith) disputes all or any part of the Interim Certificate calculated in accordance with this Clause 27 (Payment) or the Payment Certificate (subject to Clause 27.10.5), the undisputed amount of the Interim Certificate or Payment Certificate (as the case may be) shall be paid by the Authority in accordance with Clause 27.8 or 27.10.4 (as the case may be) and the provisions of this Clause 27.16 shall apply.  The parties shall use all reasonable endeavours to resolve the dispute in question within [                    ] Business Days of the dispute arising.  If they fail so to resolve it, either party may refer the matter to the Dispute Resolution Procedure.  Following resolution of the dispute, any amount agreed or determined to have been payable shall be paid forthwith by the Authority to hubco, together with interest on such amount calculated in accordance with Clause 27.17(Late Payments).

Late Payments

  - Each party shall be entitled, without prejudice to any other right or remedy, to receive interest on any payment not duly made pursuant to the terms of this Agreement on the Final Date or Payment Certificate Final Date (as the case may be) calculated from day to day at a rate per annum equal to the Default Interest Rate from the Final Date or Payment Certificate Final Date (as the case may be) up to and including the date of payment.

Set-Off

  - Whenever any sum of money shall be agreed, or determined, as due and payable by hubco to the Authority, such sum may at the Authority's discretion be deducted from or applied to reduce the amount of any sum then due, or which at any time afterwards may become due, to hubco from the Authority under this Agreement provided that the Authority has issued a Pay Less Notice.

  - Whenever any sum of money shall be agreed, or determined, as due and payable by the Authority to hubco, such sum may at hubco's discretion be deducted from or applied to reduce the amount of any sum then due, or which at any time afterwards may become due, from hubco to the Authority under this Agreement provided that hubco has given the Authority not less than [                    ] Business Days' notice of its intention to deduct or apply such sum.

- Project Bank Account

  - Within five (5) Business Days of the earlier of:

    - the date of appointment of each Qualifying Sub-Contractor by the Contractor to undertake sub-contract works (including off-site fabrication) in connection with the Project; and

    - the date falling five (5) Business Days prior to each Qualifying Sub-Contractor commencing sub-contract works (including off-site fabrication) in connection with the Project,

- hubco shall procure and deliver to the Authority an original version of a Joining Declaration duly executed by hubco, the Contractor and the relevant Qualifying Sub-Contractor.

  - the Authority shall execute the relevant Joining Declaration within five (5) Business Days of receipt of the same from hubco.

  - Where any Qualifying Sub-Contractor declines to enter into a Joining Declaration, hubco shall procure that the Contractor uses all reasonable endeavours to obtain disclosure from the Qualifying Sub-Contractor of the reasons for such refusal.  hubco shall procure that the Contractor seeks to persuade the Qualifying Sub-Contractor to re-consider its position.  hubco shall procure that the Contractor shall record this process and provide copies of such records to hubco who shall, in turn, provide such records to the Authority.

  - hubco shall procure that the Contractor informs each Below Threshold Sub-Contractor that the Below Threshold Sub-Contractor may make a Joining Request at any time.

  - hubco shall procure that the Contractor communicates every Joining Request by a Below Threshold Sub-Contractor to hubco within five (5) Business Days of such Joining Request being received by the Contractor.

  - hubco shall communicate each Joining Request by a Below Threshold Sub-Contractor to the Authority’s Representative within five (5) Business Days of such Joining Request being communicated to hubco by the Contractor.

  - Following the receipt of any Joining Request by a Below Threshold Sub-Contractor, the Authority and hubco shall discuss with the Contractor whether it is practicable and desirable for payments to the Below Threshold Sub-Contractor to be made through the Project Bank Account having regard to the number, timing and value of such payments.  If the Authority, hubco and the Contractor agree that payments to the Below Threshold Sub-Contractor should be made through the Project Bank Account then hubco shall procure and deliver to the Authority an original version of a Joining Declaration duly executed by hubco, the Contractor and the relevant Below Threshold Sub-Contractor.  The Authority shall thereafter execute the relevant Joining Declaration within five (5) Business Days of receipt of the same from hubco.  If the Authority, hubco and the Contractor do not agree that payments to the Below Threshold Sub-Contractor should be made through the Project Bank Account then hubco shall write to the Authority and fully explain the reasons for the failure to so agree.

  - If this Agreement is terminated no further monies shall be payable into the Project Bank Account.

  - Within [two (2) months] of the date of issue of the Certificate of Completion, hubco shall submit to the Authority's Representative a summary report relating to the use and operation of the Project Bank Account specifying (as a minimum):

    - the total amount of payments made through the Project Bank Account to PBA Beneficiaries;

    - the total amount of payments made through the Project Bank Account to PBA Sub-Contractors;

    - the total amount of payments made through the Project Bank Account to the Contractor in respect of Non-PBA Sub-Contractors;

    - the reasons for any Qualifying Sub-Contractor failing to be paid through the Project Bank Account; and

    - lessons learned from the use and operation of the Project Bank Account, including feedback from the Contractor and PBA Sub-Contractors.

- 28VAT

  - All amounts stated to be payable by either party under this Agreement shall be exclusive of any VAT properly chargeable on any amount.

  - Each party shall pay to the other party any VAT properly chargeable on any supply made to it under this Agreement provided that it shall first have received from the other party a valid tax invoice in respect of that supply which complies with the requirements of Part III Value Added Tax Regulations 1995.

  - If either party (referred to in this Clause as the "First Party") shall consider that any VAT which the other party (referred to in this Clause as the "Second Party") claims to be properly chargeable to the First Party in connection with this Agreement is not in fact properly so chargeable, the First Party shall be entitled to require the Second Party to obtain a clearance from the Commissioners for Revenue & Customs (or, if relevant, such other body as is charged at the time with the collection and management of VAT) (referred to in this Clause as the "Commissioners") as to the VAT (if any) properly so chargeable.  The Second Party shall forthwith request the Commissioners for such a clearance.

  - The following further provisions shall apply in respect of the application for a clearance in accordance with Clause 28.3:-

    - prior to submitting its request for such a clearance and any further communication to the Commissioners in connection with the obtaining of the clearance, the Second Party shall first obtain the agreement of the First Party to the contents of such request and any such further communication, such agreement not to be unreasonably withheld or delayed;

    - the Second Party shall provide to the First Party copies of all communications received from the Commissioners in connection with the application for a clearance as soon as practicable after receipt; and

    - the Second Party shall use all reasonable endeavours (including without limitation the provision of such additional information as the Commissioners may require) to obtain such a clearance as soon as reasonably practicable following the initial request.

  - If a clearance is required by the First Party under Clause 28.3, the First Party shall not be obliged to pay the VAT so claimed by the Second Party unless and until a clearance is received from the Commissioners which states that a sum of VAT (the "VAT Sum") is properly so chargeable or the Commissioners state that they are not prepared to give any clearance on the matter.  In this case, then subject to Clauses 28.6 and 28.7 and provided that the First Party shall first have received a valid tax invoice which complies with the requirements of Part III Value Added Tax Regulations 1995 and which states the VAT Sum to be the amount of VAT chargeable to the First Party, the First Party shall pay the VAT Sum (and any interest or penalties attributable to the VAT Sum) to the Second Party.

  - If the First Party disagrees with any clearance obtained pursuant to Clause 28.3 by the Second Party from the Commissioners, then the Second Party (provided that it is indemnified to its reasonable satisfaction against all costs and expenses including interest and penalties which it may incur in relation thereto) shall take such action and give such information and assistance to the First Party as the First Party may require to challenge such clearance or otherwise to resist or avoid the imposition of VAT on the relevant supply.

  - The following further provisions shall apply if the First Party shall exercise its rights under Clause 28.6:-

    - the action which the First Party shall be entitled to require the Second Party to take shall include (without limitation) contesting any assessment to VAT or other relevant determination of the Commissioners before any tax tribunal or court of competent jurisdiction and appealing any judgement or decision of any such tribunal or court;

    - if the Second Party shall be required to pay to or deposit with the Commissioners a sum equal to the VAT assessed as a condition precedent to its pursuing any appeal, the First Party shall, at its election, either pay such sum to the Commissioners on behalf of the Second Party or on receipt of proof in a form reasonably satisfactory to the First Party that the Second Party has paid such sum to or deposited such sum with the Commissioners the First Party shall pay such sum to the Second Party;

    - save as specifically provided in Clause 28.4, the First Party shall not be obliged to pay to the Second Party any sum in respect of the VAT in dispute to the Second Party or in respect of VAT on any further supplies made by the Second Party to the First Party which are of the same type and raise the same issues as the supplies which are the subject of the relevant dispute unless and until the final outcome of the relevant dispute is that it is either determined or agreed that VAT is properly chargeable on the relevant supply or supplies; and

    - the Second Party shall account to the First Party for any costs awarded to the Second Party on any appeal, for any sum paid to or deposited with the Commissioners in accordance with Clause 28.7.2 which is repayable to the Second Party and for any interest to which the Second Party is entitled in respect of such sums.

Changes in recoverability of VAT

  - Subject to Clause 28.9, if, following a Change in Law, hubco becomes unable to recover VAT attributable to supplies to be made to the Authority by hubco pursuant to this Agreement, the Authority shall ensure that hubco is left in no better and no worse position than it would have been had such Change in Law not occurred (including but not limited to making such amendments to this Agreement as hubco and the Authority shall agree acting reasonably), provided that hubco shall use all reasonable endeavours to mitigate the adverse effects of any such Change in Law.

  - The provisions of Clause 28.8 shall apply only if (and to the extent that) the Change in Law was not reasonably foreseeable at the date of this Agreement by an experienced contractor performing operations similar to the relevant Project Operations on the basis of draft bills published in Government green or white papers or other Government departmental consultation papers, bills, draft statutory instruments or draft instruments or proposals published in the Official Journal of the European Union, in each case published:

    - prior to the date of this Agreement; and

    - in substantially the same form as the Change in Law.

- 29Construction Industry Tax Deduction Scheme

  - This Clause 29.1 relates to the Construction Industry Tax Deduction Scheme:-

    - In this Clause 29.1 (but not otherwise):-

      - "the Act" means the Finance Act 2004;

      - "the Regulations" means the Income Tax (Construction Industry Scheme) Regulations 2005 (SI 2005/2045);

      - “the Legislation” means Chapter 3 Part 3 of the Act and the Regulations, taken together;

      - "Contractor" means a person who is a contractor for the purposes of Chapter 3 Part 3 of the Act; and

      - "sub-contractor" means a person who is a sub-contractor for the purposes of Chapter 3 Part 3 of the Act,

    - Each of the Authority and hubco shall comply with the Legislation.

    - If any payment due from the Authority to hubco under this Agreement is a contract payment under section 60(1) of the Act, then the Authority, as Contractor, shall (not later than fifteen (15) Business days before the first such payment is due to be made) verify, in accordance with Regulation 6 of the Regulations, whether the sub-contractor is registered for gross payment or for payment under deduction or is not registered under Chapter 3 Part 3 of the Act.

    - If any payment due from the Authority to hubco under this Agreement is a contract payment under section 60(1) of the Act, then:-

      - if hubco is registered for gross payment under section 63(2) of the Act, the Authority shall make a payment to hubco without any deduction;

      - if hubco is not registered for gross payments under section 63(2) of the Act, the Authority shall make a payment to hubco, subject to the deduction of the relevant percentage in accordance with section 61(1) of the Act, and thereupon Clause 29.1.7 below shall apply.

    - If any dispute arises between the Authority and hubco as to whether any payment due by the Authority to hubco under this Agreement is or is not a contract payment by virtue of the exemption in Regulation 23 of the Regulations, the parties will jointly apply to HM Revenue and Customs for a written clearance and until such clearance is received it shall be assumed that such payment is a contract payment and the provisions of this Clause 29.1 (Construction Industry Tax Deduction Scheme) shall apply accordingly.

    - The Authority shall be entitled to make a deduction at the rate specified in section 61(1) of the Act or at such other rate as may be in force from time to time from the whole of any payment to hubco (and not just that part of such payment which does not represent the direct cost to hubco or any other person of materials used or to be used in carrying out the construction operations to which the relevant payment relates) unless prior to making such payment the Authority shall have received written confirmation from HM Revenue and Customs (obtained by and at the expense of hubco) in a form which is reasonably satisfactory to the Authority directing the Authority to make the deduction against only a specified amount or proportion of any such payment to hubco.

    - Where any error or omission has occurred in calculating or making any payment under this Clause 29.1 (Construction Industry Tax Deduction Scheme) then:-

      - in the case of an over deduction, the Authority shall correct that error by repayment of the sum over deducted to hubco; and

      - in the case of an under deduction, hubco shall correct that error or omission by repayment of the sum under deducted to the Authority.

    - The Authority shall send promptly to HM Revenue & Customs any returns required by the Legislation, and shall provide to hubco a payment statement (where appropriate) and/or such other information as may be required by the Legislation in relation to any contract payment.

    - If compliance with this Clause 29.1 involves the Authority or hubco in not complying with any other of the terms of this Agreement, then the provisions of this Clause shall prevail.

- 30RECORDS AND OPEN BOOK ACCOUNTING

Records and Reports

The provisions of Schedule Part 14 (Record Provisions) shall apply to the keeping of records and the making of reports.

PART 9: TERMINATION

- 31Authority Events of Default

  - For the purposes of this Agreement, an Authority Event of Default means any of the following events or circumstances:-

    - the Authority is in material breach of its obligations under Clause 9 or Clause 11 (other than as a consequence of a breach by hubco of its obligations under this Agreement) and such breach materially adversely affects the ability of hubco to perform its material obligations under this Agreement for a continuous period of not less than thirty (30) Business Days;

    - the Authority fails to pay any sum or sums due to hubco under this Agreement (which sums are not in dispute) which, either singly or in aggregate, exceed(s) [£  ] from time to time and such failure continues for thirty (30) Business Days from receipt by the Authority of a notice of non-payment from hubco;

    - the Authority is in breach of its obligations under Clause 43.3;

    - an expropriation, sequestration or requisition of a material part of the assets and/or shares of hubco by the Authority or a Relevant Authority; or

    - the Authority is sequestrated under the Bankruptcy (Scotland) Act 2016 or otherwise becomes insolvent and its obligations are not otherwise transferred to another party such as is referred to in Clause 43.3.

- hubco's options

  - On the occurrence of a Authority Event of Default, or within a reasonable time after hubco becomes aware of the same, and while the same is still subsisting, hubco may, at its option:-

    - suspend performance by it of its obligations under this Agreement until such time as the Authority shall have demonstrated to the reasonable satisfaction of hubco that it is capable of performing, and will perform, its obligations under this Agreement; or

    - serve notice on the Authority (or such other party as may be notified in advance in writing by the Authority to hubco) of the occurrence (and specifying details) of such Authority Event of Default.  If the relevant matter or circumstance has not been rectified or remedied by the Authority (or otherwise) in respect of Clause 31.1.1, Clause 31.1.3, Clause 31.1.4 or Clause 31.1.5 within sixty (60) Business Days of such notice, and in respect of Clause 31.1.2 within thirty (30) Business Days of such notice, hubco may serve a further notice on the Authority (or its substitute notified in accordance with this Clause 31.2.2) terminating this Agreement with immediate effect.

  - hubco shall not exercise or purport to exercise any right to terminate this Agreement (or accept any repudiation of this Agreement) except as expressly set out in this Agreement.

- 32HUBCO DEFAULT

hubco Events of Default

  - For the purposes of this Agreement, hubco Event of Default means any of the following events or circumstances:-

Insolvency

    - the occurrence of any of the following events in respect of hubco, namely:-

      - any arrangement or composition with or for the benefit of creditors (including any voluntary arrangement as defined in the Insolvency Act 1986) being entered into by or in relation to hubco;

      - a receiver, administrator, administrative receiver or other encumbrance taking possession of or being appointed over, or any distress, execution or other process being levied or enforced (and not being discharged within ten (10) Business Days) upon, the whole or any material part of the assets of hubco;

      - hubco ceasing to carry on business;

      - a petition being presented (and not being discharged within twenty (20) Business Days), or a resolution being passed or an order being made for the administration or the winding-up, bankruptcy or dissolution of hubco; or

      - [if hubco shall suffer any event analogous to the events set out in Clauses 32.(a)-(d) in any jurisdiction in which it is incorporated or resident];

Long stop

    - hubco failing to achieve the Actual Completion Date within a period of [                    ] after the Completion Date;

Default

      - hubco committing a material breach of its obligations under this Agreement;

      - hubco (or an employee of hubco not acting independently of hubco) commits a Prohibited Act; or

      - a hubco Party (or anyone employed by or acting on behalf of them) commits a Prohibited Act and hubco has failed to comply with the requirements of the Authority specified in Clauses 34.3.2 to 34.3.5 (as the case may be);

    - hubco abandoning the Works (other than as a consequence of a breach by the Authority of its obligations under this Agreement).

Assignation

    - hubco failing to comply with the provisions of Clauses 43.2 or 43.4 (Assignation and Sub-contracting);

Payment

    - hubco failing to pay any sum or sums due to the Authority under this Agreement (which sums are not in dispute) which, either singly or in aggregate, exceed(s) £[                    ] (index linked) and such failure continues for sixty (60) Business Days from receipt by hubco of a notice of non payment from the Authority; or

- Insurance

    - a breach by hubco of its obligation to take out and maintain the insurances required by Clauses 39.1 and 39.2

Notification

  - hubco shall notify the Authority of the occurrence, and details, of any hubco Event of Default and of any event or circumstance which is likely, with the passage of time or otherwise, to constitute or give rise to a hubco Event of Default, in either case promptly on hubco becoming aware of its occurrence.

Authority's options

  - On the occurrence of a hubco Event of Default, or within a reasonable time after the Authority becomes aware of the same, and while the same is subsisting, the Authority may:-

    - in the case of the hubco Events of Default referred to in Clauses 32.1.1 (Insolvency), 32.1.2 (Long stop), ), 32.1.3(b) (Default) or 32.1.3(c) (Default)  32.1.5 (Assignation) or 32.1.6 (Payment) terminate this Agreement in its entirety by notice in writing having immediate effect;

    - in the case of any hubco Event of Default referred to in Clause 32.1.3(a) (Default) and 32.1.4, serve notice of default on hubco requiring hubco at hubco's option either:-

      - to remedy the hubco Event of Default referred to in such notice of default (if the same is continuing) within twenty (20) Business Days of such notice of default; or

      - to put forward within twenty (20) Business Days of such notice of default a reasonable programme (set out, if appropriate, in stages) for remedying the hubco Event of Default.  The programme shall specify in reasonable detail the manner in, and the latest date by, which such hubco Event of Default is proposed to be remedied (hubco shall only have the option of putting forward a programme in accordance with this Clause 32.(b) if it first notifies the Authority within ten (10) Business Days of such notice of default that it proposes to do so); and

    - in the case of any hubco Event of Default referred to in Clause 32.1.7 (Insurance), serve notice of default on hubco requiring hubco to remedy the hubco Event of Default (if the same is continuing) within twenty (20) Business Days of such notice of default

Remedy provisions

  - Where hubco puts forward a programme in accordance with Clause (b), the Authority shall have twenty (20) Business Days from receipt of the same within which to notify hubco (acting reasonably) that it does not accept the programme, failing which the Authority shall be deemed to have accepted the programme.  Where the Authority notifies hubco that it does not accept the programme as being reasonable, the parties shall endeavour within the following five (5) Business Days to agree any necessary amendments to the programme put forward.  In the absence of agreement within five (5) Business Days, the question of whether the programme (as the same may have been amended by agreement) will remedy the hubco Event of Default in a reasonable manner and within a reasonable time period (and, if not, what would be a reasonable programme) may be referred by either party for resolution in accordance with Schedule Part 15 (Dispute Resolution Procedure).

  - If:-

    - the hubco Event of Default notified in a notice of default served under Clause 32.3.2 or Clause 32.3.3 (as the case may be) is not remedied before the expiry of the period referred to in Clause (a) or Clause 32.3.3 (as appropriate); or

    - where hubco puts forward a programme pursuant to Clause (b) which has been accepted by the Authority or has been determined to be reasonable and hubco fails to achieve any element of the programme or the end date for the programme (as the case may be); or

    - any programme put forward by hubco pursuant to Clause (b) is rejected by the Authority as not being reasonable, and the Dispute Resolution Procedure does not find against that rejection,

then the Authority may terminate this Agreement in its entirety by written notice to hubco with immediate effect.  Provided that for the purposes of Clause 32.5.3 if hubco's performance of the programme is adversely affected by the occurrence of Force Majeure or a Relief Event then, subject to hubco complying with the mitigation and other requirements in this Agreement concerning Force Majeure or a Relief Event (as the case may be), the time for performance of the programme or any relevant element of it shall be deemed to be extended by a period equal to the delay caused by Force Majeure or the Relief Event (as the case may be) which is agreed by the parties or determined in accordance with Schedule Part 15 (Dispute Resolution Procedure).

Authority's costs

  - hubco shall reimburse the Authority for all reasonable costs incurred by the Authority in exercising any of its rights pursuant to this Clause 32 (hubco Event of Default) (including, without limitation, any relevant increased administrative expenses).  The Authority shall take reasonable steps to mitigate such costs.

  - The Authority shall not exercise, or purport to exercise, any right to terminate this Agreement except as expressly set out in this Agreement.  The rights of the Authority (to terminate or otherwise) under this Clause are in addition (and without prejudice) to any other right which the Authority may have to claim the amount of loss or damage suffered by the Authority on account of the acts or omissions of hubco (or to take any action other than termination of this Agreement).

- 33TERMINATION RESULTING FROM Force Majeure

If, in the circumstances referred to in Clause 24 (Force Majeure), the parties have failed to reach agreement on any modification to this Agreement pursuant to Clause 24 (Force Majeure) within six (6) calendar months of the date on which the party affected serves notice on the other party in accordance with Clause 24 (Force Majeure) either party may at any time afterwards terminate this Agreement by written notice to the other party having immediate effect provided always that the effects of the relevant event of Force Majeure continues to prevent either party from performing any material obligation under this Agreement.

- 34CORRUPT GIFTS AND PAYMENTS

Prohibition on corruption

  - The term "Prohibited Act" means:-

    - offering, giving or agreeing to give to the Authority or any other public body or to any person employed by or on behalf of the Authority or any other public body any gift or consideration of any kind as an inducement or reward:-

      - for doing or not doing (or for having done or not having done) any act in relation to the obtaining or performance of this Agreement or any other agreement with the Authority or any other public body; or

      - for showing or not showing favour or disfavour to any person in relation to this Agreement or any other agreement with the Authority or any other public body;

    - entering into this Agreement or any other agreement with the Authority or any other public body in connection with which commission has been paid or has been agreed to be paid by hubco or on its behalf, or to its knowledge, unless before the relevant agreement is entered into particulars of any such commission and of the terms and conditions of any such agreement for the payment of such commission have been disclosed in writing to the Authority;

    - committing any offence:-

      - under the Bribery Act 2010;

      - under any Law creating offences in respect of fraudulent acts; or

      - at common law, in respect of fraudulent acts in relation to this Agreement or any other agreement with the Authority or any other public body;

    - defrauding or attempting to defraud or conspiring to defraud the Authority or any other public body;

    - committing any breach of the Employment Relations Act 1999 (Blacklists) Regulations 2010 or section 137 of the Trade Union and Labour Relations (Consolidation) Act 1992;

    - committing any breach of the Data Protection Laws by unlawfully processing personal data in connection with any blacklisting activities; or

    - committing any offence under the Modern Slavery Act 2015.

Warranty

  - hubco warrants that in entering into this Agreement it has not committed any Prohibited Act.

Remedies

  - If hubco or any hubco Party (or anyone employed by or acting on behalf of them) commits any Prohibited Act, then the Authority shall be entitled to act in accordance with Clauses 34.3.1 to 34.3.6 below:-

    - if a Prohibited Act is committed by hubco or by an employee of hubco not acting independently of hubco, then the Authority may terminate this Agreement with immediate effect in accordance with Clause 32.1.3(b) and Clause 32.3.1 and, for the purposes of Clause 32.1.3(b) and Clause 34.3.1, all references to hubco shall not be deemed to include a hubco Party and the provisions of Clause 6.1 shall not apply;

    - if the Prohibited Act is committed by an employee of hubco acting independently of hubco, then the Authority may give written notice to hubco in accordance with Clause 34.3.6 below requiring that within twenty (20) Business Days of receipt of such notice hubco terminates the employee's employment;

    - if the Prohibited Act is committed by a Contracting Associate or by an employee of that Contracting Associate not acting independently of that Contracting Associate then the Authority may give written notice to hubco in accordance with Clause 34.3.6 below requiring that within twenty (20) Business Days of receipt of such notice hubco terminates the relevant Sub-Contract;

    - if the Prohibited Act is committed by an employee of a Contracting Associate acting independently of that Contracting Associate, then the Authority may give notice to hubco in accordance with Clause 34.3.6 below requiring that within twenty (20) Business Days of receipt of such notice hubco procures the termination of the employee's employment;

    - if the Prohibited Act is committed by any other person not specified in Clauses 34.3.1 to 34.3.4 above, then the Authority may give notice to hubco in accordance with Clause 34.3.6 below requiring that within twenty (20) Business Days of receipt of such notice hubco procures the termination of such person's employment and of the appointment of their employer (where the employer is not the Authority and where such person is not employed by hubco or the Contracting Associate); and

    - any notice under this Clause shall specify:-

      - the nature of the Prohibited Act; and

      - the identity of the party who the Authority believes has committed the Prohibited Act.

  - Without prejudice to its other rights or remedies under this Clause, the Authority shall be entitled to recover from hubco:-

    - the amount or value of any such gift, consideration or commission; and

    - any other loss sustained in consequence of any breach of this Clause.

  - On termination of hubco's employment under this Agreement in accordance with Clause 34.3, the Authority shall pay hubco in accordance with the provisions of Clause 35.5 (Payments following termination upon hubco Default).

Permitted payments

  - Nothing contained in this Clause shall prevent hubco from paying any proper commission or bonus to its employees within the agreed terms of their employment.

Notification

  - hubco shall notify the Authority of the occurrence (and details) of any Prohibited Act promptly on hubco becoming aware of its occurrence.

- 35CONSEQUENCES OF TERMINATION

Continued performance

  - Subject to any exercise by the Authority of its rights to perform, or to procure a third party to perform, the obligations of hubco, the parties shall continue to perform their obligations under this Agreement, notwithstanding the giving of any notice of default or notice of termination, until the Termination Date.

Transfer to Authority of Assets, Contracts etc.

  - On the service of a notice of termination in accordance with this Agreement for any reason:-

    - in so far as any transfer shall be necessary fully and effectively to transfer property to the Authority, hubco shall transfer to, and there shall vest in, the Authority, such part of the Works and/or the Facilities as shall have been constructed and such items of the Plant and [Authority to add other project specific items] as shall have been procured by hubco if the Authority so elects;

    - all goods and all materials on or near to the Site not yet incorporated in the Works shall remain available to the Authority for the purposes of completing the Works and if the cost of such goods and materials has not been reflected in payments made by the Authority to hubco prior to the service of a notice of termination subject to the payment by the Authority (determined as between a willing vendor and willing purchaser with any disputes determined pursuant to Clause 42 (Dispute Resolution Procedure));

    - the construction plant shall remain available to the Authority for the purposes of completing the Works, subject to payment of the Contractor's reasonable charges;

    - if the Authority so elects, hubco shall procure that any of the Construction Contract shall be novated or assigned to the Authority, provided that where termination occurs under Clause 31 (Authority Events of Default) the consent of the Contractor shall be required;

    - hubco shall deliver to the Authority (as far as not already delivered to the Authority) one complete set of:

      - "as built drawings" showing all alterations made to the Facilities since the commencement of operation of the Facilities; and

      - maintenance, operation and training manuals and BIM Modelling Data for the Facilities;

    - hubco shall use all reasonable endeavours to procure that the benefit of all manufacturer's warranties in respect of mechanical and electrical plant and equipment used or made available by hubco under this Agreement and included in the Facilities are assigned, or otherwise transferred, to the Authority with full title guarantee; and

    - hubco shall ensure that provision is made in all contracts of any description whatsoever to ensure that the Authority will be in a position to exercise its rights, and hubco will be in a position to comply with its obligations, under this Clause 35.2.

Transitional arrangements

  - On the termination of this Agreement for any reason, for a reasonable period both before and after any such termination, hubco shall have the following duties:

    - hubco shall as soon as practicable remove from the Site all property not acquired by the Authority pursuant to Clause 35.2 (or not belonging to the Authority or any Authority Party) and if it has not done so within forty (40) Business Days after any notice from the Authority requiring it to do so the Authority may (without being responsible for any loss, damage, costs or expenses) remove and sell any such property and shall hold any proceeds less all costs incurred to the credit of hubco;

    - hubco shall forthwith deliver to the Authority's Representative:

      - any security passwords, access codes and other keys to the Facilities and the Equipment; and

      - without prejudice to Clause 41 (Intellectual Property), any copyright licences for any computer programmes (or licences to use the same) necessary for the operation of the Facilities (but excluding computer programmes; and

    - hubco shall as soon as practicable vacate the Site and shall leave the Site and the Facilities in a safe, clean and orderly condition.

Continuing Obligations

  - Save as otherwise expressly provided in this Agreement:

    - termination of this Agreement shall be without prejudice to any accrued rights and obligations under this Agreement as at the date of termination; and

    - termination of this Agreement shall not affect the continuing rights and obligations of hubco and the Authority under Clauses 24 (Force Majeure), 27 (Payment), 30 (Records and Open Book Accounting), 34 (Corrupt Gifts), 35.2 (Transfer to Authority of Assets, Contracts etc), 35.3 (Transitional Arrangements), 35.5 (Payments following termination upon hubco Default), 35.6 (Payments following termination upon Authority Default), 35.8 (Payments under Clauses 35.5, 35.6 and 35.7 to be exhaustive), 36 (Indemnities), 37 (Taxation), 39 (Insurance), 40 (Exclusions and Limits on Liability), 41 (Intellectual Property), 42 (Dispute Resolution Procedure), 44 (Mitigation), 46 (Confidentiality), 49 (Notices), and Clause 57 (Governing Law and Jurisdiction) or under any other provision of this Agreement which is expressed to survive termination or which is required to give effect to such termination or the consequences of such termination.

Payments following termination upon hubco Default

  - If the Authority terminates hubco's employment under this Agreement in accordance with Clause 32 (hubco Default) or Clause 34 (Corrupt Gifts);

    - hubco shall indemnify the Authority and keep the Authority fully indemnified against all reasonable expense, loss, damage and liabilities suffered or incurred by the Authority associated with or arising from the termination including any additional expense (above the amount that would reasonably have been paid to hubco had its employment not been terminated) incurred by the Authority in completing the Works (if applicable) including the cost of finding an alternative contractor or contractors and any additional amounts charged by them for completing the Works;

    - hubco shall be entitled to be paid the total value of work properly executed at, and of any design work properly carried out in relation to the hubco Designed Portion before, the Termination Date, ascertained in accordance with this Agreement, together with any other amounts due to hubco under this Agreement less any amounts previously paid to hubco under this Agreement; and

    - no payment shall be made to hubco in respect of Clause 35.5.2 until such time as the Works are complete.

Payments following termination upon Authority Default

  - If this Agreement is terminated pursuant to Clause 31 (Authority Events of Default) hubco shall be entitled to be paid:

    - the total value of the Works properly executed at, and of any design work properly carried out  in relation to the hubco Designed Portion before, the Termination Date, ascertained in accordance with this Agreement under deduction of all amounts certified for payment in Interim Certificates previously issued under Clause 27.5;

    - the reasonable cost of removal of hubco's property from the Site;

    - any Direct Losses caused to hubco by the termination; and

    - to the extent not already included in the amount calculated in accordance with Clause 35.6.1, the cost of materials or goods properly ordered for the Works for which hubco shall have paid or for which hubco is legally bound to pay, and on such payment in full by the Authority such materials or goods shall become the property of the Authority provided always that hubco arranges for any such goods or materials to be delivered to the Site.

Payments following termination upon Force Majeure

  - If this agreement is terminated pursuant to Clause 33 (Termination resulting from Force Majeure), hubco shall be entitled to be paid:

    - the total value of the Works properly executed at, and of any design work properly carried out in relation to the hubco Designed Portion before, the Termination Date, ascertained in accordance with this Agreement under deduction of all amounts certified for payment in Interim Certificates previously issued under Clause 27.5; and

    - to the extent not already included in the amount calculated in accordance with Clause 35.7.1, the cost of materials or goods properly ordered for the Works for which hubco shall have paid or for which hubco is legally bound to pay, and on such payment in full by the Authority such materials or goods shall become the property of the Authority provided always that hubco arranges for any such goods or materials to be delivered to the Site.

Payments under Clauses 35.5, 35.6 and 35.7 to be exhaustive

  - Without prejudice to Clause 35.4.1, the making of those payments following a termination which are required to be made by Clauses 35.5 (Payments following termination upon hubco Default), 35.6 (Payments following termination upon Authority Default) and 35.7 (Payments following termination upon Force Majeure) shall be in full satisfaction of any claim in respect of the termination of, and the circumstances leading to, the termination of this Agreement or hubco's employment under this Agreement and neither hubco nor the Authority shall be entitled to any other rights or remedies in that regard.

- PART 10: INDEMNITIES, WARRANTIES & INSURANCE

- 36INDEMNITIES

hubco indemnities to Authority

  - hubco shall indemnify and keep the Authority indemnified at all times from and against all Direct Losses sustained by the Authority in consequence of:

    - any claim for, or in respect of, the death and/or personal injury of any employee of, or person engaged by, hubco or any hubco Party notwithstanding any act or omission of the Authority or any Authority Party;

    - any claim for, or in respect of, the death and/or personal injury of any third party (other than a person referred to in Clause 36.2.1 (Authority Party employees)) arising out of, or in the course of, the Works, save to the extent caused (or contributed to) by the Authority or any Authority Party, breach of any express provision of this Agreement by the Authority or any Authority Party or any deliberate or negligent act or omission of the Authority or any Authority Party;

    - any physical loss of or damage to Authority Assets arising by reason of any act or omission of hubco or any hubco Party, save to the extent that such loss or damage arises out of the breach of any express provision of this Agreement by the Authority or any Authority Party or any deliberate or negligent act or omission of the Authority or any Authority Party; and

    - any loss of or damage to property or assets of any third party arising by reason of any act or omission of hubco or any hubco Party, save to the extent that such loss or damage arises out of the breach of any express provision of this Agreement by the Authority or any Authority Party or any deliberate or negligent act or omission of the Authority or any Authority Party.

Authority indemnities to hubco

  - The Authority shall indemnify and keep hubco indemnified at all times from and against all Direct Losses sustained by hubco in consequence of:

    - any claim for, or in respect of, the death and/or personal injury of any employee of, or person engaged by, the Authority or any Authority Party notwithstanding any act or omission of hubco or any hubco Party;

    - any claim for, or in respect of, the death and/or personal injury of any third party (other than a person referred to in Clause 36.1.1) arising by reason of any act or omission of the Authority or any Authority Party in the course of the provision of the Community Services, any Unreasonable Act by the Authority or any Authority Party, breach of any express provision of this Agreement by the Authority or any Authority Party or any deliberate act or omission of the Authority or any Authority Party, save to the extent caused (or contributed to) by any act or omission of hubco or any hubco Party;

    - any physical damage to any part of the Works or any assets or other property of hubco or any hubco Party arising by reason of any breach of any express provision of this Agreement by the Authority or any Authority Party or any deliberate act or omission of the Authority or any Authority Party, save to the extent caused (or contributed to) by any act or omission of hubco or any hubco Party; and

    - any loss of or damage to property or assets of any third party arising by reason of any breach of any express provision of this Agreement by the Authority or any Authority Party or any deliberate act or omission of the Authority or any Authority Party, save to the extent caused (or contributed to) by any act or omission of hubco or any hubco Party.

provided that in the case of Clauses 36.2.3 and 36.2.4 there shall be excluded from the indemnity given by the Authority any liability:-

(a)	for the occurrence of risks against which and to the extent to which hubco is obliged to insure under this Agreement (but for the avoidance of doubt, not such liability to the extent within any applicable excess or deductible or over the maximum amount insured or to be insured under such insurance); or

(b)	in respect of a matter which is a Compensation Event.

Conduct of claims

  - This Clause 36.3 (Conduct of Claims) shall apply to the conduct, by a party from whom an indemnity is sought under this Agreement, of claims made by a third person against a party having (or claiming to have) the benefit of the indemnity.  The party having, or claiming to have, the benefit of the indemnity is referred to as the "Beneficiary" and the party giving the indemnity is referred to as the "Indemnifier".  Accordingly:

    - if the Beneficiary receives any notice, demand, letter or other document concerning any claim for which it appears that the Beneficiary is, or may become, entitled to indemnification under this Agreement, the Beneficiary shall give notice in writing to the Indemnifier as soon as reasonably practicable and in any event within twenty (20) Business Days of receipt of the same;

    - subject to Clauses 36.3.3, 36.3.4 and 36.3.5 below, on the giving of a notice by the Beneficiary pursuant to Clause 36.3.1 above, where it appears that the Beneficiary is or may be entitled to indemnification from the Indemnifier in respect of all (but not part only) of the liability arising out of the claim, the Indemnifier shall (subject to providing the Beneficiary with an indemnity to its reasonable satisfaction against all costs and expenses that it may incur by reason of such action) be entitled to dispute the claim in the name of the Beneficiary at the Indemnifier's own expense and take conduct of any defence, dispute, compromise, or appeal of the claim and of any incidental negotiations.  The Beneficiary shall give the Indemnifier all reasonable co-operation, access and assistance for the purposes of considering and resisting such claim;

    - with respect to any claim conducted by the Indemnifier pursuant to Clause 36.3.2 above:

      - the Indemnifier shall keep the Beneficiary fully informed and consult with it about material elements of the conduct of the claim;

      - the Indemnifier shall not bring the name of the Beneficiary into disrepute; and

      - the Indemnifier shall not pay or settle such claims without the prior consent of the Beneficiary, such consent not to be unreasonably withheld or delayed;

    - the Beneficiary shall be free to pay or settle any claim on such terms as it thinks fit and without prejudice to its rights and remedies under this Agreement if:

      - the Indemnifier is not entitled to take conduct of the claim in accordance with Clause 36.3.3 above; or

      - the Indemnifier fails to notify the Beneficiary of its intention to take conduct of the relevant claim within twenty (20) Business Days of the notice from the Beneficiary under Clause 36.3.3 above or notifies the Beneficiary that it does not intend to take conduct of the claim; or

      - the Indemnifier fails to comply in any material respect with the provisions of Clause 36.3.3 above;

    - the Beneficiary shall be free at any time to give notice to the Indemnifier that it is retaining or taking over (as the case may be) the conduct of any defence, dispute, compromise or appeal of any claim (or of any incidental negotiations) to which Clause 36.3.3 above applies.  On receipt of such notice the Indemnifier shall promptly take all steps necessary to transfer the conduct of such claim to the Beneficiary, and shall provide to the Beneficiary all reasonable co-operation, access and assistance for the purposes of considering and resisting such claim.  If the Beneficiary gives any notice pursuant to this Clause 36.3.5 then the Indemnifier shall be released from any liability under its indemnity under Clause 36.1 (hubco Indemnities to Authority) or Clause 36.2 (Authority Indemnities to hubco) (as the case may be) and, without prejudice to any accrued liabilities, any liability under its indemnity given pursuant to Clause 36.3.3 in respect of such claim;

    - if the Indemnifier pays to the Beneficiary an amount in respect of an indemnity and the Beneficiary subsequently recovers (whether by payment, discount, credit, saving, relief or other benefit or otherwise) a sum which is directly referable to the fact, matter, event or circumstances giving rise to the claim under the indemnity, the Beneficiary shall forthwith repay to the Indemnifier whichever is the lesser of:-

      - an amount equal to the sum recovered (or the value of the saving or benefit obtained) less any out-of-pocket costs and expenses properly incurred by the Beneficiary in recovering the same; and

      - the amount paid to the Beneficiary by the Indemnifier in respect of the claim under the relevant indemnity,

- provided that:

        - there shall be no obligation on the Beneficiary to pursue such recovery and that the Indemnifier is repaid only to the extent that the amount of such recovery aggregated with any sum recovered from the Indemnifier exceeds any loss sustained by the Beneficiary (including for this purpose indirect or consequential losses or claims for loss of profits which are excluded by this Agreement from being recovered from the Indemnifier); and

        - any person taking any of the steps contemplated by Clauses 36.1 to 36.3.5 shall comply with the requirements of any insurer who may have an obligation to provide an indemnity in respect of any liability arising under this Agreement.

Mitigation – indemnity claims

  - To avoid doubt the provisions of Clause 44 (Mitigation) apply to any indemnity given under this Agreement and any such indemnity shall not apply to the extent that such part or parts of Direct Losses could have been reduced or avoided by the Beneficiary complying with the provisions of such Clause 44 (Mitigation).

- 37TAX on INDEMNITY payments

If any payment by one party under an indemnity in this Agreement is subject to corporation tax (or any tax replacing it) in the hands of the recipient, the recipient may demand in writing to the party making the payment that the payment shall be increased by such amount as would ensure that, after taking into account any such tax payable in respect of such additional amount, the recipient receives and retains a net sum equal to the amount it would have otherwise received had the payment not been subject to such tax.  The party making the payment shall pay such additional amount within ten (10) Business Days of receipt of such demand.

- 38WARRANTIES

  - [TO BE COMPLETED]

- 39INSURANCE

hubco Insurances

  - hubco shall, at its own cost, take out the Insurances, details of which are set out in Section 1 of Schedule Part 12 (Insurance Requirements), prior to the commencement of the Works and maintain for the periods specified in Section 1 of Schedule Part 12 (Insurance Requirements).

  - Without prejudice to the other provisions of this Clause 39 (Insurance) hubco shall, at all relevant times, at its own cost, effect and maintain in full force any insurances which it is required to effect by any applicable Law.  [In addition, hubco shall discharge all its obligations under the Insurance Act 2015 when placing, renewing, maintaining or amending any of the Insurances referred to in Clauses 39.1 and 39.2, including complying with the duty of fair presentation to insurers, and taking the actions needed to protect the Authority’s separate interests where appropriate.]

  - All Insurances referred to in Clause 39.1 shall:-

    - be maintained in the names of the parties specified in Schedule Part 12 (Insurance Requirements) and shall be composite policies of insurance (and not joint) unless stated otherwise in Schedule Part 12 (Insurance Requirements));

    - be placed with insurers who are acceptable to the Authority (such acceptance not to be unreasonably withheld or delayed);

    - in so far as they relate to damage to assets (including the Facilities), cover the same for the full reinstatement value;

    - comply with the relevant provisions of Section 1 of Schedule Part 12 (Insurance Requirements); and

    - provide for 30 days prior written notice of their cancellation, non–renewal or amendment to be given to the Authority in accordance with Endorsement 1 in Section 3 (Endorsements) of Schedule Part 12 (Insurance Requirements).

  - hubco shall ensure that its brokers give the Authority a letter of undertaking in the form set out in Section 4 (Broker’s Letter of Undertaking) of Schedule Part 12 (Insurance Requirements) at Financial Close.

Subrogation and Vitiation

  - hubco shall:-

    - [procure that all policies of insurance to be effected by it pursuant to this Clause shall contain a provision to the effect that the insurers have agreed to waive all rights of subrogation against the Authority (and all Authority Parties) in accordance with Endorsement 2 in Section 3 (Endorsements) of Schedule Part 12 (Insurance Requirements) ]; and

    - [provide for non-vitiation protection in respect of any claim made by the Authority as co-insured in accordance with Endorsement [2] in Section 3 (Endorsements) of Schedule Part 12 (Insurance Requirements);]

provided that, to avoid doubt, this Clause 39.5 shall not by itself prevent hubco from claiming against the Authority (or any Authority Party) under an express provision of this Agreement for any loss or damage not covered because of the level of deductibles under such insurance permitted by this Agreement or to the extent such loss or damage exceeds the maximum of such insurance required by this Agreement.

  - Neither party shall take any action or fail to take any reasonable action or (in so far as it is reasonably within its power) permit or allow others to take or fail to take any action (including failure to disclose any fact) as a result of which any of the Insurances may be rendered void, voidable, unenforceable or suspended or impaired in whole or in part or which may otherwise render any sum paid out under any relevant policy repayable in whole or in part.

Evidence of hubco Insurance

  - Not less than thirty (30) Business Days prior to the amendment or expiry of any relevant insurance policy, hubco shall submit to the Authority a request for approval from the Authority of the insurer and the principal terms and conditions of such insurance policy (and any revision to such terms and conditions or change in identity of such insurer), such approval not to be unreasonably withheld or delayed.

  - hubco shall provide to the Authority:-

    - copies on request of all insurance policies referred to in Clauses 39.1 to 39.3 (together with any other information reasonably requested by the Authority relating to such insurance policies) and the Authority shall be entitled to inspect them during ordinary business hours; and

    - evidence that the premiums payable under all insurance policies have been paid and that the Insurances are in full force and effect in accordance with the requirements of this Clause 39 (Insurance) and Schedule Part 12 (Insurance Requirements).

  - Renewal certificates in relation to the Insurances shall be obtained as and when necessary and copies (certified in a manner acceptable to the Authority) shall be forwarded to the Authority as soon as possible but in any event within 20 Business Days of the renewal date.

  - If hubco defaults in insuring or continuing to maintain the Insurances, the Authority may insure against any risk in respect of which such default has occurred and recover any premiums from hubco as a debt.

Acceptance and compliance

  - The supply to the Authority of any draft insurance policy or certificate of insurance or other evidence of compliance with this Clause 39 shall not imply acceptance by the Authority (or the Authority's Representative) that the extent of insurance cover is sufficient and its terms are satisfactory.

  - Neither failure to comply nor full compliance with the insurance provisions of this Agreement shall relieve hubco of its liabilities and obligations under this Agreement.

Risk Management

  - With effect from the date of this Agreement, the Authority and hubco shall each designate or appoint an insurance and risk manager and notify details of the same to the other party.  Such person shall:-

    - be responsible for dealing with all risk management matters on behalf of its appointing or designating party including (without limitation) ensuring compliance by that party with this Clause 39.13.1;

    - advise and report to that party on such matters; and

    - ensure that any report or survey conducted by any insurer of any relevant procedures in relation to the Project is disclosed to the parties.

  - Without prejudice to the provisions of Clause 39.13, the parties shall notify one another, and in hubco's case the relevant insurer, of any circumstances which may give rise to a claim of a value equal to or in excess of [                    ] pounds (£[        ]) (index-linked) under the Insurances within [           ] Business Days of becoming aware of the same (or earlier, if so requested by the terms of the relevant insurance policy).  If any insurer disputes any such claim, hubco shall provide the Authority with full details of any disputed claim and the parties shall liaise with one another to ensure that the relevant claim is preserved or pursued.

Application of Proceeds

  - All insurance proceeds received by hubco under the Insurances referred to in  Section 1 of Schedule Part 12 (Insurance Requirements) shall be paid into the Insurance Proceeds Account and shall be applied in accordance with this Agreement.

  - hubco shall apply any proceeds of any policies of Insurance:-

    - in the case of third party legal liability or employers' liability insurance, in satisfaction of the claim, demand, proceeding or liability in respect of which such proceeds are payable; and

    - in the case of any other insurance, so as to ensure the performance by hubco of its obligations under this Agreement, including where necessary the reinstatement, restoration or replacement of the facilities, assets, materials or goods affected by the event giving rise to the insurance claim and consequent payment of proceeds.

  - Where reinstatement monies are required to be released from the Insurance Proceeds Account hubco shall obtain the Authority's consent.  The Authority shall give its consent (or confirm that it is withholding its consent) to the release of monies from the Insurance Proceeds Account within one (1) Business Day of a request from hubco (provided that such consent must not be unreasonably withheld).

  - Subject to Clause 36, if the proceeds of any insurance claim are insufficient to cover the settlement of such claims, hubco will make good any deficiency forthwith.

Reinstatement

  - [Without prejudice to Clause 36 (Indemnities) hubco shall be responsible for repairing, rectifying and/or reinstating all damage caused to the Facilities by hubco or a hubco Party in the conduct of the Project Operations after the Actual Completion Date.]

  - Where a claim is made or proceeds of insurance are received or are receivable under any Physical Damage Policy in respect of a single event (or a series of related events) (the "Relevant Incident") in an amount in excess of £[		] ([indexed]):

    - hubco shall deliver to the Authority as soon as practicable (and in any event within twenty (20) Business Days after the making of the claim) a plan prepared by hubco for the carrying out of the works necessary (the "Reinstatement Works") to repair, reinstate or replace (the "Reinstatement Outline") the relevant Works which is or are the subject of the relevant claim or claims in accordance with Clause 39.21 (Works carried out).  The Reinstatement Outline shall set out:

      - the identity of the person proposed to effect the Reinstatement Works, which (if not hubco or a hubco Party) shall be subject to the prior written approval of the Authority; and

      - the proposed terms and timetable or, if not then established, the reasonably anticipated terms and timetable upon which the Reinstatement Works are to be effected (including the date by which the Reinstatement Works will be completed), the final terms of which shall be subject to the prior written approval of the Authority (such approval not to be unreasonably withheld or delayed);

    - the Authority shall within ten (10) Business Days of receipt of the Reinstatement Outline notify hubco in writing that:

      - it is satisfied that the Reinstatement Outline will enable hubco to comply with its obligations to carry out the Reinstatement Works within a reasonable timetable, and (if not hubco or a hubco Party) that the identity of any person (set out in the Reinstatement Outline) that may be appointed to effect the Reinstatement Works is approved;

      - the identity of any person (set out in the Reinstatement Outline) that may be appointed to effect the Reinstatement Works (if not hubco or a hubco Party) is not approved together with its reasons for such non-approval in sufficient detail to enable hubco to understand the nature and extent of such non-approval and to assess whether the Authority’s approval under Clause (b) has been unreasonably withheld;

      - it does not approve the Reinstatement Outline together with its reasons for such non-approval, in sufficient detail so as to enable hubco to understand the nature and extent of such non-approval and to assess whether the Authority’s approval under Clause (b) has been unreasonably withheld; or

      - if the Authority does not make one of the above responses within the period specified in Clause 39.20.2, it shall be deemed to have approved the Reinstatement Outline, save where the Authority has reasonably requested any further information from hubco, in which case the time limit outlined in Clause 39.20.2 will be deemed to commence upon receipt of such information by the Authority;

    - if the Authority gives notice of non-approval in accordance with Clauses (b) or (c), hubco may amend and re-submit the Reinstatement Outline (the "Amended Reinstatement Outline") to the Authority for its reconsideration and the Authority shall give its approval or non-approval within five (5) Business Days of the submission of the Amended Reinstatement Outline to the Authority.  If the Authority does not approve the Amended Reinstatement Outline, it shall provide reasons for such non-approval in sufficient detail so as to enable hubco to understand the nature and extent of such non-approval and to assess whether the Authority’s approval has been unreasonably withheld;

    - if the Amended Reinstatement Outline or a person proposed to carry out the Reinstatement Works is not approved by the Authority in accordance with Clause 39.20.3, hubco may submit the Amended Reinstatement Outline to the Dispute Resolution Procedure in order for it to be determined whether the Authority’s approval under Clause 39.20.3 was unreasonably withheld;

    - the Reinstatement Outline or the Amended Reinstatement Outline (as the case may be) as approved by the Authority pursuant to this Clause 39.20 or as determined pursuant to the Dispute Resolution Procedure shall become the Reinstatement Plan;

    - hubco shall effect the Reinstatement Works in accordance with the Reinstatement Plan, and:

      - hubco shall enter into contractual arrangements to effect the Reinstatement Works with the person(s) identified in the Reinstatement Plan;

      - the insurance proceeds received under any Physical Damage Policy in respect of the Relevant Incident (together with any interest accrued) may be applied by hubco as required to enable it to make payments in accordance with the terms of the contractual arrangements entered into to effect the Reinstatement Works and to meet any other reasonable costs and expenses of hubco for the sole purposes of financing the Reinstatement Works;

      - the Authority agrees and undertakes that, subject to compliance by hubco with its obligations under this Clause 39.20, and provided that hubco procures that the Reinstatement Works are carried out and completed in accordance with this Clause 39.20, the Authority shall not exercise any right which it might otherwise have to terminate this Agreement by virtue of the event which gave rise to the claim under the Physical Damages Policy;

      - the Authority undertakes to use all reasonable endeavours to assist hubco in the carrying out of the Reinstatement Plan; and

      - subject to Clause 36 (Indemnities), hubco shall be solely responsible for the payment of any deficiency between the insurance proceeds and the cost of carrying out the Reinstatement Works.

Works carried out

  - Where insurance proceeds are to be used in accordance with this Agreement to repair, reinstate or replace the whole or any part of the Works or Facility, hubco shall carry out the work in accordance with the Authority’s Construction Requirements so that on completion of the work the provisions of this Agreement are complied with.

Contractor's Insurance

  - Where the Works include a hubco Designed Portion, hubco shall procure that the Contractor at its own cost takes out, or procures the taking out of, professional indemnity insurance with reputable insurers carrying on business in the European Union with a limit of indemnity of not less than £[ ],000,000 ([  ] million pounds) [on an each and every claim basis][in the annual aggregate] with at least one annual reinstatement, in relation to the hubco Designed Portion, provided always that:

    - such insurance shall be in place from the commencement of the Works until no less than twelve (12) years after the Actual Completion Date or, if earlier, after the date of termination of the Construction Contract;

    - the insurance premiums in respect of the insurance shall, as between the Authority and hubco at all times be the responsibility of hubco;

    - if such insurance is not available to the Contractor (and/or contractors engaged in projects of a similar scope, size, nature and complexity as the Contractor) at commercially reasonable rates and terms (excluding any increase in premiums attributable to the actions, omissions, errors or defaults of the Contractor), the Contractor, hubco and the Authority will meet and the Contractor will outline the steps it intends to take to manage such risks.  If the steps proposed by the Contractor are not acceptable to the Authority (acting reasonably), the Contractor, hubco and the Authority shall agree an alternative method of managing such risk.

  - hubco will procure that the Contractor will, upon request, provide the Authority with reasonable evidence that the policy referred to in Clause 39.22 is in full force and effect in accordance with the requirements of Clause 39.22.

- 40Exclusions and limitations on liability

Exclusions

  - The indemnities under this Agreement shall not apply and there shall be no right to claim damages for breach of this Agreement, in delict or on any other basis whatsoever to the extent that any loss claimed by either party is for loss of profits, loss of use, loss of production, loss of business or loss of business opportunity or is a claim for consequential loss or for indirect loss of any nature ("Indirect Losses") suffered or allegedly suffered by either party.  The Authority agrees that, notwithstanding the foregoing, any losses of hubco arising under the Construction Contract as originally executed (or as amended in accordance with and subject to Clause 4.1 (Project Documents)) which are not Indirect Losses shall not be excluded from such a claim solely by reason of this Clause.

  - The Authority shall not be liable in delict to hubco or any hubco Party in respect of any negligent act or omission of the Authority or any Authority Party relating to or in connection with this Agreement and hubco shall procure that no hubco Party shall bring such a claim against the Authority.  hubco has accepted this on the basis that it and each hubco Party will cover the risk of negligent acts or omissions by insurance or in such other manner as it (or they) may think fit.

  - Nothing in Clause 40.1 shall exclude any right of the Authority to seek damages from hubco for breach of contract in respect of any losses it incurs as a direct result of the loss of use of all or any part of the Facilities arising out of any Defect.

No Double Recovery

  - Notwithstanding any other provision of this Agreement, neither party shall be entitled to recover compensation or make a claim under this Agreement or any other agreement in relation to the Project in respect of any loss that it has incurred (or any failure of the other party) to the extent that it has already been compensated in respect of that loss or failure pursuant to this Agreement or otherwise.

  - Subject to Clause 31 (Authority Events of Default) and any other express right of hubco pursuant to this Agreement, hubco's sole remedy in respect of any breach of this Agreement which is a Compensation Event shall be pursuant to Clause 22 (Delay Events).

  - Neither party shall have the right to terminate this Agreement for breach of contract save as expressly set out in this Agreement.

Limitation on Liability

  - [Subject to Clause 40.8, but notwithstanding any other provision of this Agreement the maximum aggregate liability of hubco to the Authority pursuant to and arising out of this Agreement shall not exceed the Liability Cap.]

  - [The limitation of hubco's liability under Clause 40.7 shall not apply to:

    - any liability in relation to death or personal injury; or

    - any liability where such is caused or contributed to by:

      - the wilful default of hubco and/or any hubco Party or abandonment by hubco and/or any hubco Party;

      - fraud of hubco and/or any hubco Party;

    - any liability, where and to the extent that hubco makes recovery from any other third party or from insurances maintained by either party pursuant to Clause 39 (Insurance) in respect of such liability or where hubco would have made recovery:

      - had the relevant third party or insurer met its obligations under the relevant agreement or policy; or

      - had hubco complied with its obligations under this Agreement and/or the terms of any applicable insurance policy; or

      - had hubco diligently pursued such recovery; or

      - had hubco or a hubco Party, through its acts or omissions, not caused the relevant insurance policy to become void, voidable, unenforceable, suspended or impaired,

and excluding in each case any non-recovery to the extent such non-recovery has occurred as a direct result of the act, omission, breach or negligence of the Authority (to the extent such breach or negligence was not caused by the act or omission of hubco or a hubco Party);

    - any liability of hubco arising under paragraph 6.3 of Schedule Part 15 (Dispute Resolution Procedure) or in respect of any indemnity arising out of breach of Law by hubco or a hubco Party.]

  - hubco's liability under this Agreement shall

    - end on the date falling twelve (12) years after the Actual Completion Date; or

    - if, earlier, end on the date falling twelve (12) years after the Termination Date,

save, in each case, in respect of claims which have been made prior to such date and in respect of which actions or proceedings have been commenced within six months of such date.

PART 11: MISCELLANEOUS

- 41INTELLECTUAL PROPERTY

Project Data

  - Each party shall make available to the other party free of charge (and hereby irrevocably licences the other party to use) all Project Data (for which it is responsible) that might reasonably be required by the other party and each party shall ensure that it obtains all necessary licences, permissions and consents to ensure that it can make the Project Data available to the other party on these terms, for such purposes as the other party at its sole discretion may require, and in this Clause "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the granting of sub-licences and the term "the right to use" shall be construed accordingly.  Neither party nor any hubco Party or Authority Party shall be liable to the other party in respect of use by or on behalf of the first party of the Project Data other than in relation to the Project.  The licence given in this Clause 41.1 shall carry the right to grant sub-licences.

Intellectual Property Rights

  - Each party:-

    - grants to the other party, free of charge, an irrevocable, non-exclusive and transferable (but only to any assignee or transferee of any rights or benefits under this Agreement or upon or at any time following termination of this Agreement) licence (carrying the right to grant sub-licences) to use the Intellectual Property Rights which are or become vested in the first party; and

    - shall, where any Intellectual Property Rights (for which it is responsible) are or become vested in a third party, use all reasonable endeavours to procure the grant of a like licence to that referred to in Clause 41.2.1 above to the other party,

in both cases, for such purposes as the other party may at its sole discretion require.

Each party shall use all reasonable endeavours to ensure that any Intellectual Property Rights (for which it is responsible) created, brought into existence or acquired during the term of this Agreement vest, and remain vested throughout the term of this Agreement, in it and each party shall enter into appropriate agreements with any hubco Party or Authority Party (as applicable) (or other third parties) that may create or bring into existence, or from which it may acquire, any Intellectual Property Rights.

Maintenance of data

  - To the extent that any of the data, materials and documents referred to in this Clause are generated by or maintained on a computer or similar system, each party shall use all reasonable endeavours to procure for the benefit of the other party, at no charge or at the lowest reasonable fee, the grant of a licence or sub-licence for any relevant software to enable the other party or its nominee to access and otherwise use (subject to the payment by the other party of the relevant fee, if any) such data (for which the relevant party is responsible) for such purposes as the other party may at its sole discretion require.  As an alternative, each party may provide such data, materials or documents in a format which may be read by software generally available in the market at the relevant time or in hard copy format.

  - Each party shall ensure the back-up and storage in safe custody of the data, materials and documents referred to in Clause 41.3 for which it is responsible in accordance with Good Industry Practice.  Without prejudice to this obligation, each party shall submit to the Authority's Representative or hubco’s Representative (as applicable) for approval its proposals for the back-up and storage in safe custody of such data, materials and documents and the other party shall be entitled to object if the same is not in accordance with Good Industry Practice.  Each party shall comply, and shall cause all hubco Parties or Authority Parties (as applicable) to comply, with all procedures to which the Authority's Representative or hubco’s Representative (as applicable) has given its approval.  Each party may vary its procedures for such back-up and storage subject to submitting its proposals for change to the Authority's Representative or hubco’s Representative (as applicable) who shall be entitled to object on the basis set out above.

Claims

  - Where a claim or proceeding is made or brought against a party which arises out of the infringement of any rights in or to any Intellectual Property (as a consequence of the use of Project Data for which the other party is responsible) or because the use of any materials, Plant, machinery or Equipment (specified by the other party) in connection with the Works infringes any rights in or to any Intellectual Property of a third party then, unless such infringement has arisen out of the use of any Intellectual Property by or on behalf of the party suffering the claim or proceeding otherwise than in accordance with the terms of this Agreement [or in respect of a use of the Intellectual Property for a purpose  other than that for which it was produced], the other party shall indemnify the party suffering the claim or proceeding at all times from and against all such claims and proceedings and the provisions of Clause 36.3 (Conduct of Claims) shall apply.

- 42DISPUTE RESOLUTION PROCEDURE

  - Except where expressly provided otherwise in this Agreement, any dispute arising out of or in connection with this Agreement shall be resolved in accordance with the procedure set out in Schedule Part 15 (Dispute Resolution Procedure).

- 43ASSIGNATION AND SUBCONTRACTING

Assignation

  - This Agreement and any other agreement in connection with the Project to which both the Authority and hubco are a party shall be binding on, and shall enure to the benefit of, hubco and the Authority and their respective statutory successors and permitted transferees and assignees.  [In the case of the Authority, its successors shall include any person to whom the Scottish Ministers, in exercising their statutory powers to transfer property, rights and liabilities of the Authority upon the Authority ceasing to exist, transfers the property, rights and obligations of the Authority under this Agreement, and such other agreements in connection with the Project to which the Authority and hubco are both a party].

  - hubco shall not, without the prior written consent of the Authority, assign, transfer, sub-contract or otherwise dispose of any interest in this Agreement, the Construction Contract, and [any other contract] entered into by hubco for the purposes of performing its obligations under this Agreement.

  - The Authority shall be entitled to assign, transfer or dispose of the whole of this Agreement and/or of any agreement entered into in connection with this Agreement to which the Authority and hubco are both party:

    - [to the Scottish Ministers, another Health Authority or any other person or body replacing any of the foregoing (or to whom the Scottish Ministers exercising his statutory rights would be entitled to transfer such benefits) covered by the National Health Service (Residual Liabilities) Act 1996;]

    - to any Permitted Transfer Participant which has sufficient financial standing or financial resources to perform the obligations of the Authority under this Agreement and any other agreements to which such assignation, transfer or disposal relates; or

    - any Participant (to which neither Clause 43.3.1 nor Clause 43.3.2 applies) whose obligations under this Agreement and any other agreements to which such assignation, transfer or disposal relates are unconditionally and irrevocably guaranteed by the Authority or a Minister of the Crown or the Scottish Ministers having the legal capacity, power and authority to perform the obligations under the guarantee and the obligations of the Authority under this Agreement and any other agreements to which such assignation, transfer or disposal relates,

without the consent of hubco.  The prior written consent of hubco (not to be unreasonably withheld or delayed) shall be required for any other assignation, transfer or disposal by the Authority of the whole or any part of this Agreement or of any agreement entered into in connection with this Agreement to which the Authority and hubco are both party, [provided that nothing in this Clause shall restrict the rights of the Scottish Ministers to effect a statutory transfer].

Sub-contractors

  - hubco shall:-

    - without prejudice to Clause 43.1 (Assignation), procure that none of the persons listed below shall sub-contract all (or substantially all) of their obligations under or in the agreement set out next to its name:-

| Person | Contract |
| --- | --- |
| Contractor | Construction Contract |

without, in each case, the prior written consent of the Authority (such consent not to be unreasonably withheld or delayed).  To avoid doubt, (i) any failure to comply with Clause 43.6 shall be a reasonable ground for withholding consent and (ii) consent shall, without prejudice to the other provisions of Clause 43.4, not be required in respect of the appointment of any party currently approved by the Authority as a suitable replacement.

  - If the contract set out next to the name of any person referred to in Clause 43.4 shall at any time lapse, terminate or otherwise cease to be in full force and effect (whether by reason of expiry or otherwise), with the effect that such person shall cease to act in relation to the Project, hubco shall forthwith appoint a replacement (subject to compliance with Clause 43.4 (Sub-contractors)).

  - hubco shall procure that any replacement for any person referred to in Clause 43.4 [or any Key Sub-Contractor] shall enter into a contract upon the same or substantially similar terms as the person so replaced and shall also enter into a collateral agreement on the same or substantially the same terms as the Collateral Agreement entered into by the person so replaced.

  - Where hubco enters into a contract with a sub-contractor for the purposes of carrying out the Project Operations or any part of the Project Operations under this Agreement, hubco shall cause a term to be included in such contract:

    - which requires (i) an application for an interim certificate in respect of a Relevant Month to be made by the sub-contractor not later than the date falling one (1) Business Day before the relevant Due Date (under this Agreement); (ii) the due date for payment of interim payments under such contract to occur on the date falling one (1) Business Days after the Due Date (under this Agreement); and (iii) the final date for payment of interim payments under such contract to on the date falling fourteen (14) Business Days after the due date for payment of interim payments under such contract and provides that, for the purpose of payment alone, where the Authority has made payment to hubco and the sub-contractor's invoice includes Project Operations in relation to which payment has been made by the Authority then, to the extent that it relates to such Project Operations, the invoice shall be treated as valid and payment shall be made to the subcontractor without deduction (but without prejudice to any right to deduct or set off validly arising under the terms of the contract with the sub-contractor); and

    - which notifies the sub-contractor that the contract forms part of a larger contract for the benefit of the Authority and that should the sub-contractor have any difficulty in securing the timely payment of an invoice that matter may be referred by the sub-contractor to the Authority's Representative; and

    - in the same terms as this Clause 43.7 (including for the avoidance of doubt this Clause 43.7.3) subject only to modification to refer to the correct designation of the equivalent party as the supplier and recipient of the relevant Project Operations as the case may be;

    - which requires any contract entered into by the sub-contractor and a sub-sub-contractor providing Project Operations to include a term in such contract:

      - which requires (i) an application for an interim certificate in respect of a Relevant Month to be made by the sub-sub-contractor not later than the date falling two (2) Business Days before the relevant Due Date (under this Agreement); (ii) the due date for payment of interim payments under such contract to occur on the date falling two (2) Business Days after the Due Date (under this Agreement); and (iii) the final date for payment of interim payments under such contract to on the date falling sixteen (16) Business Days after the due date for payment of interim payments  under such contract and provides that, for the purpose of payment alone, where the Authority has made payment to hubco and the sub-sub-contractor's invoice includes Project Operations in relation to which payment has been made by the Authority then, to the extent that it relates to such Project Operations, the invoice shall be treated as valid and payment shall be made to the sub-sub-contractor without deduction (but without prejudice to any right to deduct or set off validly arising under the terms of the contract with the sub-sub-contractor);

      - which notifies the sub-sub-contractor that the contract forms part of a larger contract for the benefit of the Authority and that should the sub-sub-contractor have any difficulty in securing the timely payment of an invoice that matter may be referred by the sub-sub-contractor to the Authority's Representative; and

      - in the same terms as this Clause 43.7.4 (including for the avoidance of doubt this Clause 43.7.4(c) subject only to modification to refer to the correct designation of the equivalent party as the supplier and recipient of the relevant Project Operations as the case may be

- 44MITIGATION

  - Each of the Authority and hubco shall at all times take all reasonable steps to minimise and mitigate any loss for which the relevant party is entitled to bring a claim against the other party pursuant to this Agreement.

- 45DATA PROTECTION

Data Protection

  - For the purpose of the following Clauses, the terms “controller”, “data subject”, "personal data", “process”, “processor” and “personal data breach” shall have the meaning given to them in the Data Protection Laws.

  - Each party hereby undertakes to the other that it shall comply with the obligations of a "controller" under the Data Protection Laws and undertakes that it will only process personal data as is necessary to perform its obligations under this Agreement (without prejudice to Clause 5.2 (General standards)) in accordance with the applicable Data Protection Laws.

  - In addition, each party (to the extent that it processes personal data as a processor on behalf of the other party (the “Controller Party”) [in accordance with Schedule Part 22]:

    - taking into account the nature of processing and in accordance with Article 32 of the GDPR, warrants that it has (and all subcontractors of any tier and their agents have) the appropriate technical and organisational measures in place against unauthorised or unlawful processing of personal data and against accidental loss or destruction of, or damage to, personal data held or processed by it;

    - has taken all reasonable steps to ensure the reliability and integrity of any of its staff (including consultants and agents) who will have access to personal data processed as part of this Agreement, and to ensure such persons shall have entered into an appropriate contractual agreement that requires them to keep the personal data confidential;

    - undertakes that it will act only on the documented instructions of the Controller Party in relation to the processing of any personal data made available by or on behalf of the Controller Party as part of this Agreement, and immediately inform the Controller Party if, in its opinion, an instruction infringes the Data Protection Laws;

    - shall make available to the Controller Party all information necessary to demonstrate compliance with this Clause 45.3 and undertakes to allow the Controller Party access to any relevant premises on reasonable notice to inspect its procedures described at Clause 45.3.1 above;

    - shall promptly, and in any event within forty-eight (48) hours of receipt of any request or correspondence, notify the Controller Party about any actual or suspected breach of this Clause 45.3 or the Data Protection Laws, or any actual or suspected personal data breach and shall:

      - implement any measures necessary to restore the security of compromised personal data; and

      - support the Controller Party in making any required notifications to any regulatory authority and affected data subjects;

    - shall promptly, and in any event within forty-eight (48) hours of receipt of any request or correspondence, notify the Controller Party if it receives a subject access request or notice from a data subject exercising their rights under the Data Protection Laws in respect of any personal data or any correspondence from a regulatory authority in relation to the processing of any personal data on behalf of the Controller Party;

    - shall not sub-contract any processing of personal data without the Controller Party’s written consent;

    - shall comply with the obligations imposed on a processor under the Data Protection Laws and use all reasonable endeavours to assist the Controller Party in complying with the requirements of the Data Protection Laws (including the obligations pursuant to Articles 32 to 36 of the GDPR (inclusive));

    - upon termination of this Agreement and on the instructions of the Controller Party, shall return to the Controller Party or destroy all copies of the personal data, except to the extent it is required to keep any copies by law of the UK or the European Union; and

    - shall not transfer any personal data outside the European Economic Area without the Controller Party’s prior written consent.

  - Where a party sub-contracts any processing in accordance with Clause 45.3.7, that party shall impose the same data protection obligations in this Agreement as required by Data Protection Laws on the sub-processor by way of a written contract. The party sub-contracting processing in accordance with Clause 45.3.7 shall remain fully liable to the Controller Party for the performance of its obligations.

  - [At the time the Controller Party requires the other party to process personal data on the Controller Party’s behalf, the parties shall identify and agree in writing, in the form set out in Schedule Part 22, in accordance with this Agreement and Article 28 of the GDPR, the subject matter and duration of the processing, the nature of the processing, the type of personal data, categories of data subjects and the obligations and rights of the Controller Party.]

- 46ConfidentialITY

  - The Authority shall, subject to Clause 46.2 be entitled to make the documents and information listed in this Clause 46.1 freely available to the public (which may include, without limitation, publication on the Authority’s website):

    - this Agreement;

    - the Collateral Agreements; and

    - [		],

- and hubco acknowledges and agrees that, subject to the exclusion of information referred to in Clause 46.2.2, the provision or publication of the documents listed in the Clause 46.1 shall not give rise to any liability under the terms of this Agreement or otherwise. The Authority shall notify hubco in writing not less than ten (10) Business Days prior to any intended provision or publication of information pursuant to this Clause 46.1

    - The parties agree that the provisions of this Agreement and each Project Document shall, subject to Clause 46.2.2 below, not be treated as Confidential Information and may be disclosed without restriction and hubco acknowledges that the Authority shall, subject to Clause 46.2.2 below, be entitled to make this Agreement and each Project Document available in the public domain.

    - Clause 46.2.1 above shall not apply to provisions of this Agreement or a Project Document designated as Commercially Sensitive Information and listed in Schedule Part 17 (Commercially Sensitive Information)] to this Agreement which shall, subject to Clause 48.2, be kept confidential for the periods specified in that Part.

    - The parties shall keep confidential all Confidential Information received by one party from the other party relating to this Agreement and Project Documents or the Project and shall use all reasonable endeavours to prevent their employees and agents from making any disclosure to any person of any such Confidential Information.

Permitted Disclosure

  - Clauses 46.2.2 and 46.2.3 shall not apply to:-

    - any disclosure of information that is reasonably required by any person engaged in the performance of their obligations under this Agreement for the performance of those obligations;

    - any matter which a party can demonstrate is already or becomes generally available and in the public domain otherwise than as a result of a breach of this Clause;

    - any disclosure to enable a determination to be made under Schedule Part 15 (Dispute Resolution Procedure) or in connection with a dispute between hubco and any of its sub-contractors;

    - any disclosure which is required pursuant to any Law or Parliamentary obligation placed upon the party making the disclosure or the rules of any stock exchange or governmental or regulatory authority having the force of Law or, if not having the force of Law, compliance with which is in accordance with the general practice of persons subject to the stock exchange or governmental or regulatory authority concerned;

    - any disclosure of information which is already lawfully in the possession of the receiving party, prior to its disclosure by the disclosing party;

    - any provision of information to the parties’ own professional advisers or insurance advisers or, where it is proposed that a person should or may provide funds (whether directly or indirectly and whether by loan, equity participation or otherwise) to hubco to enable it to carry out its obligations under this Agreement, or may wish to acquire shares in hubco in accordance with the provisions of this Agreement to that person or their respective professional advisers but only to the extent reasonably necessary to enable a decision to be taken on the proposal;

    - any disclosure by the Authority of information relating to the design, construction, operation and maintenance of the Project and such other information as may be reasonably required for the purpose of conducting a due diligence exercise, to any proposed new contractor, its advisers and lenders, should the Authority decide to retender this Agreement;

    - any registration or recording of the Consents and property registration required;

    - any disclosure of information by the Authority to any other department, office or agency of the Government or their respective advisers or to the Scottish Futures Trust or to any person engaged in providing services to the Authority for any purpose related to or ancillary to this Agreement;

    - any disclosure for the purpose of:-

      - the examination and certification of the Authority's or hubco's accounts;

      - any examination pursuant to Section 6(1) of the National Audit Act 1983 of the economy, efficiency and effectiveness with which the Authority has used its resources;

      - complying with a proper request from either party’s insurance adviser, or insurer on placing or renewing any insurance policies; or

      - (without prejudice to the generality of Clause 46.3.4 above) compliance with the FOI(S)A and/or the Environmental Information (Scotland) Regulations;

    - disclosure pursuant to Clause 46.11 (Department of Health Disclosure); or

    - disclosure to the extent required pursuant to Clause 48 (Information and Audit Access)

    - [Identify here disclosure requirements to other public bodies where Facilities are joint facilities],

provided that, to avoid doubt, neither Clause (d) nor Clause 46.3.4 above shall permit disclosure of Confidential Information otherwise prohibited by Clause 46.2.3 (Confidential Information) where that information is exempt from disclosure under section 36 of the FOI(S)A.

  - Where disclosure is permitted under Clause 46.3 (Permitted disclosure), other than under Clauses 46.3.2, 46.3.4, 46.3.5, 46.3.8 and 46.11, the party providing the information shall procure that the recipient of the information shall be subject to the same obligation of confidentiality as that contained in this Agreement.

  - hubco shall not make use of this Agreement or any information issued or provided by or on behalf of the Authority in connection with this Agreement otherwise than for the purpose of this Agreement, except with the written consent of the Authority.

  - Where hubco, in carrying out its obligations under this Agreement, is provided with information relating to any Authority Party, hubco shall not disclose or make use of any such information otherwise than for the purpose for which it was provided, unless hubco has sought the prior written consent of that person and has obtained the prior written consent of the Authority.

  - Subject to Clause 45.3.9, on or before the expiry of the Defects Liability Period, hubco shall ensure that all documents or computer records in its possession, custody or control, which contain information relating to any patient or Authority Party including any documents in the possession, custody or control of a hubco Party, are delivered up to the Authority.

  - The parties acknowledge that Audit Scotland has the right to publish details of this Agreement (including Commercially Sensitive Information) in its relevant reports to Parliament.

  - The provisions of this Clause 46 (Confidentiality) are without prejudice to the application of the Official Secrets Acts 1911 to 1989.

Announcements

  - Without prejudice to Clauses 46.1 and 46.2, unless otherwise required by any Law or any regulatory or governmental authority (but only to that extent), neither party shall make or permit or procure to be made any public announcement or disclosure (whether for publication in the press, the radio, television screen or any other medium) of any Confidential Information or in the case of hubco of its (or any hubco Party's) interest in the Project or, in any such case, any matters relating thereto, without the prior written consent of the other party (which shall not be unreasonably withheld or delayed).

Department of Health Disclosure

  - Subject to Clause 46.12, the Authority shall be free to disclose the terms of this Agreement, and the Collateral Agreements to the Scottish Government Health Directorates and/or HM Treasury and the parties agree that the Authority shall be free to use and disclose such information on such terms and in such manner as the Scottish Government and/or HM Treasury see fit.

  - The Authority shall notify hubco in writing not less than ten (10) Business Days prior to any intended disclosure of the terms of any of the documents referred to in Clause 46.11 to the Scottish Government and/or HM Treasury.  hubco shall notify the Authority in writing of any terms of such documents (the "Sensitive Information") that hubco objects to being disclosed within five (5) Business Days of any such notification by the Authority (failing which hubco shall be deemed to have notified the Authority that it has no objection to any such disclosure).  Without prejudice to the Authority's right to disclose the Sensitive Information pursuant to Clause 47.5, the Authority shall consult with hubco following receipt of a notification from hubco that it objects to disclosure of such Sensitive Information with a view to agreeing whether or not part or all of the Sensitive Information can be removed from the information to be disclosed.

- 47Freedom of Information

  - hubco acknowledges that the Authority is subject to the requirements of the FOI(S)A and the Environmental Information (Scotland) Regulations and shall assist and co-operate with the Authority to facilitate the Authority's compliance with its Information disclosure requirements pursuant to the same in the manner provided for in Clauses 47.2 to 47.8.

  - Where the Authority receives a Request for Information in relation to Information that hubco is holding on its behalf and which the Authority does not hold itself the Authority shall refer to hubco such Request for Information as soon as practicable and in any event within five (5) Business Days of receiving such Request for Information and hubco shall:-

    - provide the Authority with a copy of all such Information in the form that the Authority requires as soon as practicable and in any event within five (5) Business Days (or such other period as the Authority acting reasonably may specify) of the Authority's request; and

    - provide all necessary assistance as reasonably requested by the Authority in connection with any such Information, to enable the Authority to respond to the Request for Information within the time for compliance set out in section 10 of the FOI(S)A or Regulation 5 of the Environmental Information (Scotland) Regulations.

  - Following notification under Clause 47.2, and up until such time as hubco has provided the Authority with all the Information specified in Clause 47.2.1 hubco may make representations to the Authority as to whether or not or on what basis Information requested should be disclosed, and whether further information should reasonably be provided in order to identify and locate the information requested, provided always that the Authority shall be responsible for determining at its absolute discretion:-

    - whether Information is exempt from disclosure under the FOI(S)A and the Environmental Information (Scotland) Regulations;

    - whether Information is to be disclosed in response to a Request for Information, and

in no event shall hubco respond directly, or allow its Sub-Contractors to respond directly, to a Request for Information unless expressly authorised to do so by the Authority.

  - hubco shall ensure that all Information held on behalf of the Authority is retained for disclosure for at least the number of years (from the date it is acquired) [specified in the Authority Policy relating to records retention] and shall permit the Authority to inspect such Information as requested from time to time. Following the expiry of such [ l ] period, hubco shall be entitled to dispose of such records in circumstances in which hubco has notified the Authority of such proposed disposal and the Authority has not requested within [twenty (20)] Business Days of such notification that such Information be handed over to the Authority.

  - hubco shall transfer to the Authority any Request for Information received by hubco as soon as practicable and in any event within two (2) Business Days of receiving it.

  - hubco acknowledges that any lists provided by it listing or outlining Confidential Information are of indicative value only and that the Authority may nevertheless be obliged to disclose Confidential Information in accordance with the requirements of FOI(S)A and the Environmental (Scotland) Regulations.

  - In the event of a request from the Authority pursuant to Clause 47.2, hubco shall as soon as practicable, and in any event within five (5) Business Days of receipt of such request, inform the Authority of hubco's estimated costs of complying with the request to the extent these would be recoverable, if incurred by the Authority, under Section 13(1) of the FOI(S)A and the Fees Regulations.  Where such costs (either on their own or in conjunction with the Authority's own such costs in respect of such Request for Information) will exceed the appropriate limit referred to in Section 12(1) of the FOI(S)A and as set out in the Fees Regulations (the "Appropriate Limit") the Authority shall inform hubco in writing whether or not it still requires hubco to comply with the request and where it does require hubco to comply with the request the ten (10) Business Days period for compliance shall be extended by such number of additional days for compliance as the Authority is entitled to under Section 10 of the FOI(S)A.  In such case, the Authority shall notify hubco of such additional days as soon as practicable after becoming aware of them and shall reimburse hubco for such costs as hubco incurs in complying with the request to the extent it is itself entitled to reimbursement of such costs in accordance with its own FOI(S)A policy from time to time.

  - hubco acknowledges that (notwithstanding the provisions of Clause 46 (Confidentiality)) the Authority may, acting in accordance with the Scottish Ministers Code of Practice on the Discharge of Functions of Public Authorities under Part 6 of the Freedom of Information (Scotland) Act 2002 (the "Code"), and/or having full regard to any guidance or briefings issued by the Scottish Information Commissioner or the Scottish Ministers, be obliged under the FOI(S)A, or the Environmental Information (Scotland) Regulations to disclose Information concerning hubco or the Project:-

    - in certain circumstances without consulting with hubco; or

    - following consultation with hubco and having taken their views into account,

provided always that where Clause 47.8.1 above applies the Authority shall, in accordance with the recommendations of the Code, draw this to the attention of hubco prior to any disclosure.

  - In the event that hubco is or becomes subject to Environmental Information (Scotland) Regulations or FOI(S)A it shall comply with its obligations under Environmental Information (Scotland) Regulations and FOI(S)A.  In doing so, it will use reasonable endeavours to consult the Authority before disclosing Information about them or any agreement entered into between the Authority and hubco.

- 48Information and Audit Access

  - hubco shall provide to the Authority's Representative all information, documents, records and the like in the possession of, or available to, hubco (and to this end hubco shall use all reasonable endeavours to procure that all such items in the possession of the Contractor shall be available to it and hubco has included, or shall include, relevant terms in all contracts with the Contractor to this effect) as may be reasonably requested by the Authority's Representative for any purpose in connection with this Agreement including in relation to the use and operation of the Project Bank Account.

  - For the purpose of:-

    - the examination and certification of the Authority's accounts; or

    - any examination pursuant to Section 23 of the Public Finance and Accountability (Scotland) Act 2000 of the economy, efficiency and effectiveness with which the Authority has used its resources,

the Auditor General for Scotland may examine such documents as he may reasonably require which are owned, held or otherwise within the control of hubco (and hubco shall procure that any person acting on its behalf who has such documents and/or other information shall also provide access) and may require hubco to produce such oral or written explanations as he considers necessary.

  - hubco shall provide and shall procure that its Sub-Contractors shall provide such information as the Authority may reasonably require from time to time to enable it to meet its obligations to provide reports and returns pursuant to regulations, directions or guidance applicable to the Authority including, without limitation, reports and returns regarding the physical condition of buildings occupied by the Authority, health and safety, under the firecode, relating to environmental health, the operation and administration of the Project Bank Account and to comply with [requirements for the provision of information relating to achievement of customer service targets].

- 49NOTICES

  - All notices under this Agreement shall be in writing and all certificates, notices or written instructions to be given under the terms of this Agreement shall be served by sending the same by first class post, facsimile, by hand or by email sending the same to:-

| If to hubco | Address: Fax No: Email: |
| --- | --- |
| If to the Authority | Address: Fax No: Email: |
| Where any information or documentation is to be provided or submitted to the Authority's Representative or the hubco Representative it shall be provided or submitted by sending the same by first class post, facsimile, by hand or by email sending the same to: |  |
| If to hubco’s Representative | Address: Fax No: Email |
| If to the Authority's Representative | Address: Fax No: Email: |
| (copied in each case to the Authority) |  |

  - Either party to this Agreement may change its nominated address, facsimile number or email address by prior notice to the other party.

  - Notices given by post shall be effective upon the earlier of (i) actual receipt, and (ii) five (5) Business Days after mailing.  Notices delivered by hand shall be effective upon delivery.  Notices given by facsimile shall be deemed to have been received where there is confirmation of uninterrupted transmission by a transmission report and where there has been no telephonic communication by the recipient to the senders (to be confirmed in writing) that the facsimile has not been received in legible form:-

    - within two (2) hours after sending, if sent on a Business Day between the hours of 9am and 4pm; or

    - by 11am on the next following Business Day, if sent after 4pm, on a Business Day but before 9am on that next following Business Day.

  - Notices given by email shall be deemed to have been received:

    - at the time the email enters the Information System of the intended recipient designated by them to receive electronic notices pursuant to this Agreement (as identified by the email address specified in Clause 49.1 or as notified from time to time under Clause 49.2) if on a Business Day between the hours of 9am and 4pm; or

    - by 11am on the next following Business Day, if the email enters the intended recipient’s Information System after 4pm, on a Business Day but before 9am on the next following Business Day;

- and provided that no error message indicating failure to deliver has been received by the sender and provided further that within 24 hours of transmission a hard copy of the e-mail signed by or on behalf of the person giving it is sent by post or delivered by hand to the intended recipient in accordance with the provisions of Clauses 49.1 and 49.2.

- 50NO WAIVER

  - Any relaxation, forbearance, indulgence or delay (together "indulgence") of any party in exercising any right shall not be construed as a waiver of the right and shall not affect the ability of that party subsequently to exercise that right or to pursue any remedy, nor shall any indulgence constitute a waiver of any other right (whether against that party or any other person).

- Continued Effect – no waiver

- Notwithstanding any breach of this Agreement by either party, and without prejudice to any other rights which the party may have in relation to it, the other party may elect to continue to treat this Agreement as being in full force and effect and to enforce its rights under this Agreement. The failure of any party to exercise any right under this Agreement, including any right to terminate this Agreement and any right to claim damages, shall not be deemed a waiver of such right for any continuing or subsequent breach.

- 51NO AGENCY

  - Nothing in this Agreement shall be construed as creating a partnership or as a contract of employment between the Authority and hubco.

  - Save as expressly provided otherwise in this Agreement, hubco shall not be, or be deemed to be, an agent of the Authority and hubco shall not hold itself out as having authority or power to bind the Authority in any way.

  - Without limitation to its actual knowledge, hubco shall for all purposes of this Agreement, be deemed to have such knowledge in respect of the Project as is held (or ought reasonably to be held) by any hubco Party.

- 52ENTIRE AGREEMENT

  - Except where expressly provided otherwise in this Agreement, this Agreement constitutes the entire agreement between the parties in connection with its subject matter and supersedes all prior representations, communications, negotiations and understandings concerning the subject matter of this Agreement.

  - Each of the parties acknowledges that:-

    - it does not enter into this Agreement on the basis of and does not rely, and has not relied, upon any statement or representation (whether negligent or innocent) or warranty or other provision (in any case whether oral, written, express or implied) made or agreed to by any person (whether a party to this Agreement or not) except those expressly repeated or referred to in this Agreement and the only remedy or remedies available in respect of any misrepresentation or untrue statement made to it shall be any remedy available under this Agreement; and

    - this Clause shall not apply to any statement, representation or warranty made fraudulently, or to any provision of this Agreement which was induced by fraud, for which the remedies available shall be all those available under the Law governing this Agreement.

- 53THIRD PARTY RIGHTS

  - Save to the extent expressly provided in this Agreement and, to avoid doubt, without prejudice to the rights of any permitted successor to the rights of hubco or of any permitted assignee, it is expressly declared that no rights shall be conferred under and arising out of this Agreement (whether under the Contract (Third Party Rights) (Scotland) Act 2017 or otherwise) upon any person other than the Authority and hubco.

- 54SEVERABILITY

  - If any provision of this Agreement shall be declared invalid, unenforceable or illegal by the courts of any jurisdiction to which it is subject, such provision may be severed and such invalidity, unenforceability or illegality shall not prejudice or affect the validity, enforceability and legality of the remaining provisions of this Agreement.

- 55Conflicts of Agreements

  - In the event of any conflict between this Agreement and the Project Documents, the provisions of this Agreement shall prevail.

- 56COSTS AND EXPENSES

  - Each party shall be responsible for paying its own costs and expenses incurred in connection with the negotiation, preparation and execution of this Agreement.

- 57GOVERNING LAW AND JURISDICTION

  - This Agreement shall be considered as a contract made in Scotland and shall be subject to the Laws of Scotland.

  - Subject to the provisions of the Dispute Resolution Procedure, both parties agree that the courts of Scotland shall have exclusive jurisdiction to hear and settle any action, suit, proceeding or dispute in connection with this Agreement and irrevocably submit to the jurisdiction of those courts.

- 58Further Assurance

  - Each party shall do all things and execute all further documents necessary to give full effect to this Agreement.

- COUNTERPARTS AND DELIVERY

  - This Agreement may be executed in any number of counterparts and by each of the parties on separate counterparts.

  - Where executed in counterparts:

    - this Agreement will not take effect until each of the counterparts has been delivered;

    - where any counterpart is being held as undelivered, delivery will take place on the date of delivery agreed [among]/[between] the parties (the “agreed date”).  The agreed date will be inserted [in the testing clause] of this Agreement; and

    - [section 2(3) of the Legal Writings (Counterparts and Delivery) (Scotland) Act 2015 is hereby excluded and shall not apply to the execution arrangements in respect of this Agreement ].

IN WITNESS WHEREOF these presents consisting of this and the preceding [          ] pages together with the Schedule in [          ] Parts are executed in counterpart as follows and DELIVERED on [ l ]:

SCHEDULE

- DEFINITIONS AND INTERPRETATION

SECTION 1

- DEFINITIONS

In this Agreement unless the context otherwise requires:-

| "Actual Completion Date" |  | means the later of: (a) the date of the Certificate of Completion; and (b) subject to Clause 14.10, the Completion Date; or (c) in the event of a dispute as such date may be determined in accordance with Schedule Part 15 (Dispute Resolution Procedure) |
| --- | --- | --- |
| "Adjudication Panel" |  | has the meaning given in paragraph 4.2.1 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Adjudicator" |  | means such person selected in accordance with paragraph 4 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Amended Reinstatement Outline" |  | has the meaning given in Clause 39.20.3 |
| "Ancillary Rights" |  | means such rights set out in Section 3 Ancillary Rights) of Schedule Part 4 (Land Matters) as the same may be varied with the approval of the Authority such approval not to be unreasonably withheld |
| “Application Date” | means the date specified as such in respect of each Relevant Month in the Application Schedule |  |
| “Application Schedule” | means the document at Section 3 (Application Schedule) of Schedule Part 20 (Project Bank Account) |  |
| "Application for Payment" |  | has the meaning given in Clause 27.2 (Applications for Payment) |
| "Appropriate Limit" |  | has the meaning given in Clause 47.7 |
| "Approved RDD Item" |  | means an item of Reviewable Design Data which has been returned or has been deemed to have been returned endorsed either "Level A – no comment" or "Level B – proceed subject to amendment as noted" by the Authority's Representative pursuant to the provisions of Clause 12 (Design, Construction and Commissioning Process) and Schedule Part 7 (Review Procedure) (provided that in the case of any item of Reviewable Design Data which has been returned or has been deemed to have been returned endorsed "Level B – proceed subject to amendment as noted" hubco has taken account of the Authority's Representative's comments), as such item of Reviewable Design Data may be varied or amended from time to time in accordance with Schedule Part 13 (Variation Procedure) |
| "Associated Companies" |  | means, in respect of a relevant company, a company which is a Subsidiary, a Holding Company or a company that is a Subsidiary of the ultimate Holding Company of that relevant company, and in the case of hubco shall include each of the Shareholders, and the term "Associate" shall be interpreted accordingly |
| "Authority Assets" |  | means the Facilities and any assets and Equipment or other property used by, or on behalf of, the Authority or any Authority Party |
| "Authority Design Data" |  | means all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the design, construction, testing and/or operation of the Facilities (excluding any hubco Design Data) |
| "Authority Events of Default" |  | has the meaning given in Clause 31 |
| "Authority Party" |  | means any of the Authority's agents, contractors and sub-contractors of any tier and its or their directors, officers and employees and/or [Community Services Providers] ] [and any of the Community Services Providers’ agents, contractors and sub-contractors of any tier and its or their directors, officers and employees] at the Facilities with the authority of the Authority but excluding hubco, any hubco Party and statutory undertakers and utilities and "Authority Parties" shall be construed accordingly |
| “Authority Planning Conditions” | means the planning conditions set out in Part C in Section 1 in Schedule Part 5 (Construction Matters) |  |
| "Authority Works Variation" |  | has the meaning given in Schedule Part 13 (Variation Procedure) |
| "Authority's Commissioning" |  | means the Authority's pre-completion commissioning activities to be carried out by the Authority in accordance with Clause 16 (Pre-Completion Commissioning and Completion) |
| "Authority's Construction Requirements" |  | means the requirements of the Authority (including the Authority's requirements for the design and construction of the hubco Designed Portion where applicable) set out or identified in Section 3 (Authority’s Construction Requirements) of Schedule Part 5 (Construction Matters) as amended from time to time in accordance with the terms of this Agreement |
| "Authority's Post Completion Commissioning" |  | means the Authority's post-completion commissioning activities to be carried out by the Authority in accordance with Clause 18.1 (Post Completion Commissioning) |
| "Authority's Representative" |  | means the person so appointed by the Authority pursuant to Clause 8 (Representatives) |
| "Beneficiary" |  | has the meaning given in Clause 36.3 (Conduct of Claims) |
| “Below Threshold Sub-Contractor” | means a Sub-Contractor with a Sub-Contract Value less than one per cent (1%) of the Development Amount |  |
| “BIM Modelling Data” | means the latest version of any modelling data produced by or on behalf of hubco in relation to the Project, which demonstrates certain aspects of the 3D environment of the Facilities and is compliant to a standard of BIM level 2, using CAD modelling software |  |
| “BIM Protocol” | means the agreed building information modelling protocol set out in Section 9 of Schedule Part 5 (Construction Matters) |  |
| "Business Day" |  | means a day other than a Saturday, Sunday or a bank holiday in Edinburgh |
| "CDM Regulations" |  | has the meaning given in Section 2 of Schedule Part 5 (Construction Matters) |
| "Certificate of Making Good Defects" |  | has the meaning given in Clause 17.4 and in the form set out in Section 3 of Schedule Part 16 (Certificates) |
| "Certificate of Completion" |  | means the certificate to be issued by the Authority's Representative in accordance with Clause 16.11 (Pre-Completion Commissioning and Completion) in the form set out in Section 1 of Schedule Part 16 (Certificates) |
| "Change in Law" |  | means the coming into effect or repeal (without re-enactment or consolidation) in Scotland of any Law, or any amendment or variation to any Law, or any judgement of a relevant court of law which changes binding precedent in Scotland in each case after the date of this Agreement |
| "Code" |  | has the meaning given in Clause 47.8 |
| "Collateral Agreements" |  | means the Contractor's Collateral Agreement [and the Key Sub-Contractor Collateral Agreements] |
| "Commercially Sensitive Information" |  | means the sub set of Confidential Information listed in [column 1 of Error: Reference source not found (Commercially Sensitive Contractual Provisions) and column 1 of Error: Reference source not found (Commercially Sensitive Material) of Schedule Part 17 (Commercially Sensitive Information) in each case for the period specified in column 2 of Error: Reference source not found and of Schedule Part 17] |
| "Commissioners" |  | has the meaning given in Clause 28 (VAT) |
| "Commissioning Completion Certificate" |  | means the certificate to be issued by the Authority's Representative in accordance with Clause 18.4 in the form set out in Section 2 of Schedule Part 16 (Certificates) |
| "Commissioning End Date" |  | means the date by which the parties' commissioning activities are to be completed in accordance with the Final Commissioning Programme |
| "Community Services" |  | means [Authority to complete on a project specific basis to reflect services (whether public facing or administrative or support services) being provided at the Facilities] and such other services as may be notified to hubco by the Authority from time to time |
| "Community Services Provider" |  | means any organisation (excluding for the avoidance of doubt the Authority) providing any of the Community Services at the Facilities from time to time |
| "Compensation Event" |  | has the meaning given in Clause 22.9 |
| "Completion Date" |  | means [ ] or such revised date as may be specified by the Authority’s Representative pursuant to Clause 22 or such other dates as may be agreed by the parties |
| "Confidential Information" |  | means:- - information that ought to be considered as confidential (however it is conveyed or on whatever media it is stored) and may include information whose disclosure would, or would be likely to, prejudice the commercial interests of any person, trade secrets, Intellectual Property Rights and know-how of either party and all personal data and sensitive personal data within the meaning of the Data Protection Laws and - Commercially Sensitive Information. |
| "Consents" |  | means all permissions, consents, approvals, certificates, permits, licences, statutory agreements and authorisations required by Law, and all necessary consents and agreements from any third parties (including, without limitation, any Planning Permission), needed to carry out the Project Operations in accordance with this Agreement |
| "Consolidated Adjudication Costs" |  | has the meaning given in paragraph 4.12.3 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Construction Contract" |  | means the build contract dated the same date as this Agreement between hubco and the Contractor (which, as at the date of this Agreement, is in the Agreed Form) as amended from time to time in accordance with this Agreement |
| "Construction Contract Dispute" |  | has the meaning given in paragraph 6.1 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Construction Phase" |  | means the period from and including the Execution Date to and including the Actual Completion Date |
| "Construction Quality Plan" |  | means the document at Section 8 of Schedule Part 5 (Construction Matters) |
| "Contamination" |  | means all or any pollutants or contaminants, including any chemical or industrial, radioactive, dangerous, toxic or hazardous substance, waste or residue (whether in solid, semi-solid or liquid form or a gas or vapour) and including without limitation genetically modified organisms |
| "Contracting Associate" |  | means the Contractor, [any other entity which performs on behalf of hubco any material function in connection with this Agreement or the Project Operations] |
| "Contractor" |  | means [insert the name of Contractor] engaged by hubco to carry out the Works and any substitute building contractor engaged by hubco as may be permitted by this Agreement |
| "Contractor's Collateral Agreement" |  | means the collateral agreement among the Authority, hubco and the Contractor set out in Section 1 of Schedule Part 8 (Collateral Agreement) |
| "Contractor's Site Manager" |  | means the manager to be appointed by the Contractor for purposes of supervision of all day-to-day activities on Site |
| "Contractor's Site Rules" |  | means the Contractor's rules, applicable on Site to the Authority, hubco, the Contractor and their respective sub-contractors and suppliers of every tier during the construction of the Facilities |
| “Data Protection Laws” | means any law, statute, declaration, decree, directive, legislative enactment, order, ordinance, regulation, rule or other binding restriction (as amended, consolidated or re-enacted from time to time) which relates to the protection of individuals with regards to the processing of personal data to which a party is subject, including: (i) the Data Protection Act 1998 and EC Directive 95/46/EC (up to and including 24 May 2018), and (ii) the GDPR (on and from 25 May 2018); or, in the event that the UK leaves the European Union, all legislation enacted in the UK in respect of the protection of personal data |  |
| “Declaration of Trust” | means the declaration of trust in the form set out in Section 1 (Declaration of Trust) of Schedule Part 20 (Project Bank Account) dated on or around the date hereof among the Authority, hubco and the Contractor relating to facilitating the making of payments in connection with the Project to hubco, the Contractor and Sub-Contractors |  |
| “Deemed Allocation” | has the meaning given to that term in Clause 27.11B of this Agreement |  |
| "Default Interest Rate" |  | means 2% over LIBOR |
| "Defects" |  | means any defect or fault in the Works and/or the Facilities (not being a Snagging Matter) which occurs due to a failure by hubco to comply with the Authority's Construction Requirements and/or hubco's Proposals or otherwise to comply with its obligations under this Agreement |
| "Defects Liability Period" |  | means the period of 12 months from the Actual Completion Date |
| "Delay Event" |  | has the meaning given in Clause 22 (Delay Events) |
| "Development Amount" |  | means the sum of £[INSERT SUM] |
| "Development Amount Analysis" |  | means the development amount analysis set out at Schedule Part 11 (Development Amount Analysis) |
| "Direct Losses" |  | means, subject to the provisions of Clause 40 (Limits on liability), all damage, losses, liabilities, claims, actions, costs, expenses (including the cost of legal or professional services, legal costs being on an agent/client, client paying basis), proceedings, demands and charges whether arising under statute, contract or at common law but, to avoid doubt, excluding Indirect Losses |
| "Disclosed Data" |  | means any Authority Design Data and any other written information, data and documents made available or issued to hubco or any hubco Party in connection with the Project by or on behalf of the Authority (or any Authority Party) whether before or after the execution of this Agreement |
| "Dispute" |  | has the meaning given in paragraph 1 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Dispute Resolution Procedure" |  | means the procedure set out in Schedule Part 15 (Dispute Resolution Procedure) |
| "Due Date" |  | has the meaning given in Clause 27.2 |
| "Environmental Information (Scotland) Regulations" |  | means the Environmental Information (Scotland) Regulations 2004 together with any guidance and/or codes of practice issued by the Scottish Information Commissioner or relevant Government Department in relation to such regulations |
| "Equipment" |  | has the meaning given in Schedule Part 10 |
| "Execution Date" |  | means the last date of execution of this Agreement |
| "Executive" |  | has the meaning given in Schedule Part 13 (Variation Procedure) |
| "Facilities" |  | means [INSERT ON PROJECT SPECIFIC BASIS] together with all supporting infrastructure (including the Plant and amenities located on the Site as required to enable hubco to comply with its obligations under this Agreement, all as the same may be varied, amended or supplemented from time to time in accordance with this Agreement |
| "Fees Regulations" |  | means the Freedom of Information (Fees for Required Disclosure (Scotland) Regulations 2004 |
| "Final Commissioning Programme" |  | means the programme to be jointly developed and agreed by the Authority and hubco in accordance with the provisions of Clause 16.2 (Pre-Completion Commissioning and Completion) |
| "Final Date" |  | has the meaning given in Clause 27.8 |
| "Finishes" |  | means the finishes listed in the table set out in paragraph 1.2.3 of Schedule Part 7 (Review Procedure) |
| "FOI(S)A" |  | means the Freedom of Information (Scotland) Act 2002 and any subordinate legislation (as defined in section 73 of the Freedom of Information (Scotland) Act 2002) made under the Freedom of Information (Scotland) Act 2002 from time to time together with any guidance and/or codes of practice issued by the Scottish Information Commissioner or relevant Government department in relation to such Act |
| "Force Majeure" |  | has the meaning given in Clause 24 (Force Majeure) |
| “GDPR” | means Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and repealing Directive 95/46/EC (General Data Protection Regulation) OJ L 119/1, 4.5.2016 |  |
| "Good Industry Practice" |  | means using standards, practices, methods and procedures conforming to the Law and exercising that degree of skill and care, diligence, prudence and foresight which would reasonably and ordinarily be expected from a skilled and experienced person engaged in a similar type of undertaking under the same or similar circumstances |
| "Government" |  | means the government of the United Kingdom or the Scottish Ministers |
| "Health Authority" |  | means a Health Authority established under Section 2 of the National Health Service (Scotland) Act 1978 (or any successor body to any such body established with substantially the same powers or duties) |
| "Holding Company" |  | has the meaning given to it in Section 1159 of the Companies Act 2006 |
| “hubco Consents” |  | means those Consents set in out Part B of Section 1 of Schedule Part 5 (Construction Matters) |
| “hubco Design Data” |  | means drawings, reports, documents, plans, software, formulae, calculations and other data relating to the hubco Designed Portion produced or to be produced by or behalf of hubco |
| "hubco Designed Portion" |  | means [ l ] |
| "hubco Designed Portion Design Quality Plan” |  | means, if applicable, the document at Section 8 of Schedule Part 5 (Construction Matters) |
| “hubco Event of Default” |  | has the meaning given to it in Clause 32.1 |
| “hubco Party” |  | means hubco’s agents and contractors (including without limitation the Contractor) and sub-licensees and its or their sub-contractors of any tier and its or their directors, officers, employees and workmen in relation to the Project and any Project Operations, and “hubco Parties” shall be construed accordingly |
| “hubco’s Post Completion Commissioning” |  | means hubco’s post-completion commissioning activities to be carried out by hubco in accordance with Clause 18.1 (Post Completion Commissioning) |
| “hubco’s Pre-Completion Commissioning” |  | means hubco’s pre-completion commissioning activities to be carried out by hubco in accordance with Clause 16.6 |
| “hubco’s Proposals” |  | means the proposals of hubco to deliver the Project to comply with the Authority’s Construction Requirements, as set out in Section 4 of Schedule Part 5 |
| “hubco Representative” |  | means the person so appointed by hubco pursuant to Clause 8 (Representatives) |
| “Indemnifier” |  | has the meaning given in Clause 36.3 (Conduct of Claims) |
| “Indirect Losses” |  | has the meaning given in Clause 40 (Limits on Liability). |
| “Information” |  | has the meaning given under Section 73 of the Freedom of Information (Scotland) Act 2002 |
| [“Information Release Schedule” |  | means the information release schedule set out in Schedule Part [ l ] (Information Release Schedule)] |
| “Information System” | means a system for generating, sending, receiving, storing or otherwise processing electronic communications |  |
| “Insurance Proceeds Account” |  | means the account numbered [INSERT NUMBER] in the joint names of hubco and the Authority |
| “Insurance Term” |  | means any terms and/or conditions required to be included in a policy of insurance by Clause 39 and/or Schedule Part 12 (Insurance Requirements) but excluding any risk |
| “Insurances” |  | means, as the context requires, all or any of the insurances required to be maintained by hubco pursuant to this Agreement |
| “Intellectual Property” |  | means all registered or unregistered trade marks, service marks, patents, registered designs, utility models, applications for any of the foregoing, copyrights, unregistered designs, the sui generis rights of extraction relating to databases, trade secrets and other confidential information or know-how |
| “Intellectual Property Rights” |  | means the Intellectual Property which (or the subject matter of which) is created, brought into existence, acquired, used or intended to be used by hubco, any hubco Party, the Authority or any Authority Party, or by other third parties (for the use by or on behalf of or for the benefit of hubco or the Authority) for the purposes of the design or construction of the Facilities, the operation, maintenance, improvement and/or testing of the Facilities or the conduct of any other Project Operation or otherwise for the purposes of this Agreement |
| “Interim Certificate” |  | has the meaning given in Clause 27.5 |
| “Joining Declaration” |  | means a joining declaration entered into by the Authority, hubco, the Contractor and a Sub-Contractor or Sub-Contractors in the form set out in Section 2 (Joining Declaration) of Schedule Part 20 (Project Bank Account) |
| “Joining Request” | means a request by a Below Threshold Sub-Contractor to be added as a party to the Declaration of Trust for the purpose of facilitating the receiving of payments in connection with the Project through the Project Bank Account |  |
| “Key Sub-Contractor” | means [ l ] |  |
| “Key Sub-Contractor Collateral Agreements” | means the collateral agreement among the Authority, hubco [, the Contractor] and the Key Sub-Contractors in the form set out in Section 2 of Schedule Part 8 (Collateral Agreements) |  |
| “Law” |  | means:- - any applicable statute or proclamation or any delegated or subordinate legislation; - any enforceable community right within the meaning of section 2(1) of the European Communities Act 1972; - any applicable guidance, direction or determination with which the Authority and/or hubco is bound to comply to the extent that the same are published and publicly available or the existence or contents of them have been notified to hubco by the Authority; and - any applicable judgement of a relevant court of law which is a binding precedent in Scotland, in each case in force in Scotland |
| [“Liability Cap” |  | means [[ ]% of the Development Amount]] |
| “Liquidated Damages” |  | has the meaning given in Clause 14.2 |
| [“NHS” |  | means the National Health Service] |
| [“NHS Requirement” |  | means in relation to the Works, Health Building Notes and Health Technical Memoranda and such other requirements as are designated as NHS Requirements in the Authority’s Construction Requirements.] |
| “Non-PBA Sub-Contractor” | means a Sub-Contractor that is not a party to the Declaration of Trust |  |
| “Notice of Adjudication” |  | has the meaning given in paragraph 4.1 of Schedule Part 15 (Dispute Resolution Procedure) |
| “Operational Functionality” |  | means [TO BE DEFINED ON A PROJECT SPECIFIC BASIS] |
| “Outline Commissioning Programme” |  | means the programme setting out the standards, specifications, procedures and other requirements for the carrying out and completion of the commissioning activities of the parties set out in outline in Schedule Error: Reference source not found (Outline Commissioning Programme) |
| “Participant” |  | has the meaning given in the Territory Partnering Agreement |
| “Pay Less Allocation” | means (i) a Pay Less Payment Instruction; or, where hubco does not comply with Clause 27.11A; (ii) a Deemed Allocation |  |
| “Pay Less Notice” |  | has the meaning given in Clause 27.11 |
| “Pay Less Payment Instruction” | means a document prepared by hubco specifying the sum due to each PBA Beneficiary in respect of a sum specified as considered by the Authority to be due pursuant to a Pay Less Notice issued in accordance with Clause 27.11 |  |
| “Payment Certificate” |  | has the meaning given in Clause 27.10.3 |
| “Payment Certificate Due Date” |  | has the meaning given in Clause 27.10.3 |
| “Payment Certificate Final Date” |  | has the meaning given in Clause 27.10.4 |
| “Payment Instruction” | means a document prepared by hubco specifying the sum due to each PBA Beneficiary in respect of a sum due pursuant to Clause 27.5 |  |
| “PBA Beneficiary” | means a beneficiary under the Declaration of Trust |  |
| “PBA Beneficiary Amount” | means the amount due to a PBA Beneficiary pursuant to: (i) a Payment Instruction; or, where a Pay Less Notice has been issued, (ii) a Pay Less Allocation |  |
| “PBA Sub-Contractor” | means a Sub-Contractor that is a party to the Declaration of Trust |  |
| “Performance Guarantee(s)” |  | means the guarantees to hubco in respect of the Construction Contract [insert details of any other guarantees to be given] which, as at the date of this Agreement are in the Agreed Form |
| “Permitted Transfer Participant” | means each of the following: (a) a Participant which is a local authority (as defined in the Local Government etc. (Scotland) Act 1994); or (b) a Participant which is a health board established under section 2 of the National Health Service (Scotland) Act 1978; or (c) the Scottish Fire and Rescue Service constituted under the Police and Fire Reform (Scotland) Act 2012; or (d) the Police Service of Scotland constituted under the Police and Fire Reform (Scotland) Act 2012; or (e) the Scottish Ambulance Service constituted in terms of the Scottish Ambulance Service Board Order 1999/686; but specifically excluding their successors or assignees (the provisions of Section 2, Paragraphs 2.9 and 2.10 of Schedule Part 1 being specifically disapplied for the purposes of this definition) |  |
| “Physical Damage Policies” |  | means the policies of insurance referred to in paragraph 1 of Section 1 Schedule Part 12 (Insurance Requirements) |
| “Planning Approval” |  | means detailed planning consent for the Project listed in Part B in Section 1 in Schedule Part 5 (Construction Matters) |
| “Planning Permission” |  | means any planning permission, approval of reserved matters, listed building consent, conservation areas consent and/or other consent or approval reasonably required from time to time for construction of the Facilities (including without limitation for any Authority Works Variation and the Planning Approval) |
| “Plant” |  | means the plant and Equipment to be provided and/or maintained by hubco pursuant to this Agreement |
| “Post Completion Commissioning” |  | means, as appropriate, hubco’s Post Completion Commissioning and/or the Authority’s Post Completion Commissioning |
| “Programme” |  | means the programme set out in Schedule (The Programme) as revised and issued by hubco (or on its behalf) from time to time pursuant to Clause 14 (Programme and Dates for Completion) |
| “Prohibited Act” |  | has the meaning given in Clause 34 (Corrupt Gifts) |
| “Project” |  | means [COMPLETE ON A PROJECT SPECIFIC BASIS – MAY BE CROSS-REFERENCE TO RECITALS] |
| “Project Bank Account” | means the bank account provided by the Project Bank Account Provider in the joint names of the Authority, hubco and the Contractor in relation to the Project |  |
| “Project Bank Account Provider” | means [INSERT DESIGNATION OF BANK PROVIDING THE PROJECT BANK ACCOUNT] |  |
| “Project Data” | means:- - all Authority Design Data and hubco Design Data; - all drawings, reports, documents, plans, software, formulae, calculations and other data relating to the provision of the Works; and - any other materials, documents and or data acquired, brought into existence or used in relation to the Project Operations or this Agreement |  |
| “Project Development Fee” |  | means [correct figure reflecting terms of Territory Partnering Agreement to be inserted on a project by project basis] |
| “Project Documents” |  | means the Construction Contract, the Performance Guarantees [Authority to consider if there are any other project significant documents], all as the same may be amended or replaced from time to time |
| “Project Operations” |  | means the carrying out of the Works, the carrying out of hubco’s Pre-Completion Commissioning and hubco’s Post-Completion Commissioning and the performance of all other obligations of hubco under this Agreement from time to time |
| “Proposal for an Adverse Law” | means (a) in the case of a bill, the bill being introduced by the Government or receiving the support of the Government at its second reading in the first House of Parliament into which it is introduced or the bill passing a second reading in the first House of Parliament into which it is introduced; (b) in the case of a bill passing through Scottish Parliament, the bill being introduced by the Scottish Government or receiving the support of the Scottish Government at Stage 2 in the Scottish Parliament or the bill passing Stage 2 in the Scottish Parliament; (c) in the case of subordinate legislation, the proposed statutory instrument or order being laid before Parliament in draft; (d) in the case of a directive, regulation or decision of the European Union, its adoption; or (e) in the case of an administrative act as referred to in the definition of Adverse Law, any of the following prior or preparatory to the making of such an act: (i) the taking by the Authority, the Government, a minister of the Crown, or a department, agency, regulator or other public body official of any step in a process defined by Law for the making of such administrative acts, other than any early stages of such process (such as, without limitation, consultation or information gathering) following the completion of which further substantive steps remain in such a process before the making of such an administrative act can occur; or (ii) any communication from the Government, a minister of the Crown, or the department, agency or regulator or other public body or official responsible for making such administrative acts, to the effect that such an administrative act will be made |  |
| “Qualifying Sub-Contractor” | means a Sub-Contractor with a Sub-Contract Value of at least one per cent (1%) of the Development Amount |  |
| “Quality Plans” |  | means the Construction Quality Plan and, if applicable, the hubco Designed Portion Design Quality Plan, prepared in accordance with Section 8 of Schedule Part 5 (Construction Matters), as required to be implemented by hubco in accordance with Clause 20 (Quality Assurance) |
| "Range of Finishes" |  | has the meaning given in paragraph 1.2.3(a) of Schedule Part 7 (Review Procedure) |
| "Referral" |  | has the meaning given in paragraph 4.3 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Referral Notice" |  | has the meaning given in paragraph 4.3 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Referring Party" |  | has the meaning given in paragraph 4.1 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Reinstatement Outline" |  | has the meaning given in Clause 39.20.1 |
| "Reinstatement Plan" |  | has the meaning given in Clause 39.20.5 |
| "Reinstatement Works" |  | has the meaning given in Clause 39.20.1 |
| "Related Adjudication" |  | has the meaning given in paragraph 4.11 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Related Adjudicator" |  | has the meaning given in paragraph 4.11 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Related Agreements" |  | has the meaning given in paragraph 4.11 of Schedule Part 15 (Dispute Resolution Procedure) |
| “Relevant Authority” | means any court with the relevant jurisdiction and any local, national or supra-national agency, inspectorate, minister, ministry, official or public or statutory person of the government of the United Kingdom, or of the European Union, (or of the Scottish Government or the Scottish Parliament) |  |
| "Relevant Incident" |  | has the meaning given in Clause 39.20 |
| “Relevant Month” | means each calendar month from the Commencement Date until (and including) the calendar month after the calendar month in which the Certificate of Completion is issued |  |
| "Relief Events" |  | has the meaning given to it in Clause 23 (Relief Events) |
| "Request for Information" |  | has the meaning set out in the FOI(S)A or the Environmental Information (Scotland) Regulations as relevant (where the meaning set out for the term "request" shall apply) |
| "Reserved Rights" |  | means the rights referred to in Section 2 of Schedule Part 4 (Land Matters) |
| "Responding Party" |  | has the meaning given in paragraph 4.3 of Schedule Part 15 (Dispute Resolution Procedure) |
| "Retention" |  | has the meaning given to in Clause 27.6.2 |
| "Review Procedure" |  | means the procedure set out in Schedule Part 7 (Review Procedure) |
| "Reviewable Design Data" |  | means the hubco Design Data listed at Section 5 of Schedule Part 5 (Construction Matters) relating to the hubco Designed Portion |
| "Schedule of Defects" |  | has the meaning given in Clause 17.2 |
| “Scottish Futures Trust” |  | means Scottish Futures Trust Limited (Company Number SC348382), having its registered office at 1st Floor, 11 – 15 Thistle Street, Edinburgh EH2 1DF |
| "Sensitive Information" |  | has the meaning given in Clause 46.12 (Confidentiality) |
| "Shareholder(s)" |  | means any entity holding an equity stake in hubco from time to time |
| "Site" |  | means the land made available to hubco for the Project and outlined in red on [insert details of relevant plan] |
| "Site Conditions" |  | means the physical condition of the Site including (but not limited to) climatic, hydrological, hydrogeological, ecological, environmental, geotechnical and archaeological conditions |
| "Snagging Matters" |  | means minor items of outstanding work (including in relation to landscaping) which would not materially impair the Authority's use and enjoyment of the Facilities or the carrying out by the Authority or a Community Services Provider of the Community Services |
| "Snagging Notice" |  | means the notice to be issued by the Authority's Representative in accordance with Clause 16.12 (Completion Certificate) |
| "Sub-Contract" |  | means any contract entered into, by or between hubco, the Contractor and other third parties, in relation to any aspect of the Works |
| “Sub-Contract Value” | means the original contract sum of a Sub-Contract |  |
| "Sub-Contractor" |  | means any third party (including the Contractor) who enters into any Sub-Contract |
| "Subsidiary" |  | has the meaning given to it in Section 1159 of the Companies Act 2006 |
| "Termination Date" |  | means the date on which termination of this Agreement takes effect in accordance with its terms |
| "Territory Partnering Agreement" or "TPA" |  | means the agreement entered into between hubco and the Participants dated [INSERT DATE OF TPA] |
| "Title Conditions" |  | means the Title Conditions set out in Section 1 of Schedule Part 4 (Land Matters) |
| "Unreasonable Act" |  | means any act or omission which is contrary to any reasonable instruction, guidance or rules for the operation or management of the Facilities |
| "Variation" |  | has the meaning given in Schedule Part 13 (Variation Procedure) |
| “Variation Confirmation” |  | has the meaning given in Schedule Part 13 (Variation Procedure) |
| "Variation Enquiry" |  | has the meaning given in Schedule Part 13 (Variation Procedure) |
| "Variation Procedure" |  | means the procedure set out in Schedule Part 13 (Variation Procedure) |
| "VAT" |  | means value added tax at the rate prevailing at the time of the relevant supply charged in accordance with the provisions of the Value Added Tax Act 1994 |
| "VAT Sum" |  | has the meaning given in Clause 28 (VAT) |
| "Vitiating Act" |  | has the meaning given in Endorsement 2, Section 3 of Schedule Part 12 |
| "Works" |  | means the construction, testing, commissioning and completion of the Facilities (including any temporary works) [and the installation of Group 1 Equipment] to be performed by hubco in accordance with this Agreement (as varied, amended or supplemented from time to time in accordance with this Agreement) |

- SECTION 2

- Interpretation

This Agreement shall be interpreted according to the following provisions, unless the context requires a different meaning:-

  - The headings and marginal notes and references to them in this Agreement shall be deemed not to be part of this Agreement and shall not be taken into consideration in the interpretation of this Agreement.

  - Except where the context expressly requires otherwise, references to Clauses, Sub-clauses, paragraphs, sub-paragraphs, parts, Schedule Parts and Schedule are references to Clauses, Sub-clauses, paragraphs, sub-paragraphs and parts of and Schedule Parts and the Schedule to this Agreement and references to Sections, Appendices and Attachments (if any) are references to Sections, Appendices and Attachments to or contained in this Agreement.

  - The Schedule to this Agreement and attachments (if any) are integral parts of this Agreement and a reference to this Agreement includes a reference to the Schedule and attachments (if any).

  - Words importing persons shall, where the context so requires or admits, include individuals, firms, partnerships, trusts, corporations, governments, governmental bodies, authorities, agencies, unincorporated bodies of persons or associations and any organisations having legal capacity.

  - Where the context so requires words importing the singular only also include the plural and vice versa and words importing the masculine shall be construed as including the feminine or the neuter or vice versa.

  - The language of this Agreement is English.  All correspondence, notices, drawings, Authority Design Data, hubco Design Data, test reports, certificates, specifications and information shall be in English.  All operating and maintenance instructions, name plates, identification labels, instructions and notices to the public and staff and all other written, printed or electronically readable matter required in accordance with, or for purposes envisaged by, this Agreement shall be in English.

  - Save where stated to the contrary, references to any agreement or document include (subject to all relevant approvals and any other provisions of this Agreement concerning amendments to agreements or documents) a reference to that agreement or document as amended, supplemented, substituted, novated or assigned.

  - References to any Law are to be construed as references to that Law as from time to time amended or to any Law from time to time replacing, extending, consolidating or amending the same.

  - Without prejudice to Clause 43.1, references to a public organisation (other than the Authority) shall be deemed to include a reference to any successor to such public organisation or any organisation or entity which has taken over either or both the relevant functions and relevant responsibilities of such public organisation.

  - Without prejudice to Clause 43.1, references to other persons (other than the Authority) shall include their successors and assignees.

  - References to a deliberate act or omission of the Authority or any Authority Party shall be construed having regard to the interactive nature of the activities of the Authority and of hubco and the expression shall exclude acts or omissions which were within the contemplation of the parties or which were otherwise provided for in this Agreement.

  - The words in this Agreement shall bear their natural meaning.  The parties have had the opportunity to take legal advice on this Agreement and no term shall, therefore, be construed contra proferentem.

  - Reference to "parties" means the parties to this Agreement and references to "a party" mean one of the parties to this Agreement.

  - In construing this Agreement, the rule known as the ejusdem generis rule shall not apply nor shall any similar rule or approach to the construction of this Agreement and accordingly general words introduced or followed by the word "other" or "including" or "in particular" shall not be given a restrictive meaning because they are followed or preceded (as the case may be) by particular examples intended to fall within the meaning of the general words.

  - All of hubco's obligations, duties and responsibilities shall be construed as separate obligations, duties and responsibilities owed to the Authority and to be performed at hubco's own cost and expense.

  - Reference to a document being in the Agreed Form is a reference to the form of the relevant document (or, where appropriate, the form of relevant document on disc) agreed between the parties and for the purpose of identification either (i) initialled or signed by each of them or on their behalf or (ii) entered into on or around the Execution Date.

  - Where this Agreement states that an obligation shall be performed "no later than" or "within" or "by" a stipulated date or event which is a prescribed number of Business Days after a stipulated date or event the latest time for performance shall be noon on the last Business Day for performance of the obligations concerned.

  - Words in parenthesis or italics appearing after a Clause reference or reference to a Schedule Part are inserted for ease of reference only. If there is any discrepancy between the Clause reference and the word appearing in parenthesis and italics after the Clause reference, the Clause reference shall prevail.

  - Where this Agreement states that an obligation shall be performed "no later than" or "by" a prescribed number of Business Days before a base date or "by" a date which is a prescribed number of Business Days before a base date, the latest time for performance shall be [5pm] on the last Business Day for performance of the obligations concerned.

- COMPLETION DOCUMENTS

- Documents to be delivered by hubco

Unless an original document is specifically requested, a copy (certified by an officer of hubco as being a true copy) of each of the following documents is to be delivered by hubco to the Authority in accordance with Clause 2.1 (Execution and Delivery of Documents) of this Agreement:

- The Consents and other authorisations, licences, permits, and approvals listed below:

[PROJECT SPECIFIC ITEMS TO BE LISTED].

- The Construction Contract, the Performance Guarantees and the Collateral Agreements (other than the Key Sub Contractor Collateral Agreements) executed by the parties to such agreements.

- Not used.

- Extracts from the minutes of the meeting of the board of directors (certified as true and accurate by a director of the relevant company) of hubco and each of the other parties to the documents listed in Section 1 (Documents to be Delivered by hubco) of Schedule Part 2 (Completion Documents), at which resolutions were passed approving the execution, delivery and performance of each relevant document to which such person is expressed to be a party and in each case authorising a named person or persons to execute and deliver each such document and any other documents to be delivered by it pursuant to it.

- A certificate of a director of each of the companies referred to in paragraph 4 above setting out the names and specimen signatures of the person or persons named in the relevant certified extract.

- The insurance broker’s letter of undertaking in the form set out in Section 4 of Schedule Part 12, duly executed, evidence of the insurances required in accordance with Clause 39 (Insurances) having been taken out by hubco and that the policies comply with the requirements of this Agreement.

- Not used.

- Evidence that the Insurance Proceeds Account has been opened.

- [AUTHORITY TO INDICATE OTHER PROJECT SPECIFIC DOCUMENTS, INCLUDING ANY OTHER PROJECT DOCUMENT, PLANNING AND PROPERTY RELATED AGREEMENTS]

- An original duly executed version of this Agreement.

- [An original of the Declaration of Trust duly executed by hubco and the Contractor.]

- Documents to be delivered by the Authority

The Authority shall deliver to hubco the following documents:

- A certified copy of the resolution of the Authority approving the execution, delivery and performance of the documents referred to in paragraphs 2 and 10 of Section 1 (Documents to be Delivered by hubco) above (to which the Authority is a party) and in each case authorising a named person or persons to execute and deliver each such document and any documents to be delivered pursuant hereto.

- A certificate of the relevant officer of the Authority setting out the names and specimen signatures of the person or persons named in the resolution of the Authority referred to in paragraph 1 of this Section 2 (Documents to be delivered by the Authority).

- Evidence that the Authority has agreed to be treated as the only "client" for the Project for the purposes of the CDM Regulations.

- [Evidence that the Project Bank Account has been opened.]

- Copy of a letter from the relevant officer of the Authority consenting to the subcontracting of Works to specified sub-contractors.

- [ANY OTHER NECESSARY APPROVAL DOCUMENTS ACCORDING TO CIRCUMSTANCES]

- [INSERT CONSENTS AND ANY OTHER DOCUMENTS TO BE OBTAINED BY THE AUTHORITY]

- key works personnel

[TO BE COMPLETED ON A PROJECT SPECIFIC BASIS]

- LAND MATTERS

- TITLE CONDITIONS

[TO BE INSERTED]

- RESERVED RIGHTS

[TO BE INSERTED]

- ANCILLARY RIGHTS

[TO BE INSERTED]

- CONSTRUCTION MATTERS

- Planning/Consents

[The contents of this Schedule Part 5 are project specific and should be prepared by each Authority on a project basis].

- PART A – consents obtained

PART B – HUBCO CONSENTS

PART C – AUTHORITY PLANNING CONDITIONS

- Safety During Construction

- [In this Section 2 (Safety During Construction) of Schedule Part 5 (Construction Matters) and wherever used elsewhere in this Agreement:

  - "CDM Regulations" means the Construction (Design and Management) Regulations 2015 (and "CDM Regulation" shall be construed accordingly); and

  - "the client", “the designer” and "the principal contractor" shall have the same meanings as are ascribed to them in the CDM Regulations.

- In so far as not already done, within five (5) Business Days of the date of execution of this Agreement, the Authority shall make and serve on hubco a notice in writing pursuant to CDM Regulation 4(8) that the Authority agrees to be treated as the only client in relation to the Works for the purposes of the CDM Regulations. Notwithstanding the Authority agreeing in writing to be the only client pursuant to CDM Regulation 4(8), hubco will comply with its remaining duties as set out in CDM Regulation 4(8).  During the term of this Agreement, the Authority shall not, and shall not seek to, withdraw, terminate or in any manner derogate from its agreement that it will act as, and its acceptance of its responsibilities as, the client in relation to the Works for all the purposes of the CDM Regulations.  hubco will endorse its consent, in writing, to such agreement on the said notice and return it to the Authority within five (5) Business Days of receipt.

- The Authority warrants that it has the skills, knowledge, organisational capability and experience to, and shall, observe, perform and discharge or shall procure the observance, performance and discharge of:

  - all the obligations, requirements and duties of the client arising under the CDM Regulations in connection with the Works; and

  - all obligations incumbent on the client under any Code of Practice or Guidance for the time being approved by the Health and Safety Commission pursuant to the Health and Safety at Work etc. Act 1974 or issued in connection with the CDM Regulations.

- The Authority hereby appoints in writing, and hubco agrees to act, as the principal contractor under the CDM Regulations in connection with the Works.

- hubco warrants that it has the skills, knowledge, organisational capability and experience to, and shall, observe, perform and discharge or shall procure the observance, performance and discharge of:

  - all the obligations, requirements and duties of the principal contractor, and a designer, arising under the CDM Regulations in connection with the Works; and

  - all obligations incumbent on the principal contractor, and a designer, under any Code of Practice or Guidance for the time being approved by the Health and Safety Commission pursuant to the Health and Safety at Work etc. Act 1974 or issued in connection with the CDM Regulations.

- hubco shall provide to the Authority's Representative:

  - in a substantially complete form on the Actual Completion Date; and

  - in final form within eight (8) weeks  of the Actual Completion Date,

one (1) electronic copy (on computer disk, tape or other format) of the revised and updated construction phase plan (current at that date) prepared pursuant to the CDM Regulations in relation to the Works and electronic or paper copies of every amendment or update made to such plan.]

- Authority's Construction Requirements

- hubco's Proposals

- Reviewable Design Data

- NOT USED

- Thermal and energy efficiency testing procedure

[INSERT PROCEDURE HERE]

- Quality Plan[s] (construction quality plan [and hubco designed portion design quality plan])

SECTION 9 - BIM PROTOCOL

      - DEFINITIONS

In this Section 9 (BIM Protocol) of Schedule Part 5 and elsewhere in this Agreement (save where Schedule Part 1 (Definitions and Interpretation) provides to the contrary) the following words and expressions shall have the following meanings:

- “Federated Model” means a Model consisting of connected but distinct individual Models;

- “Information Management Role” means a role in connection with the Project which includes, inter alia, the establishment and management of the processes, protocols and procedures set out in the Information Requirements;

- “Information Manager” means the person appointed, initially by the Authority, to perform the Information Management Role;

- “Information Requirements” means the document attached at Appendix 2 setting out the way in which Models shall be produced, delivered and used on the Project, including any processes, protocols and procedures referred to therein;

- “Level of Definition” means the level of detail and level of information required for a Model as specified in Appendix 1;

- “Material” means all information in any electronic medium prepared by or on behalf of hubco comprised in:

  - the Specified Models; and,

  - the Federated Models, to the extent that these comprise Specified Models or to the extent that hubco owns any additional rights in any Federated Model, excluding any material forming part thereof which is provided to hubco by or on behalf of the Authority;

- “Model” means a digital representation of part of the physical and/or functional characteristics of the Project;

- “Model Production and Delivery Table” means the table attached at Appendix 1 specifying the subject matter of each Model, the person who is to produce and deliver each Model (described in the table as “Model Originator”) at each Stage and the Level of Definition for each Model at each Stage;

- “Other Agreement” means any agreement entered into between the Authority and an Other Project Team Member in relation to the Project;

- “Other Project Team Member” means any person having responsibilities in relation to the production, delivery and/or use of Models and appointed by the Authority in relation to the Project, excluding hubco;

- “Permitted Purpose” means a purpose related to the Project (or the construction, operation and maintenance of the Project) which is consistent with the applicable Level of Definition of the relevant Model (including a Model forming part of a Federated Model) and the purpose for which the relevant Model was prepared;

- “Project Team Models” means any Models which Other Project Team Members produce and deliver as specified in the Model Production and Delivery Table and any Federated Models (or any part thereof) produced and delivered by Other Project Team Members;

- “Protocol” means this building information modelling protocol including Appendices 1 and 2;

- “Specified Models” means the Model or Models which hubco is to produce and deliver as specified in the Model Production and Delivery Table; and

- “Stage” shall have the meaning stated in Appendix 1.

      - PRIORITY OF CONTRACT DOCUMENTS

        - This Protocol forms part of this Agreement. In the event of a conflict or inconsistency between the terms of this Protocol and any other documents contained in and/or forming part of this Agreement, except where the Protocol states otherwise, the terms of this Protocol shall prevail.

        - In the event of any conflict or inconsistency between a Model prepared and delivered in accordance with this Protocol and any document or information extracted from such Model, except where the Information Requirements state otherwise, the Model shall prevail.

      - OBLIGATIONS OF THE AUTHORITY

The Authority shall:

        - arrange for a protocol in substantially the same terms as this Protocol and for the obligations set out herein to be incorporated into all Other Agreements; and

        - save to the extent that such obligations are within the scope of hubco’s obligations under any other part of this Agreement:

          - ensure that until the end of the Project the Information Requirements and the Model Production and Delivery Table are reviewed and updated at each Stage; and

          - ensure that the appointment of the Information Manager shall be changed or renewed as necessary to ensure that there is at all times until the end of the Project a person performing the Information Management Role.

      - OBLIGATIONS OF HUBCO

hubco shall:

        - produce the Specified Models (excluding any material forming part of the same which is provided to hubco by or on behalf of the Authority) to the Level of Definition specified in the Model Production and Delivery Table using the level of skill and care required under this Agreement; and

        - subject to events outside its reasonable control, (including the acts or omissions of the Authority, Other Project Team Members and any third party but excluding hubco’s sub-contractors), use reasonable endeavours to:

          - deliver the Specified Models at the Level of Definition specified in the Model Production and Delivery Table at the Stage specified therein and in accordance with the Information Requirements;

          - use the Project Team Models in accordance with any procedures therefor in the Information Requirements; and

          - comply with the Information Requirements; and

        - arrange for this Protocol to be incorporated into any sub-contracts that it enters into in relation to the Project to the extent required to enable hubco to comply with this Protocol.

      - ELECTRONIC DATA EXCHANGE

        - Without prejudice to hubco’s obligations under this Protocol and this Agreement, hubco does not warrant, expressly or impliedly, the integrity of any electronic data delivered in accordance with this Protocol.

        - hubco shall have no liability to the Authority in connection with any corruption or any unintended amendment, modification or alteration of the electronic data in a specified Model which occurs after it has been transmitted by hubco, save where such corruption, amendment, modification or alteration is a result of hubco’s failure to comply with this Protocol.

      - USE OF MODELS

        - Project Models and Data

          - Each party shall make available to the other party free of charge (and hereby irrevocably licences the other party to use) all Models and Project Data (for which it is responsible) as per the requirements of the Information Requirements and each party shall ensure that it obtains all necessary licences, permissions and consents to ensure that it can make the Project Models and Project Data available to the other party on these terms, for such purposes as the other party at its sole discretion may require, and in this paragraph "use" shall include the acts of copying, modifying, adapting and translating the material in question and/or incorporating them with other materials and the granting of sub-licences and the term "the right to use" shall be construed accordingly.  Neither party nor any hubco Party or Authority Party shall be liable to the other party in respect of use by or on behalf of the first party of the Project Data other than in relation to the Project. The licence given in this paragraph 6.1.1 shall carry the right to grant sub-licences.

Permitted Purpose of the Models: the right to use and amend the Project Team Models and Federated models during the in-use stage to reflect adaption, maintenance and any future extension to the Facilities.

          - The Authority owns:

            - any material forming part of the Specified Models which is provided to hubco by or on behalf of the Authority;

            - the Project Team Models (or any part thereof);

            - any Federated Model (or any part thereof);

            - any proprietary work contained in the same

        - Intellectual Property Rights

          - Each party

            - grants to the other party, free of charge, an irrevocable, non-exclusive and transferable (but only to any assignee or transferee of any rights or benefits under this Agreement or upon or at any time following termination of this Agreement) licence (carrying the right to grant sub licences) to use the Intellectual Property Rights which are or become vested in the first party; and

            - shall, where any Intellectual Property Rights (for which it is responsible)  are or become vested in a third party, use all reasonable endeavours to procure the grant of a like licence to that referred to in paragraph 6.2.1 above to the other party,

in both cases, for such purposes as the other party may at its sole discretion require.

Each party shall use all reasonable endeavours to ensure that any Intellectual Property Rights (for which it is responsible) created, brought into existence or acquired during the term of this Agreement vest, and remain vested throughout the term of this Agreement, in it and each party shall enter into appropriate agreements with any hubco Party or Authority Party (as applicable) (or other third parties) that may create or bring into existence, or from which it may acquire, any Intellectual Property Rights.

        - Maintenance of models and data

          - To the extent that any of the models, data, materials and documents referred to in this paragraph are generated by or maintained on a computer or similar system, each party shall use all reasonable endeavours to procure for the benefit of the other party, at no charge or at the lowest reasonable fee, the grant of a licence or sub licence for any relevant software to enable the other party or its nominee to access and otherwise use (subject to the payment by the other party of the relevant fee, if any) such data (for which the relevant party is responsible) for such purposes as the other party may at its sole discretion require.  As an alternative, each party may provide such models, data, materials or documents in a format which may be read by software generally available in the market at the relevant time or in hard copy format.

          - Each party shall ensure the backup and storage in safe custody of the models, data, materials and documents for which it is responsible in accordance with Good Industry Practice.  Without prejudice to this obligation, each party shall submit to the Authority’s Representative or hubco’s Representative (as applicable) for approval its proposals for the back-up and storage in safe custody of such models, data, materials and documents and the other party shall be entitled to object if the same is not in accordance with Good Industry Practice.  Each party shall comply, and shall cause all hubco Parties or Authority Parties (as applicable) to comply, with all procedures to which the Authority’s Representative or hubco’s Representative (as applicable) has given its approval.  Each party may vary its procedures for such back-up and storage subject to submitting its proposals for change to the Authority’s Representative or hubco’s Representative (as applicable), who shall be entitled to object on the basis set out above.

        - Claims

          - Where a claim or proceeding is made or brought against a party which arises out of the infringement of any rights in or to any Intellectual Property (as a consequence of the use of Project Data for which the other party is responsible) or because the use of any materials, Plant, machinery or Equipment (specified by the other party) in connection with the Works infringes any rights in or to any Intellectual Property of a third party then, unless such infringement has arisen out of the use of any Intellectual Property by or on behalf of the party suffering the claim or proceeding otherwise than in accordance with the terms of this Agreement [or in respect of a use of the Intellectual Property for a purpose  other than that for which it was produced], the other party shall indemnify the party suffering the claim or proceeding at all times from and against all such claims and proceedings and the provisions of Schedule Part 15 shall apply.

      - LIABILITY IN RESPECT OF A MODEL

        - The Authority and hubco agree that any provisions in this Agreement concerning the use of the Material, the Federated Models, the Project Team Models, any material forming part of the Specified Models which is provided to hubco by or on behalf of the Authority and any proprietary work contained therein shall be varied to the extent necessary to give effect to paragraphs 7.2 and 7.3 but if there are no such provisions paragraphs 7.2 and 7.3 shall apply.

        - hubco shall have no liability to the Authority arising out of any modification or amendment to, or any transmission, copying or use of the Material, or any proprietary work contained therein, by the Authority, an Other Project Team Member, or any other third party, other than that permitted by paragraph 6.3.

        - The Authority shall have no liability to hubco arising out of any modification or amendment to, or any transmission, copying or use of the Project Team Models, or any material forming part of the Specified Models which is provided to hubco by or on behalf by the Authority, or any Federated Models, or any proprietary work contained in the same, sublicensed or licensed by the Authority.

      - TERMINATION

Paragraphs 1, 2, 3, 5, 6 and 7 of this Protocol shall continue to apply following termination of hubco’s employment under this Agreement.

APPENDIX 1

The Model Production and Delivery Table showing the model requirements and the levels of definition at each of the Stages is appended overleaf.

[Insert the Model Production and Delivery Table]

APPENDIX 2

Information Requirements:

      - Standards

It is a requirement of this Agreement that BIM Level 2 Maturity be achieved as defined by BSI.

The following standards shall apply:

| Title |  | Collaborative working | Design Management | Library Objects | Briefing | Information requirements | Data Exchange /COBie | Security | Levels of Definition |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| BIM Level 1 | BS 1192:2007 + A2:2016 | ● |  |  |  |  |  |  |  |
|  | BS 7000-4:2013 |  | ● |  |  |  |  |  |  |
|  | BS 8541:2:2011 |  |  | ● |  |  |  |  |  |
| BIM Level 2 | BS 8536-1:2015 |  |  |  | ● |  |  |  |  |
|  | PAS 1192-2:2013 |  |  |  |  | ● |  |  | ● |
|  | PAS 1192-3:2014 |  |  |  |  | ● |  |  |  |
|  | BS 1192-4:2014 |  |  |  |  |  | ● |  |  |

      - Parties

The role of Information Manager shall be performed by [ l ] during Stage 2 until project completion and handover.

      - Information Requirements

The Information Requirements for the Project are defined in “[ l ] Document reference: [ l ]” which is appended to this Protocol.

- THE PROGRAMME

[The contents of this Schedule Error: Reference source not found are project specific and need to be prepared by hubco and agreed with the Authority.]

- REVIEW PROCEDURE

- REVIEW

  - The provisions of this Schedule Part 7 (Review Procedure) shall apply whenever any item, document or course of action is required to be reviewed, approved or otherwise processed in accordance with Schedule Part 7 (Review Procedure).

  - Subject to any express provision of this Agreement, the manner, form and timing of any submission to be made by hubco to the Authority's Representative for review under this Schedule Part 7 (Review Procedure) shall be a matter for hubco to determine.  Each submission under the Review Procedure shall be accompanied by a copy of the proposed document to be reviewed (including, where applicable, any Reviewable Design Data) or a statement of the proposed course of action (the entire contents of a submission being referred to in this Schedule Part 7 (Review Procedure) as a "Submitted Item").  In relation to each Submitted Item, the following procedure shall apply:

    - as soon as possible and, if the Submitted Item comprises:

      - an item of Reviewable Design Data;

      - a revised Programme submitted pursuant to Clause 14 (Programme and Dates for Completion); or

      - a document or proposed course of action submitted in the case of (an emergency),

within [     ] Business Days of the date of receipt of a submission (or re-submission, as the case may be) of the Submitted Item to the Authority's Representative (or such other period as the parties may agree), the Authority's Representative shall return one copy of the relevant Submitted Item to hubco endorsed "no comment" or (subject to and in accordance with paragraph 3 (Grounds for Objection)) "comments" as appropriate; and

    - if the Authority's Representative fails to return a copy of any Submitted Item (including any re-submitted Submitted Item) duly endorsed in accordance with paragraph 1.2.1, within [      ] Business Days (or within such other period as the parties may agree in writing) of the date of its submission to the Authority's Representative, then the Authority's Representative shall be deemed to have returned the Submitted Item to hubco endorsed "no comment" (and, in the case of Reviewable Design Data, endorsed "Level A - no comment"); and

    - in relation to the aspect of each Finish relating to the hubco Designed Portion identified in the table below:

      - hubco shall submit to the Authority a range or selection of finishes (“Range of Finishes”) no later than the relevant Finishes Proposal Date;

      - the Authority's Representative shall by the relevant Finishes Selection Date notify hubco of its selection for the relevant Finish; and

      - if no selection of a Finish has been made by the Authority’s Representative and notified to hubco in accordance with paragraph 1.2.3(b) by the end of the relevant Finish Selection Date, hubco shall be entitled to make a selection from the Range of Finishes submitted in accordance with paragraph 1.2.3(a). After the end of the relevant Finish Selection Date, should the Authority wish to vary any selection previously made by hubco or by the Authority, such variation shall be effected as a Variation in accordance with Schedule Part 13 (Variation Procedure).

Table A

| Finishes | Aspects | Finishes Proposal Date | Finishes Selection Date |
| --- | --- | --- | --- |
| External finishes (roof, windows and external elevations) | Colour and material |  |  |
| Wall finishes | Colour |  |  |
| Floor finishes | Colour and type |  |  |
| Ironmongery | Style and colour |  |  |
| Tapware | Style and content |  |  |
| Main public light fittings | Specification and style |  |  |
| External signage | Size, style, colour and location |  |  |
| Internal signage | Size, style, colour and location |  |  |
| Light switches and sockets | Style and colour |  |  |
| Hard landscaping | Colour and material |  |  |
| [Others to be inserted on a project specific basis by the Authority] |  |  |  |

  - If the Authority's Representative raises comments on any Submitted Item in accordance with paragraph 3 (Grounds for Objection) he shall state the ground upon which such comments are based and the evidence or other information necessary to substantiate that ground.  To the extent that the Authority's Representative comments on a Submitted Item other than on the basis set out in this Schedule Part 7 (Review Procedure), or fails to comply with the provisions of this paragraph, hubco may, in its discretion, either:

    - request written clarification of the basis for such comments and, if clarification is not received within [     ] Business Days of such request by hubco, refer the matter for determination in accordance with Schedule Part 15 (Dispute Resolution Procedure); or

    - in the case of a Submitted Item comprising Reviewable Design Data only, at its own risk, and without prejudice to Clause 12 (The Design, Construction and Commissioning Process), proceed with further design or construction disregarding such comments pending the outcome of any reference to the Dispute Resolution Procedure that may be made by either party.

- Further Information

  - hubco shall submit any further or other information, data and documents that the Authority's Representative reasonably requires in order to determine whether he has a basis for raising comments or making objections to any Submitted Item in accordance with this Schedule Part 7 (Review Procedure).  If hubco does not submit any such information, data and documents, the Authority's Representative shall be entitled to:

    - comment on the Submitted Item on the basis of the information, data and documents which have been provided; or

    - object to the Submitted Item on the grounds that insufficient information, data and documents have been provided to enable the Authority's Representative to determine whether he has a legitimate basis for commenting or objecting in accordance with this Schedule Part 7 (Review Procedure).

- Grounds of Objection

The expression "raise comments" in this paragraph shall be construed to mean "raise comments or make objections" unless the contrary appears from the context.  The Authority's Representative may raise comments in relation to any Submitted Item on the grounds set out in paragraph 2 (Further Information) above or on the ground that the Submitted Item would (on the balance of probabilities) breach any Law but otherwise may raise comments in relation to a Submitted Item only as follows:

  - in relation to any Submitted Item if:

    - hubco's ability to perform its obligations under this Agreement would (on the balance of probabilities) be adversely affected by the implementation of the Submitted Item; or

    - the implementation of the Submitted Item would (on the balance of probabilities) adversely affect any right of the Authority under this Agreement or its ability to enforce any such right;

  - in relation to any Submitted Item submitted pursuant to Clause 4.1 if:

    - the Authority's ability to perform its obligations under this Agreement would be adversely affected by the proposed course of action;

    - the Authority's or any Community Service Provider's ability to use and/or provide the relevant Community Services at the Facilities or to carry out any of its statutory functions would (on the balance of probabilities) be adversely affected by the proposed course of action;

    - the proposed course of action would be likely to result in an increase to the Authority's liabilities or potential or contingent liabilities under this Agreement;

    - the proposed course of action would adversely affect any right of the Authority under this Agreement or its ability to enforce any such right; or

    - hubco's ability to perform its obligations under this Agreement would be materially adversely affected by the proposed course of action;

  - in relation to Reviewable Design Data submitted pursuant to Clause 12.6:

    - which does not comprise 1:50 scale Room Layout Drawings the Authority's Representative may raise comments, subject to and in accordance with paragraph 4 (Effect of Review) on the ground that the Submitted Item is not in accordance with:

      - the Authority's Construction Requirements; and/or

      - hubco's Proposals;

    - which comprises a 1:50 scale Room Layout Drawing in respect of which there is a corresponding generic 1:50 scale Room Layout Drawing for the relevant room type (which has previously been reviewed and commented upon by the Authority's Representative in accordance with this Schedule Part 7 (Review Procedure)), the Authority's Representative may raise comments, subject to and in accordance with paragraph 4 (Effect of Review), on the ground that the Submitted Item does not conform to the generic 1:50 scale Room Layout Drawing; and

    - which comprises a 1:50 scale Room Layout Drawing in respect of which there is no corresponding generic 1:50 scale Room Layout Drawing for the relevant room type (which has previously been reviewed and commented upon by the Authority's Representative in accordance with this Schedule Part 7 (Review Procedure)), the Authority's Representative may raise comments, subject to and in accordance with paragraph 4 (Effect of Review), on the grounds that the Submitted Item:

      - is not in accordance with the Authority's Construction Requirements (insofar as they relate to the hubco Designed Portion) and/or hubco's Proposals (insofar as they relate to the hubco Designed Portion); or

      - is inconsistent with the guidance contained in any current [NHS Requirement] which is applicable to a room of that function provided that such guidance has not been superseded by and is not inconsistent with any other provisions of the Authority's Construction Requirements (including any existing Approved RDD Item).

  - in relation to a proposal to amend hubco’s Proposal (insofar as they relate to the hubco Designed Portion), to rectify (part of) the hubco Designed Portin submitted pursuant to Clause 12 on the gounds that following the amendment and rectification proposed:-

    - hubco’s Proposals (insofar as they relate to the hubco Designed Portion) would not comply with the Authority’s Construction Requirements (insofar as they relate to the hubco Designed Portion); and/or

    - the structural, mechanical and/or electrical performance of the hubco Designed Proportion would not be of equivalent standard of performance to that set out in hubco’s Proposal (insofar as they relate to the hubco Designed Portion) prior to their amendment or rectification (for the purposes of this comparison disregarding the fault which required the amendment or rectification to be made).

  - in relation to Finishes relating to the hubco Designed Portion:

    - which have the effect of making a selection from the Range of Finishes (or any alternative range or selection of Finishes submitted by hubco to the Authority's Representative) pursuant to Clause 12.6; or

    - where the Submitted Item does not comply with the relevant provisions of the Authority's Construction Requirements (insofar as they relate to the hubco Designed Portion) and/or hubco's Proposals (insofar as they relate to the hubco Designed Portion);

  - in relation to the submission of any revised Programme pursuant to Clause 14 (Programme and Dates for Completion) on the ground that the revised Programme would not (on the balance of probabilities) enable the Works to be completed by the Completion Date;

  - in relation to the submission of any Quality Plan or part of a Quality Plan or any changes to any Quality Plan pursuant to Clause 20.4 or Clause 20.7 or any quality manual or procedure in accordance with Clause 20.9 (Quality Manuals and Procedures), on the grounds that such Quality Plans, or parts of or changes to such Quality Plans, quality manuals or procedures, or the quality management systems which they reflect, would not comply with in the case of the hubco Designed Portion Design Quality Plan (if applicable) and the Construction Quality Plan referred to in Clause 20 (Quality Assurance), the requirements referred to in Section 8 of Schedule Part 5 (Construction Matters).

- Effect of Review

  - Any Submitted Item which is returned or deemed to have been returned by the Authority's Representative endorsed "no comment" (and in the case of Reviewable Design Data, endorsed "Level A - no comment") shall be complied with or implemented (as the case may be) by hubco.

  - In the case of any Submitted Item other than Reviewable Design Data, if the Authority's Representative returns the Submitted Item to hubco endorsed "comments", hubco shall comply with such Submitted Item after amendment in accordance with the comments unless hubco disputes that any such comment is on grounds permitted by this Agreement, in which case hubco or the Authority's Representative may refer the matter for determination in accordance with Schedule Part 15 (Dispute Resolution Procedure) and hubco shall not act on the Submitted Item until such matter is so determined or otherwise agreed.

  - In the case of a Submitted Item comprising Reviewable Design Data, if the Authority's Representative returns the Submitted Item endorsed other than "Level A - no comment", hubco shall:

    - where the Authority's Representative has endorsed the Submitted Item "Level B - proceed subject to amendment as noted", either proceed to construct or proceed to the next level of design of the part of the Works to which the Submitted Item relates but take into account any amendments required by the Authority's Representative in his comments;

    - where the Authority's Representative has endorsed the Submitted Item "Level C - subject to amendment as noted" not act upon the Submitted Item, amend the Submitted Item in accordance with the Authority's Representative's comments and re-submit the same to the Authority's Representative in accordance with paragraph 4.4; and

    - where the Authority's Representative has endorsed the Submitted Item "Level D - rejected" not act upon the Submitted Item, amend the Submitted Item and re-submit the Submitted Item to the Authority's Representative in accordance with paragraph 4.4,

unless hubco disputes that any such comment or proposed amendment is on grounds permitted by this Agreement, in which case hubco or the Authority's Representative may refer the matter for determination in accordance with Schedule Part 15 (Dispute Resolution Procedure) and hubco shall not act on the Submitted Item until such matter is so determined or otherwise agreed except at its own risk in accordance with paragraph 1.3.2.

  - Within [       ] Business Days of receiving the comments of the Authority's Representative on any Submitted Item comprising Reviewable Design Data, hubco shall (except in the case contemplated in paragraph 4.3.1) send a copy of the Submitted Item as amended to the Authority's Representative pursuant to paragraph 4.3 and the provisions of paragraphs 1.2.1, 4.1 and 4.3 shall apply (changed according to context) to such re-submission.

  - The return or deemed return of any Submitted Item endorsed "no comment" (or in the case of Reviewable Design Data endorsed "Level A - no comment" or otherwise endorsed in accordance with paragraph 4.3.1 or 4.3.2) shall mean that the relevant Submitted Item may be used or implemented for the purposes for which it is intended but, save to the extent expressly stated in this Agreement including, without limitation, as specified in the Appendix to this Schedule Part 7, such return or deemed return of any Submitted Item shall not otherwise relieve hubco of its obligations under this Agreement nor is it an acknowledgement by the Authority that hubco has complied with such obligations.

- Documentation Management

  - hubco shall issue [      ] copies of all Submitted Items to the Authority and compile and maintain a register of the date and contents of the submission of all Submitted Items.

  - hubco shall compile and maintain a register of the date of receipt and content of all Submitted Items that are returned or deemed to be returned by the Authority's Representative.

  - Save to the extent set out in Appendix A to this Schedule Part 7 (Review Procedure) or elsewhere in this Schedule Part 7 (Review Procedure), no review, comment or approval by the Authority shall operate to exclude or limit hubco's obligations or liabilities under this Agreement (or the Authority's rights under this Agreement).

- Variations

  - No approval or comment or any failure to give or make an approval or comment under this Schedule Part 7 shall constitute a Variation save to the extent provided in this Schedule Part 7.

  - If, having received comments from the Authority's Representative, hubco considers that compliance with those comments would amount to a Variation, hubco shall, before complying with the comments, notify the Authority of the same and, if it is agreed by the parties or determined pursuant to Schedule Part 15 (Dispute Resolution Procedure) that a Variation would arise if the comments were complied with, the Authority may, if it wishes, implement the Variation and it shall be dealt with in accordance with Schedule Part 13 (Variation Procedure). Any failure by hubco to notify the Authority that it considers compliance with any comments of the Authority's Representative would amount to a Variation shall constitute an irrevocable acceptance by hubco that any compliance with the Authority's comments shall be without cost to the Authority and without any extension of time.

  - No alteration or modification to the design, quality and quantity of the hubco Designed Portion arising from the development of detailed design of the hubco Designed Portion by or on behalf of hubco or from the co-ordination of the design of the hubco Designed Portion by or on behalf of hubco shall be construed or regarded as a Variation.

- APPENDIX

| Approved RDD Item (by category) | Scale | Meaning of "Level A - no comment" and "Level B – proceed subject to amendment as noted" endorsement of Reviewable Design Data under Schedule Part 7 (Review Procedure) (including both the actual and deemed endorsement). |
| --- | --- | --- |
| Room Data Sheets (within the Authority’s Construction Requirements) | n/a | A "Level A - no comment" endorsement or a "Level B - proceed subject to amendment as noted" endorsement of any room data sheet means that hubco may proceed to construct in accordance with the Submitted Item and that the Authority is satisfied that the design and other information in the relevant room data sheet satisfies Operational Functionality. |
| Drawings - Development Control Plan | 1:1250 | A "Level A - no comment" endorsement or a "Level B - proceed subject to amendment as noted" endorsement of any 1:1250 scale development control plan means that hubco may proceed to construct in accordance with the Submitted Item and that the Authority is satisfied that the design and other information contained in the relevant drawing satisfies Operational Functionality. |
| Drawings - Site Plan | 1:500 | A "Level A - no comment" endorsement or a "Level B - proceed subject to amendment as noted" endorsement of any 1:500 scale site plan means that hubco may proceed to construct in accordance with the Submitted Item and that the Authority is satisfied that the design and other information contained in the relevant drawing satisfies Operational Functionality. |
| Drawings - Floor Plans | 1:200 | A "Level A - no comment" endorsement or a "Level B - proceed subject to amendment as noted" endorsement of any 1:200 scale floor plan means that hubco may proceed to construct in accordance with the Submitted Item and that the Authority is satisfied that the design and other information contained in the relevant drawing satisfies the Operational Functionality. |
| Drawings - Room Layouts (including room elevations) & Reflected ceiling plans | 1:50 | A "Level A - no comment" endorsement or a "Level B - proceed subject to amendment as noted" endorsement of any 1:50 scale room layout and/or reflected ceiling drawing means that hubco may proceed to construct in accordance with the Submitted Item and that the Authority is satisfied (to the extent of the design and other information contained in the relevant drawing) that the design and other information in the relevant drawing satisfies Operational Functionality. |
| Drawings - Departmental plans | 1:50 | A "Level A - no comment" endorsement or a "Level B – proceed subject to amendment as noted" endorsement of any 1:50 scale departmental plan means that hubco may proceed to construct in accordance with the Submitted Item and that the Authority is satisfied (to the extent of the design and other information contained in the relevant drawing) that the design and other information in the relevant drawing satisfies Operational Functionality. |

- COLLATERAL AGREEMENTS

- CONSTRUCTION CONTRACTOR COLLATERAL AGREEMENT

BETWEEN:

(1)	[AUTHORITY] (the "Authority");

(2)	[CONSTRUCTION CONTRACTOR] (the "Construction Contractor");

(3)	[HUBCO] ("hubco"); and

(4)	[GUARANTOR] (the "Guarantor").

WHEREAS:

(A)	The Authority and hubco have agreed the terms on which hubco will develop and construct [description of facilities] (the "Development") at the Site (as that expression is defined in the Build Only Development Agreement) and, accordingly, have entered into the Build Only Development Agreement and the Project Documents.

(B)	The Construction Contractor and hubco have entered into an agreement of even date herewith relating to the provision of the Works (as defined in the Build Only Development Agreement) by the Construction Contractor to enable hubco to discharge its obligations to the Authority regarding such Works under the Build Only Development Agreement (the "Construction Contract").

(C)	This Construction Contractor's Collateral Agreement (the "Agreement") is one of the Construction Contractor's Collateral Agreements contemplated by the Build Only Development Agreement.

(D)	Pursuant to the Construction Contract, the Guarantor has entered into a Guarantee in favour of hubco in respect of the Construction Contractor's obligations under the Construction Contract (the "Parent Company Guarantee").

NOW IT IS HEREBY AGREED as follows:

- Definitions and interpretation

  - Definitions

In this Agreement, the following terms shall, unless the context otherwise requires, have the following meanings:

| "Business Day" | means a day other than a Saturday, Sunday or a bank holiday in Scotland |
| --- | --- |
| "Contractor Designed Portion" | means [ l ] |
| "Event of hubco Default" | has the meaning given in the Construction Contract |
| "Novation Agreement" | has the meaning given in Clause 4.5.1(b) |
| "Novation Effective Date" | means the date of performance of the obligations set out in Clause 4 (Novation) |
| "Project Documents" | has the meaning given in the Build Only Development Agreement |
| "Proposed Novation Date" | has the meaning given in Clause 4.1 (Proposed Substitute) |
| "Proposed Novation Notice" | has the meaning given in Clause 4.1 (Proposed Substitute) |
| "Proposed Step-in Date" | has the meaning given in Clause 3.1 (Commencement and Duration) |
| "Proposed Substitute" | has the meaning given in Clause 4.1 (Proposed Substitute) |
| "Step-in Date" | means the date of issue of the Step-in Undertaking |
| "Step-in Notice" | has the meaning given in Clause 3.1 (Step-in Notice) |
| "Step-in Period" | means the period commencing on the Step-in Date and ending on the earliest of: - the date of the first anniversary of the Step-in Date (but subject always to Clause 4.7 (Extension of Step-in Period)); - the Step-out Date; - the Novation Effective Date; and - termination of the Construction Contract under Clause [INSERT RELEVANT CLAUSE FROM CONSTRUCTION CONTRACT] |
| "Step-in Undertaking" | has the meaning given in Clause 3.2.4 |
| "Step-out Date" | has the meaning given in Clause 3.4.1 |
| "Termination Notice" | has the meaning given in Clause 2.3.1 |

  - Interpretation

Save to the extent that the context or the express provisions of this Agreement otherwise require:

    - headings and sub-headings are for ease of reference only and shall not be taken into consideration in the interpretation or construction of this Agreement;

    - all references to Clauses are references to Clauses of this Agreement;

    - all references to agreements, documents or other instruments include (subject to all relevant approvals) a reference to that agreement, document or instrument as amended, supplemented, substituted, novated or assigned from time to time;

    - all references to any statute or statutory provision shall include references to any statute or statutory provision which amends, extends, consolidates or replaces the same or which has been amended, extended, consolidated or replaced by the same and shall include any orders, regulations, codes of practice, instruments or other subordinate legislation made under the relevant statute or statutory provision;

    - any reference to time of day shall be a reference to Edinburgh time;

    - the words "herein", "hereto" and "hereunder" refer to this Agreement as a whole and not to the particular Clause in which such word may be used;

    - words importing the singular include the plural and vice versa;

    - words importing a particular gender include all genders;

    - "person" includes any individual, partnership, firm, trust, body corporate, government, governmental body, authority, agency, unincorporated body of persons or association;

    - any reference to a public organisation shall be deemed to include a reference to any successor to such public organisation or any organisation or entity which has taken over the functions or responsibilities of such public organisation;

    - references to "Party" means a party to this Agreement and references to "Parties" shall be construed accordingly;

    - all monetary amounts are expressed in pounds sterling;

    - references to the word "includes" or "including" are to be construed without limitation;

    - the obligations of any Party under this Agreement are to be performed at that Party's own cost and expense;

    - terms used in this Agreement that are defined in the Build Only Development Agreement or the Project Documents shall have the meanings given to them in the Build Only Development Agreement or the Project Documents, as appropriate.

- Termination Notice and Authority Termination

  - Construction Contractor's Warranties and Undertakings

The Construction Contractor warrants and undertakes to the Authority that it has complied with and fulfilled and shall continue to comply with and fulfil its duties and obligations arising under or by virtue of the Construction Contract, provided that (during the period prior to expiry of the Defects Liability Period (as defined in the Build Only Development Agreement)) the Authority shall only be entitled to make a claim against the Construction Contractor under this Clause 2.1 (Construction Contractor’s Warranties and Undertakings) if the Build Only Development Agreement has terminated and in any case shall not be entitled to do so during the Step-in Period or after the Construction Contract has been novated under Clause 4 (Novation).

  - Liability of Construction Contractor

Any liability arising from any claim for breach of the warranty under or pursuant to Clause 2.1 (Construction Contractor’s Warranties and Undertakings) shall be in addition to and without prejudice to any other present or future liability of the Construction Contractor to the Authority (including, without prejudice to the generality of the foregoing, any liability in negligence) and shall not be released, diminished or in any other way be affected by any independent enquiry into any relevant matter which may be made or carried out by or on behalf of the Authority by any person nor by any action or omission of any person whether or not such action or omission might give rise to an independent liability of such person to the Authority provided always that the Construction Contractor shall owe no greater duties or obligations to the Authority under this Agreement than it owes or would have owed to hubco under the Construction Contract.  Without prejudice to Clause 12, the Construction Contractor shall be entitled in any action or proceedings brought by the Authority under this Agreement to rely on any limitation or exclusion of liability in the Construction Contract and to raise equivalent rights in defence of liability (but excluding set-offs and counterclaims) as it would have against hubco under the Construction Contract.

  - Termination Notice

    - The Construction Contractor undertakes not to terminate the Construction Contract on account of an Event of hubco Default without first giving the Authority not less than [    ] Business Days' prior written notice specifying the grounds for that termination.  Any such notice, other than one given in circumstances where there is no default under the Construction Contract by hubco or the Construction Contractor, shall be a "Termination Notice".

    - Notwithstanding any provision of the Construction Contract to the contrary, on termination of the Build Only Development Agreement by the Authority, the Parties agree that the Construction Contract shall not come to an end except in accordance with the terms of this Agreement.

- Step-In and Step-Out

  - Step-in Notice

    - If the Authority has terminated the Build Only Development Agreement in accordance with the terms of the Build Only Development Agreement or if the Authority has received a Termination Notice, then subject to the provisions of this Agreement, the Authority may give written notice to the Construction Contractor (a "Step-in Notice") of the intention of the Authority to issue a Step-in Undertaking on a specified date (the "Proposed Step-in Date") provided that such Proposed Step-in Date shall be:

        - no later than [         ] Business Days after termination of the Build Only Development Agreement where this has been terminated by the Authority; and

        - no earlier than the date falling [     ] Business Days prior to the date of expiry of the Termination Notice and no later than the date of expiry of the Termination Notice where a Termination Notice has been given by the Construction Contractor.

    - Without prejudice to Clause 3.2.6, unless the Construction Contractor otherwise consents, only one Step-in Notice may be given during the period of this Agreement.  Subject to Clause 5.1 (Rights of Termination) below, the Construction Contractor shall not be entitled to terminate the Construction Contract until after the Proposed Step-in Date.

  - Notice of Obligations and Step-in Undertaking

    - Within [     ] Business Days of receipt of any Step-in Notice, the Construction Contractor shall give written notice to the Authority of any sums of which the Construction Contractor has actual knowledge which are due and payable but unpaid by hubco and of any other material obligations or liabilities, of which the Construction Contractor has actual knowledge, which should have been performed or discharged by hubco under the Construction Contract, in each case, as at the date of the Step-in Notice.

    - The Construction Contractor shall inform the Authority in writing as soon as reasonably practicable of:

        - any change in such sums, obligations or liabilities referred to in Clause 3.2.1; and

        - any further sums, obligations or liabilities thereafter falling due and payable but unpaid or falling due for performance or discharge and unperformed or undischarged (as the case may be);

in each case of which the Construction Contractor has actual knowledge, before the Step-in Date.

    - The Construction Contractor shall give the Authority the information referred to in Clauses 3.2.1 and 3.2.2 in good faith and may not give any further notifications pursuant to Clause 3.2.2 less than [      ] Business Days prior to the Proposed Step-in Date.  The Authority shall not be required to assume any liability under a Step-in Undertaking for any outstanding obligations or liabilities of hubco to the Construction Contractor which are not notified to the Authority pursuant to Clauses 3.2.1 or 3.2.2.

    - Not later than the Proposed Step-in Date the Authority shall decide if it is prepared to issue a Step-in Undertaking.  If it does so decide, the Authority shall promptly give the Construction Contractor written notification of such decision.  The Authority shall deliver to the Construction Contractor on the Proposed Step-in Date, a written undertaking in form and substance agreed with the Construction Contractor (both the Authority and the Construction Contractor acting reasonably) (the "Step-in Undertaking"), incorporating a clause in terms similar to Clause 11 (but only to the extent that there will not be double counting of default interest accruing under the Construction Contract and this Agreement), and undertaking to the Construction Contractor:

        - to pay or procure the payment to the Construction Contractor, within [     ] Business Days of demand by the Construction Contractor, of any sum due and payable but unpaid by hubco to the Construction Contractor under the Construction Contract before the Step-in Date and which has been notified by the Construction Contractor to the Authority in accordance with Clause 3.2.1 or 3.2.2;

        - to perform or discharge or procure the performance or discharge of any unperformed or undischarged obligations of hubco under the Construction Contract which shall have fallen due for performance or discharge before the Step-in Date and which have been notified by the Construction Contractor to the Authority in accordance with Clause 3.2.1 or 3.2.2 within such period as the Construction Contractor may reasonably require;

        - to pay or procure the payment of any sum due and payable by hubco under the Construction Contract as a result of any act or omission occurring during the Step-in Period which shall arise from any act or omission occurring after the Step-in Date (but subject to Clauses 3.4 and 4.5(b)) but not, to avoid doubt, any sum due in respect of any Works carried out before the Step-in Date; and

        - to perform or discharge or procure the performance or discharge of any obligations of hubco under the Construction Contract as a result of any act or omission occurring during the Step-in Period which shall arise from any act or omission occurring after the Step-in Date (but subject to Clauses 3.4 (Step-Out) and 4.5(b)) but not, to avoid doubt, to perform or discharge or to procure the performance or discharge of any obligations in respect of any Works carried out before the Step-in Date.

    - hubco shall immediately assign all its rights and powers under the Parent Company Guarantee to the Authority in accordance with Clause [INSERT REFERENCE FROM PCG] of the same.  The Guarantor acknowledges and agrees that upon intimation to it of such assignation, the Guarantor shall owe its obligations under the Parent Company Guarantee to the Authority to the exclusion of hubco (but without prejudice to hubco's right to claim thereunder in respect of any cause of action arising in respect of the period prior to the assignation) upon the terms and conditions of the Parent Company Guarantee.

    - If the Authority shall not have issued the Step-in Undertaking on or before the Proposed Step-in Date, the Step-in Notice shall be deemed to have been withdrawn and the rights and obligations of the Parties shall be construed as if the Step-in Notice had not been given.

  - Restriction of Right of Termination

During or in respect of the Step-in Period, the Construction Contractor confirms to the Authority that it shall continue to observe and perform its duties and obligations under the Construction Contract and shall, without prejudice to Clause 5.1 (Rights of Termination), only be entitled to exercise its rights of termination under the Construction Contract:

    - by reference to an Event of hubco Default arising during the Step-in Period provided that no event of default by hubco under the Build Only Development Agreement (whether resulting in termination of the Build Only Development Agreement or otherwise, and notwithstanding that it has occurred during the Step-in Period) shall entitle the Construction Contractor to exercise such rights of termination during the Step-in Period; or

    - if the Authority, in breach of the terms of the Construction Contract, fails to pay when due any amount owed to the Construction Contractor or fails to perform or discharge when falling due for performance or discharge any obligation under the Step-in Undertaking or fails to procure such payment or performance or discharge; or

    - if such rights of termination arise in circumstances where there is no default under the Construction Contract by the Authority or the Construction Contractor.

  - Step-Out

    - the Authority may, at any time, give the Construction Contractor at least [  thirty (30)] days' prior written notice to terminate the Step-in Period on a date specified in the notice (the "Step-out Date");

    - the Authority shall give the Construction Contractor at least [   thirty (30)] days' prior written notice that (subject to Clause 4.4.2) the Step-in Period will end due to the occurrence (subject to Clause 4.7 (Extension of Step-In Period) of the first anniversary of the Step-in Date;

provided that

        - the Authority has performed and discharged in full or procured the performance and discharge in full of any obligations of hubco under the Construction Contract in relation to the maintenance of records and the provision of reports during the Step-in Period so as to permit the Construction Contractor to monitor the performance of hubco's other obligations under the Construction Contract; and

        - all liability under the Step-in Undertaking pursuant to any claims made up to the date specified in either Clause 3.4.1 or Clause 3.4.2 (as the case may be) shall have been fully and unconditionally discharged,

the Authority shall be released from the Step-in Undertaking on the expiry of the Step-in Period in accordance with Clauses 3.4.1 and 3.4.2.  Such release shall not affect the continuation of hubco's obligations towards the Construction Contractor under the Construction Contract.

- Novation

  - Proposed Substitute

At any time that the Authority is entitled to give a Step-in Notice pursuant to Clause 3.1 (Step-In Notice) or at any time during the Step-in Period the Authority may give notice (a "Proposed Novation Notice") to the Construction Contractor that it wishes itself or another person (a "Proposed Substitute") to assume, by way of sale, transfer or other disposal, the rights and obligations of hubco under the Construction Contract and specifying a date (the "Proposed Novation Date"):

    - falling not later than [     fifteen (15)] Business Days after termination of the Build Only Development Agreement where this has been terminated by the Authority;

    - falling not later than the expiry of the Termination Notice where a Proposed Novation Notice is given by the Authority at a time when it is entitled to give a Step-in Notice pursuant to Clause 3.1; and

    - falling not later than [         twenty eight (28)] Business Days after the date of the Proposed Novation Notice, where a Proposed Novation Notice is given during a Step-in Period,

Save as provided in Clause 4.4 (Consent Withheld), only one Proposed Novation Notice may be given during the period of this Agreement.  Without prejudice to Clauses 3.3 (Restriction of Right of Termination), the Construction Contractor shall not be entitled to terminate the Construction Contract during the notice period specified in a Proposed Novation Notice.

  - Information for Consent to Novation

If the Proposed Novation Notice specifies the Authority as the Proposed Substitute, the Construction Contractor's consent to the novation shall be deemed to have been given automatically.  Where the Proposed Substitute is not the Authority, a novation in accordance with a Proposed Novation Notice shall only be effective if the Construction Contractor consents to that novation in writing in accordance with Clause 4.3 (Grant of Consent) and Clause 5.1 (Rights of Termination) and the Authority shall (as soon as practicable) supply the Construction Contractor with the following information:

    - the name and registered address of the Proposed Substitute;

    - the names of the shareholders in the Proposed Substitute and the share capital owned by each of them;

    - the names of the directors and the secretary of the Proposed Substitute;

    - details of the means by which it is proposed to finance the Proposed Substitute (including the extent to which such finance is committed and any conditions precedent as to its availability for drawing); and

    - the resources (including contractual arrangements) which are to be available to the Proposed Substitute to enable it to perform its obligations under the Construction Contract.

  - Grant of Consent

The Construction Contractor may withhold or delay consent to a novation only where the Proposed Substitute is not the Authority and the Authority has failed to show to the Construction Contractor's satisfaction (acting reasonably) that:

    - the Proposed Substitute has the legal capacity, power and authorisation to become a party to and perform the obligations of hubco under the Construction Contract; and

    - the technical competence and financial standing of and the technical and financial resources available to the Proposed Substitute are sufficient to perform the obligations of hubco under the Construction Contract.

The Construction Contractor shall notify the Authority in writing, within [     five (5)] Business Days of the later of receipt of a Proposed Novation Notice and all information required under Clause 4.2 (Information for Consent to Novation), as to whether or not it has decided to grant such consent (together with an explanation of its reasons if it has decided to withhold its consent).

  - Consent Withheld

If, in accordance with Clause 4.3 (Grant of Consent), the Construction Contractor withholds its consent to a Proposed Novation Notice, the Authority shall be entitled to give one or more subsequent Proposed Novation Notices, pursuant to the provisions of Clause 4.1 (Proposed Substitute), containing changed particulars relating to the same Proposed Substitute or particulars relating to another Proposed Substitute which (where the replacement Proposed Substitute is not the Authority) the Authority has good cause to believe would fulfil the requirements of Clauses 4.3.1 and 4.3.2, provided that only one Proposed Novation Notice may be outstanding at any one time, and provided further that:

    - where a Step-in-Notice has not been issued, any revised Proposed Novation Date shall be a date falling no later than the date specified in Clause 4.1.1 or 4.1.2 as appropriate; and

    - if the Proposed Novation Notice was served during the Step-in Period, any revised Proposed Novation Date shall be a date falling not later than [      ] Business Days after the date of the revised Proposed Novation Notice.

  - Implementation of Novation

    - If the Construction Contractor consents to a novation pursuant to a Proposed Novation Notice (whether automatically or otherwise), then on the Proposed Novation Date and without prejudice to Clause 5.1, hubco shall immediately assign all its rights and powers under the Parent Company Guarantee to the Authority in accordance with Clause [INSERT PCG REFERENCE] of the same, and on the Proposed Novation Date and without prejudice to Clause 5.1 (Rights of Termination):

(a)	subject to the prior performance by hubco of its obligations under Clause 4.5.1 the Proposed Substitute shall become a party to the Construction Contract in place of hubco and, thereafter, shall be treated as if it was and had always been named as a party to the Construction Contract in place of hubco; and

(b)	the Construction Contractor, hubco and the Proposed Substitute shall enter into a novation agreement (the "Novation Agreement") and any other requisite agreements, in form and substance satisfactory to the Construction Contractor (acting reasonably), pursuant to which:

      - the Proposed Substitute shall be granted all of the rights of hubco under the Construction Contract (including those arising prior to the end of the Step-in Period);

      - subject to the Construction Contractor giving to the Proposed Substitute within [    ] Business Days of receipt of the Proposed Novation Notice such notice as is referred to in Clause 3.2.1 and to the provisions of Clauses 3.2.2 and 3.2.3, mutatis mutandis, the Proposed Substitute shall assume all of the obligations and liabilities of hubco under the Construction Contract (including those arising prior to the end of any Step-in Period and those arising during the period of the Proposed Novation Notice);

(c)	the Guarantor acknowledges and agrees that it shall owe its obligations 	under the Parent Company Guarantee to the Authority to the exclusion of 	hubco (but without prejudice to hubco's right to claim thereunder in respect of 	any course of action arising in respect of the period prior to the novation) upon 	the terms and conditions of the Parent Company Guarantee,

provided that the Construction Contractor will not be in breach of any of its obligations under this Agreement if the Proposed Substitute does not enter into one or other of such agreements.

    - On and after the Novation Effective Date:

        - the Construction Contractor shall owe its obligations under the Construction Contract (whether arising before, on or after such date) to the Proposed Substitute and the receipt, acknowledgement or acquiescence of the Proposed Substitute shall be a good discharge; and

        - if the Authority shall have entered into a Step-in Undertaking, the Authority will be released from the Step-in Undertaking, provided that:

            - all obligations of the Authority under the Step-in Undertaking which have accrued up to the Novation Effective Date and are identifiable as at that date shall have been fully and unconditionally discharged; and

            - the Authority has performed and discharged in full or procured the performance and discharge in full of the obligations of hubco under the Construction Contract in relation to the maintenance of records and the provision of reports during the Step-in Period up to the Novation Effective Date so as to permit the Construction Contractor to monitor the performance of hubco's other obligations under the Construction Contract.

    - the Authority and the Construction Contractor shall use all reasonable endeavours to agree and the Authority shall use reasonable endeavours to procure that the Proposed Substitute agrees any amendments to the Construction Contract necessary to reflect Clause 3.2.2 and the fact that the Build Only Development Agreement may have terminated at the time of the Novation Effective Date.

  - Termination After Novation

After the Novation Effective Date the Construction Contractor shall only be entitled to exercise its rights of termination under the Construction Contract:

    - in respect of any Event of hubco Default arising after that date in accordance with the Construction Contract; or

    - if the Proposed Substitute does not discharge the obligations and liabilities assumed by it under Clause 4.5(b) which relate to matters arising prior to the end of the Step-in Period within [     ] Business Days following the Novation Effective Date.

  - Extension of Step-In Period

As at the date of the first anniversary of the Step-in Date, if the Step-in Period has not previously ended, and:

    - the Authority is in the course of conducting discussions in good faith with a Proposed Substitute (the novation to whom has been approved by the Construction Contractor whether automatically or otherwise in accordance with Clause 4.3 (Grant of Consent)), the Step-in Period shall be extended and shall continue until such date as is proposed by the Authority and agreed by the Construction Contractor; or

    - a contract has been entered into between the Authority and a Proposed Substitute (which has been approved by the Construction Contractor in accordance with Clause 4.3 (Grant of Consent) as at such date,

the Step-in Period shall be extended and shall continue until the date such contract comes into force, provided that such date shall not be later than [       ] Business Days after the last date of execution of such contract.

- Rights and Obligations under the Construction Contract

  - Rights of Termination

If:

    - no Step-in Notice or Proposed Novation Notice is given before a Termination Notice expires or within [  ] Business Days after termination of the Build Only Development Agreement by the Authority; or

    - a Step-in Undertaking is not issued on the Proposed Step-in Date; or

    - the Step-in Notice is withdrawn or, pursuant to Clause 3.2.6, deemed to have been withdrawn; or

    - the Step-in Period ends before the occurrence of the Novation Effective Date; or

    - in the absence of a Step-in Undertaking, the Construction Contractor withholds its consent to a novation pursuant to a Proposed Novation Notice, in accordance with Clause 4.3 (Grant of Consent), and does not subsequently grant consent to a novation in accordance with Clause 4.4 (Consent Withheld) on or before the Proposed Novation Date; or

    - in the absence of a Step-in Undertaking, the obligations of the Proposed Substitute set out in Clause 4.5 (Implementation of Novation) are not performed on the Proposed Novation Date; or

    - the Construction Contractor is entitled to terminate the Construction Contract under Clause 3.3 (Restriction of Right of Termination) or 4.6 (Termination After Novation); or

    - the Authority exercises its right to Step-out under Clause 3.4.1,

the Construction Contractor shall, on and from the Step-Out Date be entitled to:

    - exercise all of its rights under the Construction Contract and act upon any and all grounds for termination available to it in relation to the Construction Contract whenever occurring; and/or

    - pursue any and all claims and exercise any and all rights and remedies against hubco.

  - hubco's Obligations to Continue

Until completion of a novation pursuant to Clause 4.5 (Implementation of Novation) (unless the terms of such novation expressly preserve an obligation or liability of hubco), hubco shall continue to be liable for all its obligations and liabilities, whenever occurring, under or arising from the Construction Contract notwithstanding:

    - the service of a Step-in Notice or the issue of a Step-in Undertaking or the expiry of the Step-in Period or the release of a Step-in Undertaking; or

    - the service of a Proposed Novation Notice; or

    - any other provision of this Agreement.

- Revocation of Notices

A Termination Notice and a Step-in Notice may each be revoked (in writing to the recipient) by the Party giving them before the expiry of their respective notice periods.  Upon any such revocation, the rights and obligations of the Parties shall be construed as if the relevant notice had not been given.

- Assignation

  - Binding on Successors and Assignees

This Agreement shall be binding on and shall enure to the benefit of the Parties and their respective successors and permitted assignees.  In the case of the Authority, its successors shall include any person to which the Scottish Ministers, [in exercising their statutory powers to transfer property, rights and liabilities of the Authority upon the Authority ceasing to exist,] transfers the rights and obligations of the Authority under this Agreement.

  - Restriction on Assignation

No Party shall assign or transfer any part of its respective rights or obligations under this Agreement without the prior consent of the others (such consent not to be unreasonably withheld or delayed), provided that:

    - hubco shall not assign this Agreement to any party other than a party to whom hubco’s interests in the Construction Contract are assigned in accordance with the Construction Contract;

    - the Authority shall be entitled, without the consent of any other Party, to transfer all its rights and obligations hereunder, to any person to whom it assigns or otherwise disposes of the benefit of the Build Only Development Agreement in accordance with Clause 43 (Assignation, Sub-Contracting) of the Build Only Development Agreement and, otherwise, with hubco's and the Construction Contractor's consent (not to be unreasonably withheld or delayed);

    - nothing in this sub-clause shall restrict the rights of the Scottish Ministers to effect a statutory transfer;

    - the Construction Contractor shall assign this Agreement to any party to whom it assigns the Construction Contract (in accordance with the terms of that agreement).

  - No Loss

The Construction Contractor agrees that it shall not at any time assert that any permitted assignee in terms of this Agreement is precluded from recovering any loss resulting from any breach of this Agreement by reason that such assignee is not an original party to this Agreement or that no loss or a different loss has been suffered by such assignee.

- Confidentiality

  - The parties shall be bound to observe, mutatis mutandis, the terms of Clause [INSERT REFERENCE] of the Construction Contract with respect to any information or document referred to in Clause [INSERT REFERENCE] of the Construction Contract which shall come into its possession pursuant to this Agreement.]

  - The Construction Contractor agrees that the Authority shall be entitled to disclose the terms of this Agreement in accordance with Clause 46 (Confidentiality) of the Build Only Development Agreement.

- Notices

Any notice given under this Agreement shall be deemed to be duly given if it is delivered by hand or sent by recorded delivery to the party named therein at the address of such party shown in this Agreement or such other address as such party may by notice in writing nominate for the purpose of service and if sent by recorded delivery shall be deemed (subject to proof to the contrary) to have been received forty eight (48) hours after being posted.

- Payments and Taxes

  - Payments

All payments under this Agreement to any Party shall be made in pounds sterling by electronic transfer of funds for value on the day in question to the bank account of the recipient (located in the United Kingdom) specified to the other Parties from time to time.

  - VAT

    - All amounts stated to be payable by any Party under this Agreement shall be exclusive of any VAT properly payable in respect of the supplies to which they relate.

    - Each Party shall pay any VAT properly payable hereunder in respect of any supply made to it under this Agreement, provided that it shall first have received a valid tax invoice in respect of that supply which complies with the requirements of Part III Value Added Tax Regulations 1995.

  - Deductions from payments

All sums payable by a Party to any other Party under this Agreement shall be paid free and clear of all deductions or withholdings whatsoever in respect of taxation, save as may be required by Law.

- Default Interest

Each Party shall be entitled, without prejudice to any other right or remedy, to receive interest on any payment not made on the due date calculated from day to day at a rate per annum equal to the Default Interest Rate from the day after the date on which payment was due up to and including the date of payment.

- Aggregate Liability

Notwithstanding any other provision of this Agreement, the Construction Contractor's aggregate liability from time to time under this Agreement and the Construction Contract shall not at any time exceed its maximum liability as stated in the Construction Contract (as amended or varied).

- Professional Indemnity Insurance

  - Where the Works include a Contractor Designed Portion, the Construction Contractor by this Agreement covenants with the Authority that it has at its own cost taken out, or procured the taking out of, professional indemnity insurance with reputable insurers carrying on business in the European Union with a limit of indemnity of not less than £[ ],000,000 ([  ] million pounds) [on an each and every claim basis][in the annual aggregate] with at least one annual reinstatement, in relation to the Contractor Designed Portion, provided always that:

    - such insurance shall be in place from the commencement of the Works until no less than twelve (12) years after the Actual Completion Date or, if earlier, after the date of termination of the Construction Contract;

    - the insurance premiums in respect of the insurance shall at all times be the responsibility of the Construction Contractor; and

    - if such insurance is not available to the Construction Contractor (and/or contractors engaged in projects of a similar scope, size, nature and complexity as the Construction Contractor) at commercially reasonable rates and terms (excluding any increase in premiums attributable to the actions, omissions, errors or defaults of the Construction Contractor), the Construction Contractor and the Authority will meet and the Construction Contractor will outline the steps it intends to take to manage such risks.  If the steps proposed by the Construction Contractor are not acceptable to the Authority (acting reasonably), the Construction Contractor and the Authority shall agree an alternative method of managing such risk.

  - The Construction Contractor will, upon request, provide the Authority with reasonable evidence that the policy referred to in this Clause 13 (Professional Indemnity Insurance) is in full force and effect in accordance with the requirements of this Clause 13 (Professional Indemnity Insurance).

- Third Party Rights

It is agreed that this Agreement is not intended to, and does not, give to any person who is not a party to this Agreement any rights to enforce any provisions contained herein (whether under the Contract (Third Party Rights) (Scotland) Act 2017 or otherwise) except for any person to whom the benefit of this Agreement is assigned or transferred in accordance with Clause 7 (Assignation).

- Agency

  - No Delegation

No provision of this Agreement shall be construed as a delegation by the Authority of any of its statutory authority to any other Party.

  - No Agency

Save as otherwise provided in this Agreement, no other Party shall be or be deemed to be an agent of the other Parties nor shall any party hold itself out as having authority or power to bind the other parties in any way.

  - Independent Contractor

The Parties shall, at all times, be independent contractors and nothing in this Agreement shall be construed as creating any partnership between the Parties or any relationship of employer and employee between the Parties.

- Whole Agreement

  - This Agreement (when read together with the Build Only Development Agreement, the Construction Contract and the Parent Company Guarantee) contains or expressly refers to the entire agreement between the Parties with respect to the specific subject matter of this Agreement and expressly excludes any warranty, condition or other undertaking implied at Law or by custom and supersedes all previous agreements and understandings between the Parties with respect thereto and each of the Parties acknowledges and confirms that it does not enter into this Agreement in reliance on any representation, warranty or other undertaking not fully reflected in the terms of this Agreement.

  - Nothing in this Agreement is intended to or shall operate so as to exclude or limit any liability for fraud or fraudulent misrepresentation.

- Waiver

Failure by any Party at any time to enforce any provision of this Agreement or to require performance by the other Parties of any provision of this Agreement shall not be construed as a waiver of such provision and shall not affect the validity of this Agreement or any part of it or the right of the relevant Party to enforce any provision in accordance with its terms.

- Severability

If any condition, Clause or provision of this Agreement not being of a fundamental nature, is held to be illegal or unenforceable, the validity or enforceability of the remainder of this Agreement shall not be affected thereby.

- Costs and Expenses

Each Party shall be responsible for paying its own costs and expenses incurred in connection with the negotiation, preparation and execution of this Agreement.

- Amendments

No amendment to this Agreement shall be binding unless in writing and signed by the duly authorised representatives of the Parties.

- Governing Law and Jurisdiction

  - Law

This Agreement shall be governed by and construed in all respects in accordance with Scottish law.

  - Jurisdiction

The Parties each submit to the jurisdiction of the Scottish Courts as regards any claim or matter arising in relation to this Agreement.

- Counterparts and Delivery

  - This Agreement may be executed in any number of counterparts and by each of the parties on 			separate counterparts.

  - Where executed in counterparts:

    - this Agreement will not take effect until each of the counterparts has been delivered;

    - where any counterpart is being held as undelivered, delivery will take place on the date of delivery agreed [among]/[between] the parties (the “agreed date”).  The agreed date will be inserted [in the testing clause] of this Agreement; and

    - [section 2(3) of the Legal Writings (Counterparts and Delivery) (Scotland) Act 2015 is hereby excluded and shall not apply to the execution arrangements in respect of this Agreement].

IN WITNESS WHEREOF these presents consisting of this and the [  ] preceding pages are executed in counterpart as follows and DELIVERED on [ l ]

COLLATERAL WARRANTY

among

[AUTHORITY,] having its principal offices at [ l ] (the “Beneficiary” which expression shall include its successors in title or permitted assignees under this Agreement and/or the Beneficiary’s appointee);

[hubco], a company incorporated in Scotland under the Companies Acts (Registered Number [ l ]) and having its Registered Office at [ l ] (“hubco” which expression shall include its successors in title or permitted assignees under this Agreement);

[ l ] LIMITED, a company incorporated in [Scotland/England and Wales/Northern Ireland] under the Companies Acts (Registered Number [ l ]) and having its Registered Office at [ l ] (the “Contractor" which expression shall include its successors in title or permitted assignees under this Agreement); and

and

[ l ] LIMITED, a company incorporated in [Scotland/England and Wales/Northern Ireland] under the Companies Acts (Registered Number [ l ]) and having its Registered Office at [ l ] (the “Sub-Contractor").

WHEREAS:

- The Beneficiary and hubco have entered into an agreement for the [insert name of facilities] (the "Project") on or about the date hereof (the “BODA Agreement").

- hubco and the Contractor have entered into a contract (the "Construction Contract") on or about the date hereof for the construction of the Project (the "Contract Works").

- The Contractor has entered or intends to enter into an agreement with the Sub-Contractor (the “Sub-Contract") whereby the Sub-Contractor will [design and] construct part of the Contract Works (the “Sub-Contract Works") in connection with the Project as more particularly described in the Sub-Contract.

- It is a condition of the Sub-Contract that the Sub-Contractor enters this Agreement with the Beneficiary.

- The Beneficiary shall be entitled to rely and is deemed to have relied on the Sub-Contractor's reasonable skill, care and diligence in respect of all matters covered by this Agreement insofar as they relate to the Sub-Contract Works provided by the Sub-Contractor under the Sub-Contract.

NOW IT IS AGREED as follows:

- Warranty and Undertaking

  - The Sub-Contractor warrants and undertakes to the Beneficiary that it has complied and will continue to comply with all the terms and obligations under or arising out of the Sub-Contract on the Sub-Contractor’s part to be performed and observed and shall complete the Sub-Contract Works in accordance with the Sub-Contract.

  - [Without prejudice to Clause 1.1 of this Agreement, the Sub-Contractor further warrants and undertakes to the Beneficiary that it has exercised and will continue to exercise all the due skill, care and diligence to be expected from a properly qualified and competent designer experienced in providing design services on projects similar in nature, size and complexity to the Project in:

    - the design of the Sub-Contract Works;

    - the specification of goods and materials for the Sub-Contract Works, and in particular in ensuring that it has not and will not specify for use in relation to the Sub-Contract Works any products or materials not in conformity with relevant British or European standards or Codes of Practice or which are at the time of specification generally known within the United Kingdom to an experienced designer of such works as the Sub-Contract Works to be deleterious to health and safety or to the durability of buildings and/or other structures and/or finishes and/or plant and machinery in the particular circumstances in which they are used;]

    - the Sub-Contract Works and all materials and goods specified therein will correspond as to description, quality and condition with the requirements of the Sub-Contract; and

    - [the Sub-Contract Works will at practical completion or its equivalent under the Sub-Contract, as the case may be, comply with all relevant legislation and Good Industry Practice].

- Insurance

  - [The Sub-Contractor shall maintain throughout the duration of provision of the Sub-Contract Works and for a period of 12 years after the date of practical completion or its equivalent under the Construction Contract, or if earlier the date of termination of the Sub-Contract, professional indemnity insurance in an amount of not less than [INSERT PI LEVEL] million pounds (£[INSERT FIGURE],000,000) sterling on an each and every claim basis and for any one occurrence or series of occurrences arising out of any one event with an insurer of good repute carrying on business in the European Union provided always that such insurance is available at rates which are commercially reasonable to sub-contractors.

  - In determining whether or not insurance is available as aforesaid, the financial characteristics and claims’ record of the Sub-Contractor shall be ignored.

  - The Sub-Contractor shall immediately inform the Beneficiary if such insurance ceases to be available at rates which are commercially reasonable in order that the Sub-Contractor and the Beneficiary can consider alternative means of best protecting their respective positions in respect of the Project in the absence of such insurance provided that the Beneficiary shall be entitled to require the Sub-Contractor to maintain such lesser amount of professional indemnity insurance as is available to the Sub-Contractor at rates which are commercially reasonable.

  - As and when it is reasonably requested to do so by the Beneficiary the Sub-Contractor shall produce for inspection documentary evidence satisfactory to the Beneficiary (acting reasonably) that its professional indemnity insurance is being maintained.

  - The Sub-Contractor confirms that this Agreement has been disclosed to and has been approved by the Sub-Contractor’s professional indemnity insurers or underwriters.

  - Should the Sub-Contractor be in breach of any of its obligations under this Clause 2 (Insurance), the Beneficiary may itself insure against any risk with respect to which the breach shall have occurred and may recover such sum or sums from the Sub-Contractor as a debt.]

- Copyright

  - The Sub-Contractor hereby grants to the Beneficiary or its appointee and all those authorised by the Beneficiary an irrevocable, transferable, non-exclusive and royalty-free licence (which shall be capable of assignation) to use and reproduce all information (whether or not stored in computer systems), drawings, models, bills of quantities, specifications, schedules, details, plans, programmes, budgets, reports, calculations or other documents, work or things including all applicable passwords or access codes whatsoever provided or to be provided by the Sub-Contractor in connection with the Sub-Contract Works (the “Documents”) for such purposes as the Beneficiary may at its sole discretion require.

  - Such licence shall carry the right to grant sub-licences and shall subsist notwithstanding that the Sub-Contract is terminated or the obligations and duties there under have been completed.  For the avoidance of doubt, the grant of such licence or sub-licences shall not impose any additional liability on the Sub-Contractor.

  - The Sub-Contractor shall on reasonable demand provide to the Beneficiary or its appointee and those authorised by the Beneficiary additional copies of any documents on receipt of reasonable copying costs.  The Sub-Contractor will not be liable for any use by the Beneficiary or any appointee or sub-licensee of any of the Documents for any purpose other than that for which the same were prepared and provided by the Sub-Contractor or for any improper or negligent use by the Beneficiary or any appointee or sub-licensee.

  - The Sub-Contractor agrees to indemnify and keep indemnified the Beneficiary from and against all loss, damage, cost, expense, liability or claim in respect of breach of the copyright or other intellectual property rights of any third party caused by or arising out of the carrying out of the Sub-Contract Works or the use of the licence.

- Assignation

  - This Agreement may be assigned in whole or in part by the Beneficiary to any successor to the Beneficiary’s interest in the Project or any part thereof without the consent of the Sub-Contractor being required and such assignation shall be effective upon written notice thereof being given to the Sub-Contractor.  No assignation of this Agreement by any other party shall be permitted.

  - The Sub-Contractor agrees that it shall not at any time assert that any permitted assignee in terms of this Agreement is precluded from recovering any loss resulting from any breach of this Agreement by reason that such assignee is not an original party to this Agreement or that no loss or a different loss has been suffered by such assignee.

- No Waiver or Variation

  - No failure, approval, act or forbearance on the part of the Beneficiary in respect of any right of the Beneficiary pursuant to this Agreement shall constitute any waiver of any right of the Beneficiary under or arising out of this Agreement nor relieve the Sub-Contractor of any of its duties or obligations under or arising out of this Agreement.

  - The Sub-Contractor will not seek to modify or vary any of the obligations for which it is responsible under the Sub-Contract in any respect if that modification or variation will be detrimental to the Beneficiary or affects the Beneficiary's rights or obligations under the BODA Agreement or affects the Sub-Contractor's obligations under this Agreement.

- Equivalent Rights

The obligations of the Sub-Contractor under this Agreement shall be no greater in extent or quantity than if the Beneficiary had been named as joint employer with the Contractor under the Sub-Contract.  The Sub-Contractor shall be entitled in any action or proceedings by the Beneficiary to rely on any limitation in the Sub-Contract and to raise the equivalent rights in defence of liability as it would have against the Contractor under the Sub-Contract (other than counterclaim, set-off or to state a defence of no loss or a different loss has been suffered by the Contractor).

- Notices

  - Any notice, consent or demand to be given or made by any party under this Agreement (hereinafter called a “Notice”) shall only be validly served if in writing and delivered personally or sent by pre-paid first class recorded delivery post or sent by fax to the following address and marked for the attention of the following person in the case of each party:

| - Party | - Address | - Fax No. | - Person |
| --- | --- | --- | --- |
| - The Beneficiary | - [ l ] | - [ l ] | - [ l ] |
| - hubco | - [ l ] | - [ l ] | - [ l ] |
| - The Contractor | - [ l ] | - [ l ] | - [ l ] |
| - The Sub-Contractor | - [ l ] | - [ l ] | - [ l ] |

Any party may by Notice to the other party/parties change its address, fax number or the title of the person for whose attention Notices are to be given or made pursuant to this Clause.  Any such Notice shall be deemed to have been received:

    - if delivered personally, at the time of delivery;

    - in the case of pre-paid first class recorded delivery post, on the first Business Day after the date of posting; and

    - in the case of a fax, at the time of transmission.

  - If any Notice is delivered or faxed after 5 p.m. on a Business Day, or at any time during a day which is not a Business Day, that Notice shall be deemed to have been received at 9 a.m. on the next Business Day.

  - For the purposes of this Clause 7 (Notices), “Business Day” means any day which is not a Saturday, a Sunday or a public holiday in Scotland.  In proving service it shall be sufficient to prove that the envelope containing such Notice was properly addressed to the relevant party and either delivered personally to that address or delivered into the custody of the postal authorities as a pre-paid first class recorded delivery letter, or that such Notice was transmitted by fax to the correct fax number of the relevant party (as demonstrated by the transmission slip).  For the avoidance of doubt, Notices shall not be validly served if sent by e-mail.

- The definitions of words and phrases used in this Agreement shall be those set out in the Construction Contract and Sub-Contract except where expressly defined in this Agreement.

- This Agreement shall be governed by and construed in accordance with Scots Law and the parties hereto submit to the exclusive jurisdiction of the Scottish Courts.

- Save to the extent expressly provided in this Agreement no provision of this Agreement is intended to or does confer upon any third party any benefit or right enforceable at the option of that third party or any liability whatsoever to any third party (whether under the Contract (Third Party Rights) (Scotland) Act 2017 or otherwise).

- The Sub-Contractor shall not without first giving the Beneficiary not less than twenty eight (28) days written notice exercise or seek to exercise any rights it may have to determine its employment under the Sub-Contract or treat it as having been determined by the Contractor (which expression in this clause shall include the appointment of a liquidator, receiver, administrator, administrative receiver or manager of the Contractor) or to discontinue performance of any service or obligations thereunder.

- Counterparts and Delivery

  - This Agreement may be executed in any number of counterparts and by each of the parties on separate counterparts.

  - Where executed in counterparts:

    - this Agreement will not take effect until each of the counterparts has been delivered;

    - where any counterpart is being held as undelivered, delivery will take place on the date of delivery agreed [among]/[between] the parties (the “agreed date”).  The agreed date will be inserted [in the testing clause] of this Agreement; and

    - [section 2(3) of the Legal Writings (Counterparts and Delivery) (Scotland) Act 2015 is hereby excluded and shall not apply to the execution arrangements in respect of this Agreement ].

IN WITNESS WHEREOF these presents consisting of this and the [  ] preceding pages are executed in counterpart as follows and DELIVERED on [ l ]:-

- OUTLINE COMMISSIONING PROGRAMME

[The contents of this Schedule Part 9 are project specific and should be prepared by each Authority on a project basis.]

- EQUIPMENT

      - DEFINITIONS

For the purposes of this Schedule Part 10 (Equipment) unless the context otherwise requires:

- “Equipment” means the Group 1 Equipment, the Group 2 Equipment, the Group 2a Equipment and the Group 3 Equipment;

- “Equipment Responsibilities Matrix" means the equipment responsibilities matrix contained in Appendix 2 to this Schedule Part 10;

- “Group 1 Equipment” means the Group 1 Equipment listed in Appendix 1 to this Schedule Part 10;

- “Group 2 Equipment” means the Group 2 Equipment listed in Appendix 1 to this Schedule Part 10;

- “Group 2a Equipment” means the Group 2a Equipment listed in Appendix 1 to this Schedule Part 10; and

- “Group 3 Equipment” means the Group 3 Equipment listed in Appendix 1 to this Schedule Part 10.

      - EQUIPMENT RESPONSIBILITIES MATRIX

        - Subject to the provisions of paragraph 2.2 below, the Equipment Responsibilities Matrix sets out the respective responsibilities of the parties in relation to various matters relating to Equipment, namely:

          - the party responsible for developing the initial specification for the item of Equipment, carrying out the tender process, selecting and procuring the appropriate Equipment (at its own cost), the responsibility for which is set out in the column headed “Supplied/ Procured”;

          - the party responsible for the initial installation of the item of Equipment (at its own cost), the responsibility for which is set out in the column headed “Installed/ Placed”; and

          - the party responsible for the initial commissioning of items of Equipment and staff training (at its own cost) as appropriate, the responsibility for which is set out in the column headed “Commissioned”.

        - Where hubco is responsible for the any of the matters under paragraphs 2.1.1, 2.1.2 and 2.1.3, hubco shall (or shall procure that):

          - all available manufacturers warranties and/or guarantees that are (or ought to be) obtainable on the market relating to the Equipment are obtained; and

          - the benefit of any manufacturers warranties and/or guarantees are assigned and/or made available to the Authority.

      - EQUIPMENT INSTALLATION AND COMMISSIONING

        - In specifying, procuring, installing and commissioning Equipment, the parties will be subject to and will comply with the terms of Clause 16, Schedule Part 9 (Outline Commissioning Programme) and the Final Commissioning Programme [for the relevant Phases].

        - The parties will liaise and agree a schedule of delivery around Group 2 Equipment and Group 3 Equipment as part of the Final Commissioning Programme [for the relevant Phase] to ensure the Works are designed and completed to enable the installation of the Equipment supplied by the Authority, taking into account loading, ventilation and fixing requirements.

          - In accordance with Clause 16.6 and the Final Commissioning Programme [for the relevant Phase], early access to server rooms will be made available to allow the Authority to install, commission and monitor Group 3 Equipment, access being required until the [relevant Phase] Actual Completion Date.

          - In addition:

            - the server rooms must be completed, secure and completely cleaned by hubco prior to installation of Group 3 Equipment by the Authority, and this will be reflected in the Final Commissioning Programme [for the relevant Phase];

            - for the avoidance of doubt, no part of the Works will be carried out in the server rooms during or following installation of the Group 3 Equipment by the Authority, save to the extent authorised by the Authority acting reasonably; and

            - there shall be no access to the server rooms by hubco following Group 3 Equipment installation in the server room save to the extent authorised by the Authority or otherwise by this Agreement.

      - AUTHORITY’S ACTIONS

        - Except where otherwise agreed with hubco and included in hubco’s procurement arrangements, the Authority will, at its own cost, procure and deliver and unload to hubco to a central location as is agreed between the parties at the Site (which for the avoidance of doubt, must be safely accessible by those persons delivering the relevant item or items of Equipment), the Group 2 Equipment in accordance with the Final Commissioning Programme or on the date specified in the relevant notice issued pursuant to paragraph 5.3 below or as otherwise agreed between the parties.

        - As soon as reasonably practicable after delivery, the Authority and hubco shall undertake a visual inspection of any Group 2 Equipment delivered by the Authority. If it is apparent from the visual inspection that such Group 2 Equipment is damaged or otherwise does not accord with the items of equipment listed in Appendix 1 to this Schedule Part 10, the Authority shall remove any such damaged Group 2 Equipment, or such Group 2 Equipment which is not in accordance with the items of equipment listed in Appendix 1 to this Schedule Part 10, and shall deliver a replacement for such Group 2 Equipment in accordance with the original dates in the Final Commissioning Programme or on the date specified in the relevant notice issued pursuant to paragraph 5.3 below or as otherwise agreed between the parties.

        - The Authority shall provide hubco with all necessary design information that it may reasonably require in respect of the Group 2 Equipment, including key dimensions, service supplies, commissioning details, fixing details and loads required to install structure partitions and services adjacent to and/or serving those items of Group 2 Equipment and to notify hubco of the precise required locations within the relevant rooms of such Group 2 Equipment in accordance with the Final Commissioning Programme.

        - In the event that the Authority has not supplied any Group 2 Equipment for the Project on the date set out in the Final Commissioning Programme, or on the date specified in the relevant notice issued pursuant to paragraph 5.3 below or as otherwise agreed between the parties, hubco shall be relieved of any obligation to install or place such Group 2 Equipment and the provisions of Clause 22 shall apply.

        - Not used.

        - The Authority shall at its own cost procure, install and commission the Group 3 Equipment at the Facilities as part of the Authority’s Commissioning or Authority’s Post Completion Commissioning activities.

        - Not used.

        - The Authority shall ensure that delivery of any Group 2 Equipment and delivery and installation of any Group 3 Equipment by or on behalf of the Authority shall be performed in accordance with Law, Good Industry Practice, exercising due care and attention and having regard to hubco’s other operations at the Facilities.

        - The Authority shall make good any damage caused by or in the course of delivery of the Group 2 Equipment to the reasonable satisfaction of hubco.

        - When undertaking delivery of the Group 2 Equipment and delivery and installation of the Group 3 Equipment, as the case may be, the Authority shall, and shall procure that Authority Parties shall, comply with all relevant safety procedures, which shall include any relevant construction phase plans and health and safety plans for the construction of the Facilities, the Contractor’s Site Rules from time to time and any reasonable directions with regard to site safety that may be issued by or on behalf of the Contractor’s Site Manager from time to time and that there is no interference with, hindrance or delay of hubco or any hubco Party.

      - HUBCO OBLIGATIONS

        - In addition to the obligations on hubco defined in paragraph 2.2 above and paragraph 1 of Appendix 2: Equipment Responsibility Matrix of this Schedule Part 10, and in order to facilitate a choice of Equipment actively involving the Authority, hubco shall in the period prior to the [relevant Phase] Actual Completion Date inform the Authority as to:

          - the proposed make, model and manufacturer of items of Equipment to be supplied by hubco provided always that the Authority may, within a reasonable period of time and taking into account hubco’s obligations under this Agreement, request that hubco substitute the proposed piece of Equipment, or choices offered, with another type or model or style (whether or not enhanced or superior) or an item of equipment other than that which hubco was proposing to supply provided that any such request must take into account the following issues:

            - the cost and lead time for the ordering and delivery of the proposed substitute;

            - the cost and availability of spares for the proposed substitute;

            - not used;

            - any warranty periods relating to the proposed substitute;

            - the installation period and whether the installation requirements for the proposed substitute differ from the installation requirements of the hubco Proposals;

            - not used; and

            - any other matter agreed by the parties (acting reasonably),

and where, as a result of any of items specified in (a) to (g) above, there is a cost or other impact on hubco as a result of the Authority’s preferred piece of Equipment, then this shall be dealt with as a Variation in accordance with the provisions of Schedule Part 13 (Variation Procedure).

        - hubco shall install the Group 2 Equipment and Group 2a Equipment at the Facilities in accordance with the Final Commissioning Programme and in accordance with requirements of Schedule Part 9 (Outline Commissioning Programme).

        - If hubco requires an item of Group 2 Equipment to be delivered on a date other than that set out in the Final Commissioning Programme, hubco shall give the Authority not less than twenty five (25) Business Days prior written notice of the date upon which hubco requires the Authority to procure the delivery for each item of Group 2 Equipment to be installed by hubco in accordance with paragraph 5.2.

        - Following delivery of the Group 2 Equipment pursuant to paragraph 4.1 above, hubco shall procure the safe and appropriate storage of the same until the completion of installation by hubco.

        - hubco shall at its own cost procure, install and commission the Group 2a Equipment at the Facilities as set out in the Final Commissioning Programme.

        - hubco shall, without prejudice to the Authority’s rights and obligations under Clause 13, allow the Authority and/or any Authority Party, access to the Site, or procure that access is given, in accordance with the Final Commissioning Programme to enable the Authority and/or any Authority Party, to install the relevant Group 3 Equipment. Subject to paragraphs 4.8 to 4.10, hubco shall ensure that neither it nor any hubco Party shall interfere with, hinder or delay the Authority or any Authority Party in undertaking the installation of the Group 3 Equipment.

      - GENERAL PROVISIONS

        - Where either:

          - hubco is unable to install and/or place an item of Group 2 Equipment because it is faulty; or

          - the Authority is unable to supply and/or procure any item of Group 2 Equipment required to be installed by hubco; or

          - the Authority has failed to supply and/or procure, install and/or place or commission any item of Group 3 Equipment,

the parties agree that hubco shall continue with the Project Operations as though such supply and/or procurement, installation and/or placement and/ or commissioning had occurred and any such delay shall not prevent the issue of the Certificate of Completion [of the relevant Phase].

        - To the extent that any changes to the Facilities once completed are required to facilitate any delayed supply and/or procurement, installation and/or placement and/ or commissioning of such Group 2 Equipment or Group 3 Equipment, such change shall require the issue of a Variation in accordance with Schedule Part 13 (Variation Procedure).

        - To avoid doubt, where such Group 2 Equipment is faulty due to the acts or omissions of hubco or any hubco Party, then hubco shall reimburse the Authority for any costs reasonably and properly incurred by the Authority in procuring the repair or replacement of an item of Group 2 Equipment within 20 Business Days of receipt of a demand thereof together with supporting information.

APPENDIX 1 - EQUIPMENT LIST

[The Equipment List is the Equipment List in the Agreed Form]

APPENDIX 2 - EQUIPMENT RESPONSIBILITY MATRIX

RESPONSIBILITIES MATRIX

Each Group of Equipment shall be supplied, installed and commissioned in accordance with the allocation of responsibility specified in the table below, and subject to and in accordance with the provisions of this Schedule Part 10, together with the requirements of Schedule Part 9 (Outline Commissioning Plan) and the Final Commissioning Programme:

| Group | Supplied/ Procured | Installed/ Placed | Commissioned |
| --- | --- | --- | --- |
| Group 1 Equipment | hubco | hubco | hubco |
| Group 2 Equipment | Authority | hubco | Authority |
| Group 2a Equipment | hubco | hubco | hubco |
| Group 3 Equipment | Authority | Authority | Authority |

- DEVELOPMENT AMOUNT ANALYSIS

- [insert breakdown of Development Amount which will dictate the drawdown by hubco of the Development Amount over the period of the Project.]

- INSURANCE REQUIREMENTS

This Schedule Part 12 comprises-

Section 1:	Policies to be taken out by hubco

Section 2:	Policies to be taken out by the Authority

Section 3:	Endorsements

Section 4:	Broker’s Letter of Undertaking

## POLICIES TO BE TAKEN OUT BY HUBCO AND MAINTAINED PRIOR TO COMMENCEMENT OF THE WORKS AND TO BE MAINTAINED FOR THE PERIODS SPECIFIED IN THIS SCHEDULE PART 12.

Common to each policy in Section 1 (unless stated otherwise):

Insureds:-

- Authority

- hubco

- Contractor

- Construction sub-contractors of any tier

- Consultants - for their site activities only,

each for their respective rights and interests in the Project.

- CONTRACTORS’ ‘ALL RISKS’ INSURANCE (CAR)

  - Insured Property

The permanent and temporary works, materials [(including but not limited to equipment supplied by the Authority], goods, plant and equipment for incorporation in the works (other than constructional plant, tools, accommodation and equipment belonging to or the responsibility of the Contractor or the construction sub-contractors) and all other property used or for use in connection with works associated with the Project ("The Insured Property").

  - Coverage

“All risks” of physical loss or damage to the Insured Property unless otherwise excluded.

  - Sum Insured

At all times an amount not less than the full reinstatement or replacement value of the Insured Property, but not less than £[                 ] plus provision to include extensions as appropriate.

  - Maximum Deductible

£ [     ]

  - Territorial Limits

United Kingdom including offsite storage and during inland transit.

  - Period of Insurance

From the date of this Agreement until the Actual Completion Date and thereafter in respect of defects liability until expiry of the [12] months defects liability period.

  - Cover Features & Extensions

    - Terrorism.

    - Munitions of war clause.

    - Additional costs of completion clause.

    - Professional fees clause.

    - Debris removal clause.

    - 72 hour clause.

    - European Union local authorities clause.

    - Free issue materials clause.

    - [10]% escalation clause.

    - Automatic reinstatement of sum insured clause.

    - Loss minimisation.

  - Principal Exclusions

    - War and related perils (UK market agreed wording).

    - Nuclear/radioactive risks (UK market agreed wording).

    - Pressure waves caused by aircraft and other aerial devices travelling at sonic or supersonic speeds.

    - Wear, tear and gradual deterioration.

    - Consequential financial losses.

    - Cyber risks.

    - Inventory losses.

    - Fraud and employee dishonesty.

    - DE5/ DE3 drop down option.

- Construction Third Party Liability Insurance

  - Interest

To indemnify the Insured in respect of all sums that they may become legally liable to pay (including claimant’s costs and expenses) as damages in respect of accidental:

    - death, or bodily injury, illness, death, disease contracted by any person;

    - loss or damage to property;

    - interference to property or any easement right of air, light, water or way or the enjoyment or use thereof by obstruction, trespass, nuisance, loss of amenities, or any like cause.

happening during the Period of Insurance and arising out of or in connection with the Project.

  - Limit of Indemnity

Not less than £[  ]m in respect of any one occurrence, the number of occurrences being unlimited, but in the aggregate in respect of pollution liability.

  - Maximum Deductible

£[	] for each and every occurrence of property damage. (Personal injury claims will be paid in full).

  - Territorial Limits

UK [and elsewhere in the world in respect of non manual visits].

  - Jurisdiction

Worldwide excluding the USA and Canada.

  - Period of Insurance

As per the Contractors’ “All Risks” Insurance, including the defects liability period.

  - Cover Features & Extensions

    - Munitions of war.

    - Cross liability clause.

    - Contingent motor.

    - Legal defence costs.

  - Principal Exclusions

    - Liability for death, illness, disease or bodily injury sustained by employees of the insured.

    - Liability arising out of the use of mechanically propelled vehicles whilst required to be compulsorily insured by legislation in respect of such vehicles.

    - Liability in respect of predetermined penalties or liquidated damages imposed under any contract entered into by the Insured.

    - Liability in respect of loss or damage to property in the care, custody and control of the insured but this exclusion is not to apply to all property belonging to the Authority which is in the care, custody and control of another Insured.

    - Events more properly covered under a professional indemnity policy.

    - Liability arising from the ownership, possession or use of any aircraft or marine vessel.

    - Liability arising from seepage and pollution unless caused by a sudden, unintended and unexpected occurrence.

    - Losses indemnified under the CAR policy or DSU policy.

## POLICIES TO BE TAKEN OUT BY THE AUTHORITY AND MAINTAINED PRIOR TO COMMENCEMENT OF THE WORKS AND TO BE MAINTAINED FOR THE PERIODS SPECIFIED IN THIS SCHEDULE PART 12.

Common to all policies in Section 2 (unless stated otherwise):

Insureds:-

- Authority

- hubco

- Contractor

- Construction sub-contractors of any tier

- Consultants - for their site activities only,

each for their respective rights and interests in the Project.

- EXISTING STRUCTURES INSURANCE

  - Insured Property

Any existing structures owned by the Authority or in respect of which the Authority is responsible and any contents thereof owned by the Authority or for which the Authority is responsible ("The Insured Property").

  - Coverage

“All risks” of physical loss or damage to the Insured Property unless otherwise excluded.

  - Sum Insured

At all times an amount not less than the full reinstatement or replacement value of the Insured Property, but not less than £[                 ] plus provision to include extensions as appropriate.

  - Maximum Deductible

£ [     ]

  - Territorial Limits

United Kingdom including offsite storage and during inland transit.

  - Period of Insurance

From the date of this Agreement until the Actual Completion Date and thereafter in respect of defects liability until expiry of the [12] months defects liability period.

  - Cover Features & Extensions

    - Terrorism.

    - Munitions of war clause.

    - Additional costs of completion clause.

    - Professional fees clause.

    - Debris removal clause.

    - 72 hour clause.

    - European Union local authorities clause.

    - Free issue materials clause.

    - [10]% escalation clause.

    - Automatic reinstatement of sum insured clause.

    - Loss minimisation.

  - Principal Exclusions

    - War and related perils (UK market agreed wording).

    - Nuclear/radioactive risks (UK market agreed wording).

    - Pressure waves caused by aircraft and other aerial devices travelling at sonic or supersonic speeds.

    - Wear, tear and gradual deterioration.

    - Consequential financial losses.

    - Cyber risks.

    - Inventory losses, fraud and employee dishonesty.

- ENDORSEMENTS

Unless the context otherwise requires defined terms set out in the following endorsements shall have the meaning set out in this Agreement.

Endorsement 1

Cancellation

This policy shall not be cancelled or terminated before the original expiry date is to take effect except in respect of non-payment of premium.

The insurer shall by written notice advise the Authority:

- at least 30 days before any such cancellation or termination is to take effect;

- at least 30 days before any reduction in limits or coverage or any increase in deductibles is to take effect; and

- of any act or omission or any event of which the insurer has knowledge and which might invalidate or render unenforceable in whole or in part this policy.

Endorsement 2

Multiple Insured/Non-Vitiation Clause

Each of the parties comprising the insured shall for the purpose of this policy be considered a separate co-insured entity, insured on a composite basis, with the words "the insured" applying to each as if they were separately and individually insured provided that the total liability of the insurers under each section of this policy to the insured collectively shall not (unless the policy specifically permits otherwise) exceed the limit of indemnity or amount stated to be insured under that section or policy.  Accordingly, the liability of the insurers under this policy to any one insured shall not be conditional upon the due observance and fulfilment by any other insured party of the terms and conditions of this policy or of any duties imposed upon that insured party relating thereto, and shall not be affected by any failure in such observance or fulfillment by any such other insured party.

It is understood and agreed that any payment or payments by insurers to any one or more of the insureds shall reduce, to the extent of that payment, insurers' liability to all such parties arising from any one event giving rise to a claim under this policy and (if applicable) in the aggregate.

Insurers shall be entitled to avoid liability to or (as may be appropriate) claim damages from any insured party in circumstances of fraud misrepresentation non-disclosure or material breach of warranty or condition of this policy (each referred to in this clause as a “Vitiating Act”) committed by that insured party save where such misrepresentation non-disclosure or breach of warranty or condition was committed innocently and in good faith.

For the avoidance of doubt it is however agreed that a Vitiating Act committed by one insured party shall not prejudice the right to indemnity of any other insured who has an insurable interest and who has not committed the Vitiating Act.

Insurers hereby agree to waive all rights of subrogation and/or recourse which they may have or acquire against any insured party (together with their employees and agents) except where the rights of subrogation or recourse are acquired in consequence of a Vitiating Act in which circumstances insurers may enforce such rights against the insured responsible for the Vitiating Act notwithstanding the continuing or former status of the vitiating party as an insured.

Notwithstanding any other provision of this policy or any other document or any act and/or omission by any insured party insurers agree that:

(1) no party other than the Authority has any authority to make any warranty, disclosure or representation in connection with this policy on behalf of the Authority;

(2) where any warranty, disclosure or representation is required from the Authority in connection with this policy insurers will contact the Authority in writing (in accordance with Endorsement 3 to the Contract) and set out expressly the warranty, disclosure and/or representation required within a reasonable period of time from the Authority (regarding itself); and

(3) save as set out in a request from insurers to the Authority in accordance with (2) above, the Authority shall have no duty to disclose any fact or matter to insurers in connection with this policy save to the extent that for the Authority not to disclose a fact or matter would constitute fraudulent misrepresentation and/or fraudulent non-disclosure.

Endorsement 3

Communications

All notices or other communications under or in connection with this policy shall be given to each insured (and the Authority) in writing or by facsimile.  Any such notice will be deemed to be given as follows:

- if in writing, when delivered;

- if by facsimile, when transmitted but only if, immediately after transmission, the sender’s facsimile machine records a successful transmission has occurred.

The address and facsimile number of the Authority for all notices under or in connection with this policy are those notified from time to time by the Authority for this purpose to hubco at the relevant time.  The initial address and facsimile number of the Authority are as follows:

| 1. The Authority: |  |
| --- | --- |
| Address: |  |
| Facsimile No: [ ] |  |
| Attention: | The Chief Executive from time to time of the Authority |

It is further agreed that a notice of claim given by the Authority or any other insured shall in the absence of any manifest error be accepted by the insurer as a valid notification of a claim on behalf of all insureds.

Endorsement 4

Loss Payee (applicable only to the Physical Damages Policies)

All proceeds of this policy shall be payable without deduction or set-off to the Insurance Proceeds Account.

Endorsement 5

Primary Insurance

It is expressly understood and agreed that this policy provides primary cover for the insured parties and that in the event of loss destruction damage or liability covered by this policy which is covered either in whole or in part under any other policy or policies of insurance effected by or on behalf of any of the insured parties the insurers will indemnify the insured parties as if such other policy or policies of insurance were not in force and the insurers waive their rights of recourse if any against the insurers of such other policy or policies of insurance.

Endorsement 6

Ringfencing

The level of any indemnity available to an insured party under this policy in relation to any claim(s) concerning the Project shall not be affected and/or reduced by any claim(s) unrelated to the Project.

- BROKER’S LETTER OF UNDERTAKING

To:        The Authority

Dear Sirs

Agreement dated [	] entered into between [                     ] Limited (the “hubco”) and [                       ] (the “Authority”) (the “Agreement”)

- We refer to the Agreement.  Unless the context otherwise requires, terms defined in the Agreement shall have the same meaning in this letter.

- We act as insurance broker to hubco in respect of the Insurances and in that capacity we confirm that the Insurances which are required to be procured pursuant to clause [  ] and schedule [  ] of the Agreement:

  - where appropriate name you and such other persons as are required to be named pursuant to the Agreement for their respective interests;

  - are, in our reasonable opinion as insurance brokers, as at today’s date, in full force and effect in respect of all the matters specified in the Agreement; and

  - that all premiums due to date in respect of the Insurances are paid and the Insurances are, to the best of our knowledge and belief, placed with insurers which, as at the time of placement, are reputable and financially sound.  We do not, however, make any representations regarding such insurers’ current or future solvency or ability to pay claims; and that

  - the endorsements set out in Section 3 (Endorsements) of Schedule Part 12 (Insurance Requirements) of the Agreement are as at today’s date in full force and effect in respect of the Insurances.

- We further confirm that the attached cover notes confirm this position.

- Pursuant to instructions received from hubco and in consideration of your approving our appointment [or continuing appointment] as brokers in connection with the Insurances, we hereby undertake in respect of the interests of the Authority in relation to the Insurances:

  - Notification Obligations

    - to notify you at least 30 (thirty) days prior to the expiry of any of the Insurances if we have not received instructions from hubco to negotiate renewal and in the event of our receiving instructions to renew, to advise you promptly of the details thereof;

    - to notify you at least 30 (thirty) days prior to ceasing to act as brokers to hubco unless, due to circumstances beyond our control, we are unable to do so in which case we shall notify you as soon as practicable; and

    - to pay into the Insurance Proceeds Account without set off or deduction of any kind for any reason all payments in respect of claims received by us from insurers in relation to the Insurances specified in Clauses 40.1 to 40.3 of the Agreement.

  - Advisory Obligations

    - to notify you promptly of any default in the payment of any premium for any of the Insurances;

    - to notify you if any insurer cancels or gives notification of cancellation of any of the Insurances, at least 30 (thirty) days before such cancellation is to take effect or as soon as reasonably practicable in the event that notification of cancellation takes place less than 30 (thirty) days before it is to take effect;

    - to notify you of any act or omission, breach or default of which we have knowledge which in our reasonable opinion may either invalidate or render unenforceable in whole or in part any of the Insurances or which may otherwise materially impact on the extent of cover provided under the Insurances; and

    - to advise hubco of its duties of disclosure to insurers and to specifically advise upon:

      - the facts, circumstances and beliefs that should generally be disclosed to insurers; and

      - the obligation not to misrepresent any facts, matters or beliefs to insurers.

  - Disclosure Obligations

    - to disclose to insurers all information made available to us from any source and any fact, change of circumstances or occurrence made known to us from any source which in our reasonable opinion is material to the risks insured against under the Insurances and which properly should be disclosed to insurers as soon as practicable after we become aware of such information, fact, change of circumstance or occurrence whether prior to inception or renewal or otherwise; and

    - to treat as confidential all information so marked or otherwise stated to be confidential and supplied to us by or on behalf of hubco or the Authority and not to disclose such information, without the prior written consent of the supplier, to any third party other than those persons who, in our reasonable opinion have a need to have access to such information from time to time, and for the purpose of disclosure to the insurers or their agents in respect of the Insurances in discharge of our obligation set out at Clause 4.3.1 of this letter. Our obligations of confidentiality shall not conflict with our duties owed to hubco and shall not apply to disclosure required by an order of a court of competent jurisdiction, or pursuant to any applicable law, governmental or regulatory authority having the force of law or to information which is in the public domain.

  - Administrative Obligations

    - to hold copies of all documents relating to or evidencing the Insurances, including but without prejudice to the generality of the foregoing, insurance slips, contracts, policies, endorsements and copies of all documents evidencing renewal of the Insurances, payment of premiums and presentation and receipt of claims;

    - to supply to the Authority and/or its insurance advisers (or the Authority’s or its insurance advisers’ authorised representatives) promptly on written request copies of the documents set out in Clause 4.4.1 of this letter, and to the extent available, to make available to such persons promptly upon the Authority’s request the originals of such documents;

    - to administer the payment of premiums due pursuant to the Insurances such that, in so far as we hold appropriate funds, all such premiums shall be paid to insurers in accordance with the terms of the Insurances;

    - to administer the payment of claims from insurers in respect of the Insurances (the “Insurance Claims”) including:

      - negotiating settlement of Insurance Claims presented in respect of the Insurances;

      - collating and presenting all information required by insurers in relation to Insurance Claims presented in respect of the Insurances, and

      - insofar as it is relevant and practicable, liaising with and reporting to each Authority throughout the settlement, payment and administration of such Insurance Claims.

    - to advise the Authority promptly upon receipt of notice of any material changes which we are instructed to make in the terms of the Insurances and which, if effected, in our opinion as Insurance Brokers would result in any material reduction in limits or coverage or in any increase in deductibles, exclusions or exceptions;

    - to advise the Authority in advance of any change to the terms of, or any lapse, non-renewal and/or cancellation of any policy maintained in respect of the Insurances; and

    - to use our reasonable endeavours to have endorsed on each and every policy evidencing the Insurances (when the same is issued) endorsements substantially in the form set out in Section 3 to Schedule Part 12 of the Agreement.

  - Insurance Cost Reporting Procedures

    - to prepare following request, at the expense of hubco, a Joint Insurance Cost Report on behalf of both hubco and the Authority in accordance with the Insurance Review Procedure as set forth in Section 4 of Schedule Part 12 of the Agreement. We shall ensure that the information in the Joint Insurance Cost Report is fairly represented, based on the information available to us.

- Notification Details

  - Our obligations at Clause 4 of this letter to notify or inform you shall be discharged by providing the requisite information in hard copy to:

[ ] Authority

  - We shall supply further letters substantially in this form on renewal of each of the Insurances and shall supply copies of such letters to those parties identified to us by the Authority for such purposes.

- This letter shall be governed by and construed in accordance with the law of Scotland.

Yours faithfully

--------------------

For and on behalf of [hubco’s broker]

- Variation Procedure

- Interpretation

For the purposes of this Agreement, and in particular this Schedule Part 13 (Variation Procedure), unless the context requires otherwise:

| "Authority Works Variation" | means a variation to the Works initiated by the Authority in accordance with this Schedule Part 13 (Variation Procedure) |
| --- | --- |
| "Authority Works Variation Confirmation" | means a Variation Confirmation pursuant to paragraph 4.4 of Section 2 of Schedule Part 13 (Variation Procedure) in respect of a Authority Works Variation |
| "Authority Works Variation Enquiry" | has the meaning given in paragraph 2.1.1 of Section 2 of Schedule Part 13 (Variation Procedure) |
| "Qualifying Variation" | means a Variation for which a Variation Confirmation has been issued and the supplementary agreement referred to in paragraph 4.4 of Section 2 of Schedule Part 13 (Variation Procedure) has become unconditional in all respects |
| "Variation" | means an Authority Works Variation |
| "Variation Confirmation" | has the meaning given in paragraph 4.4 of Section 2 of Schedule Part 13 (Variation Procedure) |
| "Variation Enquiry" | has the meaning given in paragraph 2.1 of Section 2 of Schedule Part 13 (Variation Procedure) |

- Variations

- GENERAL

Subject to receiving the Variation Confirmation issued in accordance with the terms of this Schedule Part 13 and to any Consent which must be obtained or modified being so obtained or modified and subject to the other provisions of this Schedule Part 13, hubco shall be under a duty to implement a Variation.  hubco will not be entitled to any payment or compensation for or in respect of a Variation save as provided in accordance with this Schedule Part 13.

- Variation Enquiries

  - A Variation Enquiry shall be a document issued by the Authority's Representative which:

    - states on its face that it is a Variation Enquiry; and

    - specifies the nature of the Authority Works Variation and which of the provisions of the Authority's Construction Requirements and/or hubco's Proposals are required to be amended to accommodate the relevant Authority Works Variation.

  - The Authority's Representative may not issue a Variation Enquiry other than in accordance with the provisions of this Section 2.

- hubco Response to Variation Enquiry

Preliminary Indicative Information

  - Prior to giving a notice referred to in paragraph 3.2 of this Section 2:

    - hubco may at its option within ten (10) Business Days of receipt of a Variation Enquiry:

      - give to the Authority in good faith a preliminary non-binding indication of the estimated cost of implementing the Variation and provide such other information about the Variation as is available to hubco and which it believes is useful to the Authority; and

      - such information shall include in particular hubco's estimated effect on the date when the Actual Completion Date will occur;

    - if hubco provides an indication referred to in paragraph 3.1.1(a), the Authority shall within a further five (5) Business Days of its receipt confirm whether or not it wishes hubco to proceed to respond to the Variation Enquiry in accordance with provisions of paragraph 3.2.

hubco Response

  - Within one (1) month of receipt of a Variation Enquiry or (if the provisions of paragraph 3.1.2 apply) within one (1) month of the Authority confirming that it wishes hubco to proceed with responding to the Variation Enquiry or in either case such longer period as may be agreed by the parties or determined in accordance with Schedule Part 15 (Dispute Resolution Procedure) as reasonable given the nature of the Variation Enquiry and all other relevant considerations, hubco shall either:

    - give notice to the Authority's Representative that it objects to the Variation Enquiry stating the grounds of the objection.  hubco may only object to a Variation Enquiry on one or more of the following grounds:

      - that implementation of the Variation would materially and adversely affect the health and safety of any person; or

      - that implementation of the Variation would:

        - infringe any Law; or

        - cause any existing Consent (which is not reasonably likely, on a balance of probabilities, to be capable of modification) to be revoked; or

        - require a new Consent which will not (using all reasonable endeavours) be obtainable; or

        - have a material and adverse effect on the carrying out of the Works (except those Works which have been specified as requiring to be amended in the Variation Enquiry) in a manner not compensated pursuant to this Schedule Part 13; or

        - be a departure from Good Industry Practice; or

      - that the Authority does not have the legal power or capacity to require the Variation to be implemented or to do anything envisaged by this Schedule Part 13 in respect of, or in connection with, the Variation; or

      - that the Variation would, if implemented, result in a change in the essential nature of the Facilities; or

      - that the Variation Enquiry does not comply with paragraph 2 of this Section 2; or

      - that the information contained in the Variation Enquiry is inadequate to enable hubco to respond in accordance with paragraph 3.2.2 below (on the assumption, whether or not the case, that it has no objection under paragraphs (a) to (e));

or

    - give notice to the Authority's Representative stating:

      - the steps which hubco proposes to take to implement the Variation giving such level of detail as is reasonable and appropriate in all the circumstances hubco's estimated increase or decrease in the Development Amount calculated in accordance with paragraph 1 of Section 3 of this Schedule Part 13 in respect of the Variation having regard to all relevant facts and matters, including any costs (by line item) incurred or to be incurred under paragraph 5 of this Section 2.

      - whether, in the view of hubco, implementing the Authority Works Variation Enquiry would be likely to prevent the Actual Completion Date from occurring at the Completion Date (prior to any adjustment being made to the Completion Date by reason of the implementation or proposed implementation of the Authority Works Variation) and, if so, giving an estimate of the extension of time likely to be required (subject to any further time required to obtain or amend any Consent);

      - any Consent which must be obtained or amended for the Variation to be implemented and the latest date by which hubco must receive a Variation Confirmation and any such Consent must be obtained or modified for the matters set out in 3.2(i) to paragraph 3.2(iii) inclusive above to remain valid, such date being a reasonable period of time after service of the notice by hubco under this paragraph 3.2.2 to enable the Authority's Representative to consider any matter under paragraph 4.1.3 below; and

      - such amendments to the provisions of this Agreement which are necessary as a consequence of the Variation, the objective of such amendments being to ensure that (save for the obligation of the Authority to make payments or altered payments in respect of the Variation or any other adverse consequences for the Authority arising from the Variation itself) the parties are in no better and no worse position in relation to the Project than they would have been in if such Variation had not been implemented.

- Resolution of Disputes and Variation Confirmation

  - Within ten (10) Business Days of receipt of the notice referred to in paragraph 3.2 of this Section 2:

    - if hubco has served a notice under paragraph 3.2.1 but the Authority's Representative does not accept that hubco is entitled to object to the Variation Enquiry, the matter may be referred for resolution in accordance with Schedule Part 15 (Dispute Resolution Procedure) and if the Dispute is resolved in favour of the Authority then hubco shall forthwith give the notice referred to in paragraph 3.1.2;

    - if the contents of the notice under paragraph 3.1.2 shall be to the satisfaction of the Authority's Representative he shall so inform hubco and the parties shall proceed to agree or determine all the matters referred to in paragraph 4.3 of this Section 2; or

    - if he wishes to consider further any matter, the Authority's Representative may give notice to that effect to hubco provided that if no response is given under paragraph 4.1.2 of this paragraph 4.1 prior to the date referred to in paragraph (d), (Latest date for Variation Confirmation) the Variation Enquiry shall be deemed to have been withdrawn; or

    - if any aspect of a notice under paragraph 3.2.2 shall not be to the Authority's Representative's satisfaction he shall so notify hubco and shall specify the alterations to the notice which he would require in order to be so satisfied.

  - If the Authority's Representative has given a notice referred to in paragraph 4.1.4 of this Section 2 then, unless agreement has been reached with hubco within a further ten (10) Business Days from the date of issue of that notice (in which case the Authority's Representative shall proceed pursuant to paragraph 4.1.2 of this Section 2) or the Authority's Representative withdraws the Variation Enquiry, the outstanding Dispute shall be referred for resolution in accordance with Schedule Part 15 (Dispute Resolution Procedure) to be determined (if the Authority's Representative so requires it) concurrently with any matter referred to in paragraph 4.3 of this Section 2.  In seeking to reach agreement and/or in so determining a Dispute pursuant to this paragraph or to paragraph 4.3, the criterion to be applied to resolve any such dispute (except where another criterion or other criteria are expressly or by implication stated in this Schedule Part 13) shall be that hubco shall be in no worse position in relation to the Project and the Works after the Variation is implemented than it would have been in had the Variation not been implemented.

  - The parties shall meet and seek to agree the matters referred to in paragraphs 4.3.1 and 4.3.2 in relation to the Variation, failing which agreement being reached in a reasonable period of time, either party may refer any matter for resolution in accordance with Schedule Part 15 (Dispute Resolution Procedure).  The matters to be agreed or determined are:

    - in relation to the terms of the Variation:

      - any alteration to the Completion Date;

      - the increase or decrease in the Development Amount calculated in accordance with paragraph 1 of Section 3 of this Schedule Part 13;

      - any amendment to the provisions of this Agreement which is referred to in paragraph 3.2.2(d)

in each case occasioned by the Variation; and

    - the terms of a supplementary agreement under which:

      - as required to give effect to the Variation in each case, the Authority's Construction Requirements and/or hubco's Proposals are amended; and/or provision is made for the amendment of the as-built drawings and specifications, including room data sheets and other records, drawings, operating and maintenance manuals, the asset register, the health and safety file; and

      - the matters referred to in paragraph 4.3 of this Section 2 are fully recorded and given effect as amendments to and/or other variations to the provisions of this Agreement and/or such other documentation as is necessary.

  - Upon the agreement or determination of all the matters referred to in paragraph 4.3, and upon any Consent having been modified or obtained, in accordance with paragraph 5 in terms reasonably satisfactory to hubco and the Authority, the Authority's Representative shall, by notice (a "Variation Confirmation") confirm the Variation.  Upon the issue of the Variation Confirmation, the parties shall enter into the supplementary agreement referred to in paragraph 4.3.

  - Upon the Variation Confirmation being issued and the supplementary agreement referred to in paragraph 4.4 becoming unconditional in all respects:

    - the relevant Variation shall be a Qualifying Variation; and

    - the rights and liabilities of the parties under this Agreement shall be construed accordingly.

- Consent and Variations

  - If it shall be necessary to obtain or amend any Consent in respect of any Variation then the Authority shall use all reasonable endeavours to obtain and, where the co-operation and involvement of both parties is required, hubco shall use all reasonable endeavours to assist and co-operate in obtaining, such Consent.  The provisions of Clause 11 (Consents and Planning Approval) shall apply in relation to Planning Permissions, save that the time taken to obtain such Consent shall be taken into account for the purposes of determining any extension of time and any other amounts payable by the Authority to hubco under this Schedule Part 13.

  - If it shall not be possible to obtain any such Consent as is referred to in paragraph 5.1 above by the latest date when a Variation Confirmation could be given with regard to the Variation in question in accordance with the notice by hubco pursuant to paragraph 3.2.2 of this Section 2 of Schedule Part 13, the Variation Enquiry shall be deemed to be withdrawn and the provisions of paragraph 6 of this Section 2 of Schedule Part 13 shall apply accordingly.

- Withdrawal

The Authority's Representative may withdraw a Variation Enquiry at any time prior to the issue of a Variation Confirmation, or, in the case of a Variation which requires the obtaining of, or an amendment to any Consent, the date when the last such Consent is granted, whichever shall be later.  In the case of a withdrawal or deemed withdrawal the Authority shall pay hubco all out of pocket expenses reasonably and properly incurred by hubco in connection with the Variation.

- Payment in respect of Variations

Adjustment to Contract Sum

- The increase or reduction in the Development Amount arising out of a Qualifying Variation shall be calculated on the basis of a fair and reasonable valuation of the aggregate of any increased design and construction costs (including insurance costs and costs that arise as a consequence of the effect on the regular progress of the Works) less the aggregate of any reduction in design and construction costs which result directly from the Qualifying Variation.

- Where the effect of a Qualifying Variation is an increase in the Development Amount, then as part of the matters to be agreed pursuant to paragraph 4.3 of Section 2:

  - the Authority and hubco shall agree:

    - a payment schedule in respect of the payment of such increase reflecting the amount and timing of the costs to be incurred by the Contractor in carrying out the Qualifying Variation to the extent borne by hubco; and

    - where payment for part of the Qualifying Variation reflects the carrying out of, or specific progress towards, an element within the Qualifying Variation, an objective means of providing evidence confirming that the part of the Qualifying Variation corresponding to each occasion when payment is due under the payment schedule appears to have been duly carried out,

(such payment schedule and evidence to be determined in accordance with Schedule Part 15 (Dispute Resolution Procedure) in the event of the Authority and hubco failing to agree as to its terms) provided that where all or any part of the Qualifying Variation is being carried out by a third party under a contract with hubco, subject to the terms of any contract between the hubco and that third party in relation to the implementation of the Qualifying Variation having been approved by the Authority (such approval not to be unreasonably withheld), the process under Schedule Part 15 (Dispute Resolution Procedure) shall not determine a payment schedule or evidence which would not enable hubco to be funded by the Authority in time to make payments to that third party in accordance with its contract with the Authority.

  - and the relevant amendments to this Agreement shall reflect that:

    - the Authority shall make payment to hubco in accordance with the procedures for payment of interim payments in accordance with Clause 27.

    - Not used.

- RECORD PROVISIONS

- General Requirements

- hubco shall retain and maintain all the records (including superseded records) referred to in Section 2 of this Schedule Part 14 in accordance with this Section 1 of Schedule Part 14, the requirements of Good Industry Practice, in chronological order, in a form that is capable of audit and at its own expense.  hubco shall make such records available for inspection to the Authority where it has reasonable cause for requiring such records, on giving reasonable notice shall provide such facilities as the Authority may reasonably require for its representatives to visit any place where the records are held and examine the records maintained under this Schedule Part 14.

- Wherever practical, original records shall be retained and maintained in hard copy form.  True copies of the original records may be kept by hubco where it is not practicable to retain original records.

- Those records relating to the Project Operations (including the design, construction and development, of the Facilities) shall be retained for the duration of this Agreement.

- Financial and other records (including without limitation all information provided in support of any Variation) shall be retained and maintained by hubco for a period of at least six (6) years after the Actual Completion Date in sufficient detail, in appropriate categories and generally in such a manner to enable hubco to comply with its obligations under Clause 48 (Information and Audit Access).

- Where hubco wishes to dispose of any records maintained as provided in this Part of this Schedule or in respect of which the required period for their retention has expired, then hubco shall notify the Authority and if, within forty (40) Business Days of such notice, the Authority elects to receive certain of those records, then hubco shall deliver up such records to the Authority in the manner and at the location as the Authority shall reasonably specify, and the costs of retaining those records in safe storage and delivering up the same shall be borne by hubco.

- Subject to paragraph 5, for a period of not more than six (6) years following the termination for whatever reason of this Agreement, hubco shall retain in safe storage all such records as are referred to in Section 2 of this Schedule Part 14 which were in existence at the date of termination of this Agreement.  On the expiry of such period or at the earlier request of the Authority, hubco shall deliver up all those records (or where those records are required by statute to remain with hubco or a Contracting Associate of hubco, copies thereof) to the Authority in the manner and at the location as the Authority shall reasonably specify.  The Authority shall make available to hubco all the records hubco delivers up pursuant to this paragraph subject to reasonable notice.  The costs of retaining those records in safe storage and delivering up the same shall be borne[:

  - by hubco where the termination arises as a result of a hubco Event of Default; and

  - by the Authority where the termination arises for any other cause.

- Any drawings required to be made or supplied pursuant to this Agreement shall be of a size appropriate to show the detail to be depicted clearly without magnifying aids and shall conform to British Standards 1192 or 308 or equivalent as appropriate.  Where by prior agreement the Authority has agreed to accept microfilm, microfiche or other storage media (which must include secure back up facilities), drawings and other documents shall be made or supplied in such form as has been agreed.

- hubco shall use all reasonable endeavours to assist the Authority in its preparation of any report and/or return required pursuant to regulations, directions or guidance applicable to the Authority (in each case as amended replaced or consolidated from time to time) or as required by external agencies including without limitation, reports and returns regarding the physical condition of the Facilities, health and safety under the Fire (Scotland) Act 2005 and the Fire Safety (Scotland) Regulations 2006, relating to environmental health, by the Scottish Futures Trust[, Scottish Government Health Directorates] or the Scottish Government from time to time.

- Records to be kept

- This Agreement and the Project Documents including all amendments to such agreements.

- hubco shall at all times maintain a full record of particulars of the costs of performing the Project Operations.  This shall require hubco to keep (and where appropriate to procure that the sub-contractors shall keep) books of account in accordance with best accountancy practice with respect to this Agreement showing in detail:

  - administrative overheads;

  - payments to Sub-Contractors and to sub-contractors;

  - capital and revenue expenditure;

  - such other items as the Authority may reasonably require to conduct cost audits for verification of cost expenditure or estimated expenditure, for the purpose of Schedule  Part 13 (Variation Procedure),

and hubco shall have (and procure that the sub-contractors shall have) the books of account evidencing the items listed in paragraphs 2.1 to 2.4 available for inspection by the Authority (and any expert) upon reasonable notice, and shall present a report of these to the Authority as and when requested.

- All other documents, software or other information expressly referred to in this Agreement.

- Records relating to the appointment and supersession of the Authority's Representative and hubco's Representative.

- Project Data.

- Documents, drawings, design data or submissions raised in accordance with Schedule Part 7 (Review Procedure).

- Documents relating to planning applications, consents, refusals and appeals.

- Records relating to any specialist or statutory inspections of the Facilities, including any roadways.

- Notices, reports, results and certificates relating to completion of the Works and completion of the commissioning activities.

- Documents relating to events of Force Majeure, Delay Events and Relief Events and the consequences of the same.

- Documents submitted in accordance with Schedule Part 13 (Variation Procedure) and all documents provided in support.

- Documents related to referrals to the Dispute Resolution Procedure.

- Tax invoices and records related to Value Added Tax.

- Records required by Law (including in relation to Health and Safety matters and health and safety files prepared pursuant to CDM Regulations) and all Consents.

- Documents relating to insurance and insurance claims.

- All other records, notices or certificates required to be produced and/or maintained by hubco pursuant to this Agreement or any Project Document.

- DISPUTE RESOLUTION PROCEDURE

- The procedure set out in this Schedule Part 15 (the "Dispute Resolution Procedure") shall apply to any dispute, claim or difference arising out of or relating to this Agreement ("Dispute") except where it has been excluded from this procedure by any express term of this Agreement.

- This Dispute Resolution Procedure shall not impose any pre-condition on either party or otherwise prevent or delay either party from commencing proceedings in any court of competent jurisdiction in relation to any Dispute in which that party requires either:

  - an order (whether interim or final) restraining or interdicting the other party from doing any act or compelling the other party to do any act; or

  - a decree for a liquidated sum to which there is no stateable defence.

- MEDIATION

  - Without prejudice to paragraph 4 below, if the parties have been unable between themselves to resolve the Dispute within twenty (20) Business Days of the Dispute arising, they may (if both parties so agree) refer the Dispute to mediation on such conditions as may be agreed between the parties.  Any mediation shall be completed within thirty (30) Business Days of such referral and any agreement arising therefrom shall be recorded in writing and signed by the parties and shall be final and binding to the extent set out in such agreement unless otherwise agreed by the parties.

  - For the avoidance of doubt, mediation shall not be a precondition to the commencement of adjudication or court proceedings.

- Adjudication

  - Either party may at any time (notwithstanding that other dispute resolution procedures are running concurrently) give the other party to the Dispute notice of its intention to refer the Dispute to adjudication (the "Notice of Adjudication").  The Party giving notice (the "Referring Party") shall by the same means of communication, send a copy of the Notice of Adjudication to an Adjudicator selected in accordance with paragraph 4.2 below.

  - The Adjudicator nominated to consider a Dispute referred to him shall be selected on a strictly rotational basis from the relevant panel of adjudicators appointed in accordance with the following:

    - there shall be a panel of adjudicators in respect of construction matters (the "Adjudication Panel"). All the adjudicators on the panel shall be wholly independent of hubco, the Authority, any relevant Sub-Contractor and any of the major competitors of hubco or relevant Sub-Contractor;

    - the Adjudication Panel shall be comprised of three (3) adjudicators as identified in paragraph 7 (Panel Members) who shall be selected jointly by hubco and the Authority.  Such selections shall take place within twenty-eight (28) days of the date of this Agreement;

    - if any member of the panel resigns or is otherwise no longer available to act as an adjudicator during the term of the Agreement, a replacement adjudicator shall be appointed by hubco and the Authority as soon as practicable, provided that no such appointment may be made under this paragraph 4.2.3 unless and until the Authority confirms in writing that the replacement adjudicator identified by the parties has been appointed pursuant to this Schedule Part 15;

    - if hubco and the Authority are unable to agree on the identity of the adjudicators to be selected for the panel or any replacement adjudicator(s), the Chairman (or Vice Chairman) for the time being of the Chartered Institute of Arbitrators Scottish Branch shall appoint such adjudicator(s) within seven (7) days of any application for such appointment by either party;

    - in the event that the first panel member is unable or unwilling to confirm acceptance of his appointment as Adjudicator or where he fails to respond within two (2) days of the date of the Notice of Adjudication, then the Referring Party shall invite the person next in line to act as Adjudicator.  In the event that the second panel member is unable or unwilling to confirm acceptance of his appointment as Adjudicator or where he fails to respond within four (4) days of the date of the Notice of Adjudication then the Referring Party may apply to the Chairman for the time being of the Royal Institute of Chartered Surveyors for Scotland who shall within seven (7) days of the Notice of Adjudication, nominate an Adjudicator (who shall also within the same period, confirm acceptance of his appointment as Adjudicator) to determine the Dispute described in the Notice of Adjudication.

  - The Referring Party shall, within seven (7) days of the date of the Notice of Adjudication, serve its statement of case (the "Referral Notice") on the Adjudicator (appointed pursuant to paragraph 4.2) and the other party to the Dispute (the "Responding Party").  The Referral Notice shall set out each element of the Referring Party's claim and the relief or remedy sought in sufficient detail so as to enable the Responding Party to understand and, where appropriate, respond to the claim and the Referral Notice shall be accompanied by copies of, or relevant extracts from, this Agreement and such other documents as the Referring Party intends to reply upon.  The date of the referral of the Dispute (the "Referral") shall be the date of the Referral Notice.

  - Within seven (7) days of appointment in relation to a particular Dispute, the Adjudicator shall establish the procedure and timetable for the adjudication.  The Adjudicator shall (subject to complying with paragraph 4.8) in his absolute discretion, consider whether a hearing is necessary in order to resolve the Dispute.  He shall establish the procedure and timetable subject to any limitation within this Agreement.  The parties shall comply with any request or direction of the Adjudicator in relation to the Adjudication.

  - The Adjudicator shall reach a decision on the Dispute within twenty-eight (28) days of the date of the Referral (or such other period as the parties may agree).  The Adjudicator may extend the period of 28 days by up to 14 days with the consent of the Referring Party.  Unless the parties agree otherwise, the Adjudicator shall give reasons for his decision.  Unless and until the Dispute is finally determined by court proceedings or by an agreement in writing between the parties, pursuant to paragraph 5.1 of this Schedule Part 15 the Adjudicator's decision shall be binding on both parties who shall forthwith give effect to the decision.

  - Subject to paragraph 6.4, the Adjudicator's costs of any reference shall be borne as the Adjudicator shall specify or, in default, equally by the parties.  Each party shall bear its own costs arising out of the adjudication, including legal costs and the costs and expenses of any witnesses.

  - The Adjudicator shall be deemed not to be an arbitrator but shall render his decision as an adjudicator and the law relating to arbitration shall not apply to the Adjudicator or his determination or the procedure by which he reached his determination.

  - The Adjudicator shall act fairly and impartially and may take the initiative in ascertaining the facts and the law.  The Adjudicator shall have the power to open up, review and revise any opinion, certificate, instruction, determination or decision of whatever nature given or made under this Agreement.

  - All information, data or documentation disclosed or delivered by a party to the Adjudicator in consequence of or in connection with his appointment as Adjudicator shall be treated as confidential.  The Adjudicator shall not, save as permitted by Clause 46 (Confidentiality), disclose to any person or company any such information, data or documentation and all such information, data or documentation shall remain the property of the party disclosing or delivering the same and all copies shall be returned to such party on completion of the Adjudicator's work.

  - The Adjudicator is not liable for anything done or omitted in the discharge or purported discharge of his functions as Adjudicator unless the act or omission is in bad faith.  Any employee or agent of the Adjudicator is similarly protected from liability.

- 4.10A.1 	The Adjudicator may on his own initiative or on the request of the Referring Party or Responding Party correct his decision so as to remove a clerical or typographical error arising by accident or omission.

- 4.10A.2 	Any correction of a decision shall be made within 5 days of the date upon which the Adjudicator’s decision was delivered to the parties.

- 4.10A.3 	Any correction of a decision shall form part of the decision.

  - If any Dispute raises issues which, in the opinion of hubco, is substantially the same as or connected with issues raised in a dispute or difference arising out of or relating to any other agreement (all such agreements being referred to as the "Related Agreements") between hubco and the Contractor which was or has been referred to adjudication (the "Related Adjudication") and an adjudicator has already been appointed (the "Related Adjudicator") then hubco may request that the Dispute be referred to the Related Adjudicator and paragraphs 4.12 to 4.14 shall apply.

  - Subject to paragraphs 4.13 and 4.14 below, in the event that a Related Adjudicator orders that a Dispute under this Agreement be consolidated with a Related Adjudication with which he is dealing under the Related Agreement, then:

    - with effect from the time of such order, the Dispute which shall be determined by the Related Adjudicator, who shall become the Adjudicator; and

    - such order shall be binding on hubco and the Authority and both of them shall acknowledge the appointment of the Related Adjudicator as the adjudicator of the Dispute, with hubco or the Authority (as the case may be) using its best endeavours to procure that the third party who is a party to the Related Agreement shall with effect from the time of such order comply with the requirements of the Related Agreement (including if applicable any requirement or direction of the Related Adjudicator appointed under such Related Agreement) as to the future conduct of the determination of the Dispute and the Related Adjudication; and

    - notwithstanding paragraph 4.6, hubco and the Authority shall be jointly responsible with the third party who is a party to the Related Agreement for the Related Adjudicator’s fees and expenses including those of any specialist consultant appointed under the adjudication procedure in the Related Agreement, in respect of the period in which the Dispute is consolidated with the Related Adjudication pursuant to an order of the Related Adjudicator (“Consolidated Adjudication Costs”).  hubco and the Authority agree that the Related Adjudicator shall have the discretion to make directions to require hubco, the Authority and the third party who is a party to the Related Agreement to pay or make contribution to the Consolidated Adjudication Costs in different proportions.  If no such directions are made, hubco, the Authority and the third party who is a party to the Related Agreement shall bear the Consolidated Adjudication Costs in equal shares, and if hubco, the Authority or the third party has paid more than such equal share, that party or third party shall be entitled to a contribution from the other party, parties or third party, as the case may be.

  - Notwithstanding anything to the contrary a Dispute under this Agreement may only be consolidated with a Related Adjudication, if the Related Adjudicator receives particulars of the Dispute within ten (10) days of the referral of the Related Adjudication to the Related Adjudicator under the Related Agreement.

  - Where hubco requests that a Dispute under this Agreement be consolidated (in terms of paragraph 4.11) with a Related Adjudication and heard by the Related Adjudicator, the Dispute may only be consolidated where the Authority has previously consented in writing to the identity of the Related Adjudicator appointed in respect of the Related Adjudication.  The Authority’s consent to such request shall not be unreasonably withheld and if the Authority refuses to consent, it must give reasons in writing for its refusal.  Should the Authority fail to respond within two (2) days of receipt of such a request it shall be deemed to have consented to the appointment of the Related Adjudicator.  Where the Related Adjudicator is on the Adjudication Panel at the time of the Referral then the Authority shall be deemed to have consented to the appointment of the Related Adjudicator.

- Court proceedings

  - Subject to paragraph 4 (Adjudication) disputes, to the extent not finally resolved pursuant to the procedures set out in the foregoing provisions of this Schedule Part 15 (Dispute Resolution Procedure) shall be referred to the Court of Session Edinburgh save where the Sheriff Courts have exclusive competence in which case they shall be referred to [insert relevant sheriff court] in the Sheriffdom of [insert relevant sheriffdom]. Where any Dispute is one to which Chapter 47 of the Rules of the Court of Session 1994 applies, any action to be pursued in the Court of Session in respect of such Dispute shall be pursued as a commercial action utilising the procedural rules prescribed for such an action in Chapter 47 of the Rules of the Court of Session 1994.

- Submissions in relation to Adjudication

  - If any Dispute raises issues which relate to any dispute between hubco and the Contractor arising under the Construction Contract or otherwise affects the relationship or rights of hubco and/or the Contractor under the Construction Contract (the "Construction Contract Dispute") then hubco may include as part of its submissions made to the Adjudicator submissions made by the Contractor.

  - Any submissions made by the Contractor shall:

    - be made within the time limits applicable to the delivery of submissions by hubco to the Adjudicator; and

    - concern only those matters which relate to the Dispute between the Authority and hubco arising out of this Agreement or in connection therewith.

  - Where the Contractor makes submissions in any reference before the Adjudicator, the Adjudicator's costs of such reference shall be borne as the Adjudicator shall specify, or in default, one-third by the Authority and two-thirds by hubco.

  - The Authority shall have no liability to the Contractor arising out of or in connection with any decision of the Adjudicator or in respect of the costs of the Contractor in participating in the resolution of any Dispute under this Agreement.

  - hubco shall not allow the Contractor access to any Confidential Information relevant to the issues in dispute between the Authority and hubco save where:

    - the Confidential Information is relevant also to the issues relating to the Construction Contract Dispute; and

    - hubco has first delivered to the Authority a written undertaking from the Contractor addressed to the Authority that they shall not use any such Confidential Information otherwise than for the purpose of the dispute resolution proceedings under this Agreement and that they shall not disclose such Confidential Information to any third party other than the Adjudicator or the courts or any professional adviser engaged by the Contractor to advise in connection with the Dispute.

- Panel Members

The panel members referred to in paragraph 4.2 are as follows:

| Adjudication Panel | [ ] |
| --- | --- |

or any replacements or substitutes to be agreed between the parties.

- No Loss

Where the Authority would otherwise be expressly liable to make payment to hubco of sums which include amounts payable in turn by hubco to any Sub-Contractor, the Authority shall not be entitled to withhold, reduce or avoid any such payment to hubco in reliance only on the fact that the amount which is due from hubco to the Sub-Contractor or the entitlement of the Sub-Contractor to payment of such amount as a result of the circumstances giving rise to the Authority’s obligation to pay, is conditional on the entitlement of, or receipt of payment by hubco from the Authority.

- Continuing obligations

Unless this Agreement has already been repudiated or terminated, the parties shall, (notwithstanding that any Dispute is subject to the Dispute Resolution Procedure set out in this Schedule Part 15 (Dispute Resolution Procedure), continue to carry out their obligations in accordance with this Agreement.

- CERTIFICATES

*Certificate of Completion

Issued by:	Authority's Representative - [                    ]

Address:	[                    ]

hubco:	[HUBCO]

Address:	 [                    ]

Contractor:			[CONTRACTOR]

Address:				[                    ]

Issue date: 			…………………

Works:

Situated at:

Build Only Development Agreement dated: …………………

Under the terms of the above-mentioned Build Only Development Agreement,

I certify that the Actual Completion Date of the Works was achieved on [	].

To be signed by or for the issuer named above.

Signed....………………………………………………

Authority's Representative

*Commissioning Completion Certificate

Issued by:	Authority's Representative - [                    ]

Address:	[                    ]

hubco:	[HUBCO]

Address:	 [                    ]

Contractor:				[CONTRACTOR]

Address:					[                    ]

Issue date: 				…………………

Works:

Situated at:

Build Only Development Agreement dated: …………………

Under the terms of the above-mentioned Build Only Development Agreement, I certify that the Commissioning End Date was achieved on [	   ].

To be signed by or for the issuer named above.

Signed....………………………………………………

Authority's Representative

*Certificate of Making Good Defects

Issued by:	Authority's Representative - [                    ]

Address:	[                    ]

hubco:	[HUBCO]

Address:	 [                    ]

Contractor:		[CONTRACTOR]

Address:			[                    ]

Issue date: …………………

Works:

Situated at:

Build Only Development Agreement dated: …………………

Under the terms of the above-mentioned Build Only Development Agreement, I certify that all Defects in the Schedule of Defects have been made good on [	].

To be signed by or for the issuer named above.

Signed....………………………………………………

Authority's Representative

- COMMERCIALLY SENSITIVE INFORMATION

- Commercially Sensitive Contracual provisions

| Column 1 Commercially Sensitive Contractual Provisions | Column 2 For period ending on the date below |
| --- | --- |
| Any terms of or figures set out within this Agreement but only insofar as such terms or figures relate to the build up of pricing of the Works, including the prices of any sub-contractors of the Contractor. | From the Execution Date until the date falling 2 years after the [first Phase] Actual Completion Date |

- Commercially Sensitive Material

| Column 1 Commercially Sensitive Material | Column 2 For period ending on the date below |
| --- | --- |
| Information about hubco’s processes, methodologies, working methods and information relating to the development of new processes and methodologies which amounts to a trade secret or which, if disclosed, could reasonably be considered to provide a commercial advantage to hubco’s competitors. | From the Execution Date until the date falling 2 years after the [first Phase] Actual Completion Date |

- LIQUIDATED DAMAGES

[TO BE INSERTED ON A PROJECT SPECIFIC BASIS]

- not used

- PROJECT BANK ACCOUNT

- DECLARATION OF TRUST

- joining declaration

- APPLICATION SCHEDULE

| Relevant Month | Application Date |
| --- | --- |
| [ l ] | [ l ] |
| [ l ] | [ l ] |
| [ l ] | [ l ] |

- not used

- Details of processing of personal data

This Schedule Part 22 includes certain details of the processing as required by Article 28(3) GDPR and Clause 45 of this Agreement.

1 Subject matter and duration of the processing of personal data

The subject matter and duration of the processing of the personal data are set out in this Schedule Part 22 and Clause 45 of this Agreement.

This Schedule Part 22 shall take effect on the Execution Date and shall continue in full force and effect until the expiry or valid termination of this Agreement.

2 The nature and purpose of the processing of personal data

The [Authority] [and] [hubco] shall carry out the following processing of personal data on behalf of the Controller Party in respect of this Agreement:

[ l ] [INCLUDE DESCRIPTION HERE]

3 The types of personal data to be processed

The following types of personal data will be processed on behalf of the Controller Party when required to do so in accordance with this Agreement:

[ l ] [INCLUDE LIST OF PERSONAL DATA TYPES HERE]

4 The categories of data subject to whom the personal data relates

Personal data relating to the following categories of data subjects will be processed:

[ l ] [INCLUDE CATEGORIES OF DATA SUBJECTS HERE]

5 The obligations and rights of the controller

The obligations and rights of the Controller Party are set out in this Agreement.

Adjust to reflect identity if Project Service Provider is a subsidiary of hubco

Adjust to reflect identity of the Project Service Provider where a subsidiary of hubco is to be used.

The use of a Project Bank Account is mandatory for all public bodies which are subject to the terms of the Scottish Public Finance Manual (“SPFM”) where the Development Amount is in excess of the applicable OJEU Threshold for public works contracts (currently £4,104,394).  Where the Development Amount is less than the OJEU Threshold, or the procuring authority is not subject to SPFM, use of a Project Bank Account is at the discretion of the Authority.  Where a procuring authority does not use a Project Bank Account, it will still require to comply with its obligations under the Procurement Reform (Scotland) Act 2014.  Any changes arising out of this requirement require SFT approval.

If there are project specific reasons why a condition or event cannot be satisfied until after contract signature, the Agreement will need to be amended accordingly.  In those circumstances, any conditions precedent ("CPs") should be limited as far as possible to items of real project significance that cannot be satisfied prior to signature. This approach is necessary to minimise the risk of a party terminating the Agreement for failure to satisfy a trivial or insignificant CP.

Where the Authority or a Community Services Provider is a health board.

On a project specific basis where there is a phased construction or refurbishment project, this will have to be reviewed.  Consider whether a phased programme of access may be required.

The Template Project Agreement assumes that detailed Planning Permission will have been obtained, and that sufficient time has elapsed to minimise the risk of judicial review, prior to contract signature.  Where this is not the case, the Authority may consider including judicial review drafting on a project by project basis which appropriately (and on a value for money basis) allocates the risk of judicial review.  No risk should be passed to the Authority to the extent arising out of the conduct of the planning process by or on behalf of hubco.

Where there are legislative requirements in relation to the Facilities which can be complied with only by or require the input or co-operation of the Authority as occupier or user of the Facilities or any part of them, then specific drafting should be inserted addressing those issues.  Any such acceptance of responsibility by the Authority should be narrowly prescribed.

In the event that detailed planning permission includes obligations with which it is the Authority (as owner/occupier of the facility) who must comply, it will be necessary to include appropriate drafting to reflect any such obligations.

To be used on a project specific basis where the Authority is responsible for discharging, implementing and/or complying with certain planning conditions.

hubco is warranting the design of the hubco Designed Portion insofar as the design of the hubco Designed Portion is comprised in hubco’s Proposals, in what hubco is to complete in accordance with this Clause 12.3 and any further design that hubco is required to carry out as a consequence of an Authority Works Variation. If the Authority wishes hubco to assume responsibility for those elements of the design of the hubco Designed Portion contained in the Authority’s Construction Requirements this clause will require to be amended. In that scenario it is likely that hubco and the Contractor will require collateral warranties from the design consultants appointed by the Authority in connection with the Authority’s Construction Requirements.

Where the Authority is a health board.  Other Participants to consider additional requirements they may have on a project by project basis.

Specify where qualifications are set out.  Authority must have right to notify hubco of its comments.

Use text if optional Clause 12.13 is used.

This optional Clause 12.13 should be used if the Authority is not in a position to provide all necessary designs and specifications on or before the Execution Date.

On Projects where there is more than one Relevant Participant, the Participants may require that representatives of each have similar rights as referred to in this Clause 13.1.

Provision for notification of early completion has been included to enable the parties (at their discretion) to consider early occupation by the Authority of the Facilities. The consequential amendments required as a result of agreeing to that option would have to be considered and agreed on a project specific basis at the time. (For example, dealing with knock on effect on commissioning programmes, Equipment procurement, payment etc).

Project Specific.

The Template Project Agreement assumes that each of the Authority and hubco will undertake inspection and commissioning activities both prior to and after completion.  Parties need to consider which commissioning activities have to occur before and which after completion (and, in each case, by whom) on a project specific basis. The Template Project Agreement envisages that the FCP will set out all requirements and obligations in relation to the development, nature, principles and performance of the completion tests to be performed to enable certification of completion to take place. This Template Project Agreement should be amended as necessary to reflect any particular project arrangements.

Authority to describe any other core requirements to be complied with in relation to hubco's commissioning activities.

Project specific.  Authorities will need to consider what the Authority's commissioning activities will entail.  Parties will need to consider when the Authority's commissioning activities (including, for example, installing of its own equipment) will be carried out.

To be specified on a project by project basis.

The definition provides for a period of 12 months.  Authorities may wish to consider longer periods for specific aspects eg M&E.

Authority to consider what commissioning/services start-up activities will be carried out by hubco and what commissioning activities will be carried out by the Authority during this period.

Authorities to ensure that hubco's activities in this regard remain covered by the insurance to be procured under this Agreement.

This provision may not be necessary. It will depend on the significance of each party's activities during this period and will depend on how release of retentions during this period are structured.

To be amended on a project by project basis.  For example, operational manuals may need to be made available at an earlier date depending on the timing of commissioning activities.  Furthermore, it may be possible, for hubco to provide draft manuals to the Authority for comment prior to finalisation and suitable amendments should be made to the Clause where relevant.

A discovery of fossils and antiquities is treated as a Relief Event entitling hubco to an extension of time in accordance with Clause 22 (Delay Events) but leaving the financial risks of such discovery with hubco.  If there is a known problem on site the provisions relating to discoveries may need to be reviewed and amended on a project specific basis.

Amendments to reflect the concept that the management system, rather than the quality manager, is important.

Delay Events give rise to an extension of time for completion of construction.  Compensation is payable for all Delay Events (other than Force Majeure or Relief Events) as follows:-

- Authority Variations: Variation Procedure

- Authority breach 22.3.2, 22.3.3 ,22.3.4, 22.3.7, 22.3.8, 22.3.9, 22.3.10, 22.3.11, 22.3.12 and 22.3.13: Compensation Event

Should particular project specific circumstances warrant, the list of events could be extended to include other events with SFT approval.  However, Authorities should not permit the inclusion of a "catch-all" provision to the extent that any event outside the control of the parties should be a Relief Event. Only approved specified events should be listed.  Equally, Authorities are free, on a project specific basis, to delete any item from this list if project specific circumstances merit although examples of this have been, and are expected to remain, extremely rare.

To be reviewed in light of project specific insurance arrangements.

To be reviewed on a project by project basis to reflect the Stage 2 Project Development Fee payable in terms of 	Schedule Part 5 (New Project Approval Process) of the TPA in respect of the Project.

Please note that the Section 110A of the Construction Act provides that either the payee or the payer shall issue a “payment notice” not later than 5 days after the date that such payment becomes due.  2 Business Days (including for these purposes bank holidays) is less than 5 calendar days and therefore should not be increased.

The drafting contained in Clause 27.6 is for use where the Authority operates a cash retention.

Authorities to consider on a project by project basis whether to link payment of the Retention (first or second 	instalment) to receipt of operation and maintenance manual and/or the health and safety file.

Two months may be a more appropriate period. To be considered on a project by project basis.

It is recommended to have the Joining Declaration signed by the relevant Qualifying Sub-Contractor at the same time as the Qualifying Sub-Contractor signs its Sub-Contract.

Delete if relevant parties are incorporated and resident in Scotland.

If it is critical for project specific reasons to meet the scheduled date for completion, the Authority may need to include an earlier trigger which would enable it to terminate prior to the longstop date if it became clear at a given point in time that the longstop date was incapable of being met.

This means the employee acts under the authority of or with the knowledge of any one or more directors of hubco.

This means the employee acts under the authority of or with the knowledge of any one or more directors of the Contracting Associate.

Authority to include project specific provisions (e.g. relating to Equipment, IT, planning, land and Authority Assets or information etc).  Authority to consider what protection is required to ensure compliance with the handover provisions on a project specific basis (taking into account the nature, importance and value of the assets that the handover provisions will apply to).

Only if termination is prior to completion - otherwise the completion requirements should include guarantees etc 	(subject to defects correction).

To be reviewed on a project specific basis in light of insurance arrangements.

Deliberate acts or omissions do not include acts or omissions which are within the contemplation of the parties or provided for in this Agreement (see 2.11 of Schedule Part 1 [Definitions and Interpretation]).

The Authority indemnities relating to physical damage in Clauses 36.2.3 and Clause 36.2.4 do not cover physical damage caused by negligent acts or omissions.  hubco should insure against that risk.  Authorities should not act as insurers of last resort in those circumstances.

A general indemnity has not been included in relation to Authority breach.  hubco has its express rights under the agreement (for example, Delay Events) and its rights to sue for breach of contract in order to recover any additional loss.

Any warranties to be given by the Authority must be justified on a project specific basis (it is expected that such circumstances will be limited for example, where the Authority is the only source of the information and hubco has no means of obtaining or verifying that information itself).

The insurance drafting assumes that insurance is placed on a project specific basis.  However, it is possible that hubco may wish to use a corporate/group policy to effect insurance.  Whilst in principle such an approach may be acceptable, it will be important for the Authority, in conjunction with its insurance advisers and SFT, to review in detail hubco's proposals and ensure that the level of protection afforded to the Authority is adequate and broadly consistent with the protection available where insurance is placed on a project specific basis.  In particular:

•	The Authority should always be named as a co-insured under the material damage 	policy

•	If the Authority is not named as a co-insured under the third party liability policy, then the policy should 	include an appropriately worded ‘indemnity to principals’ clause and a waiver of subrogation to the benefit 	of the Authority.

•	This clause must require hubco to provide immediate notification to the Authority of any cancellation or 	material change in the terms and conditions of the policy.  This undertaking should be reflected in the 	broker’s letter of undertaking.

•	If insurers are unwilling to pay insurance proceeds into the Insurance Proceeds Account, this clause should 	specify that they are paid into the Insurance Proceeds Account upon receipt by hubco, with the proceeds 	held on trust for the benefit of the Authority prior to transfer.

•	Where a corporate policy is used revisions to the broker's letter of undertaking in Section 4 of Schedule Part 12 may be required.  It will 	be important for the Authority’s legal and insurance advisers to consider the acceptability of the proposed changes and to keep any changes to a minimum.

•	The indemnities may also need to be amended.

If insurers are unwilling to waive subrogation rights against unnamed Authority Parties, Authority to consider including specified named Authority Parties (especially sub-contractors).  Authorities should, however, resist a suggestion that 3rd parties should automatically be carved out from this clause.

This clause may not be amended but an obligation may be put in Schedule Part 12 as follows:-

The Insurers hereby waive all rights of subrogation however arising which they may have or acquire against the Authority, Authority Parties and its or their respective parents, affiliates, directors, officers employees and assigns arising out of any occurrence in respect of which any claim is admitted under this Policy except where the rights of subrogation or recourse are acquired in consequence of a Vitiating Act in which circumstance insurers may enforce such rights against the vitiating party notwithstanding the continuing or former status of the vitiating party as an Insured.

To refer to only such Insurances, the proceeds of which are to be paid into the Insurance Proceeds Account.

Authorities to consider on a project specific basis.  Authorities may prefer to rely on the indemnity Clause 36.

As a matter of good practice, Authorities should review the relevant subcontracts to ensure that they contain mirror provisions excluding the right to claim Indirect Losses.

It is for Authorities to consider whether inclusion of a liability cap (and the level of such cap where included) represents value for money to the Authority or is otherwise acceptable.

Authorities may consider expanding the list of exclusions.

If either party is to be given access to any of the other party's computer systems, as a matter of good practice and also to clarify potential liability for unauthorised access to those systems under the Computer Misuse Act 1990, the scope of each party's authorisation to access each other's computer systems will need to be defined clearly.  The terms of such authorisation will be project specific.

Authorities to consider on a project by project basis.

Where the Authority is a health board.

Where the Authority is a health board.  Appropriate wording to be used where the Authority is a local authority or other Participant.

Where the Authority is a health board.  Appropriate wording to be used where the Authority is a local authority or other Participant.

Authorities should review the scope of this provision in the light of project specific data processing requirements.

Clause 45.5 is to be used in those circumstances where the parties do not know, upon signing the agreement, what processing will be required in accordance with clause 45.3. Please note it is a legal requirement under Article 28 of the GDPR to agree this information in writing. If processing can be confirmed at signing, Schedule Part 22 should be completed with the appropriate information and the wording within square brackets in the first paragraph of clause 45.3 should be included.

Authorities should keep this exemption strictly limited and should be mindful of FOI(S)A and OGC guidance when agreeing what parts of the documents should be treated as Commercially Sensitive Information.  Proper due diligence is required here in order to avoid the Authority being in a position where it is required to disclose information under FOI(S)A which has been designated as Commercially Sensitive.

Where the Authority is a health board.  Appropriate wording to be used where the Authority is a local authority or 		other Participant.

46.11 and 46.12 only to be used where the Authority is a health board.  Other Authorities may wish to consider alternative wording.

This should enable the Authority to comply with its obligations under the FOI(S)A.  If the Authority wished to go beyond this, for instance by referring in addition to other information or to information held by first tier subcontractors on behalf of hubco, this can be specified – but this may have cost/vfm implications.

Authorities should ensure that the appropriate policy is in place.

It is up to the parties to decide whether costs associated with any future change in the Authority’s FOI(S)A cost recovery policy should go through Schedule Part 13 (Variation Procedure).

If the Environmental Information (Scotland) Regulations are relevant to the project, the parties may include broadly equivalent provisions in the Agreement dealing with costs and based upon the Authority’s policy towards reimbursement of such costs under Section 8 of the Environmental Information (Scotland) Regulations.

Authority to consider if appropriate.

Each Application Date must be an objectively fixed date (i.e. not contingent on an application being submitted)

Note:  Authorities to specify on a project by project basis what key subcontractor (ie. with design responsibility) collateral warranties are required.

Any information or classes of information that the parties agree should be treated as Commercially Sensitive Information should be included in Schedule 17 entitled Commercially Sensitive Information.  The Authority should be mindful of guidance on this issue when agreeing which information should be categorised as commercially sensitive.  This can cover specific bid information (for specific periods) or other types of generic information but broad blanket categorisations are not appropriate.

Note:  This provision should be drafted on a project specific basis to encompass any principal sub-contractors to hubco

Authorities may request longer periods on a project specific basis.

Definition to be used where the optional Clause 12.13 is used. A new schedule part will also need to be added containing the Information Release Schedule.

To be completed by Authority on a project specific basis.

Where the Authority is a health board.

Where the Authority is a health board.

This would include matters such as points of access, adjacencies of rooms, quantity description and areas of rooms etc.  To be developed on a project specific basis.

This is not intended to encompass design material agreed prior to signature.

This Schedule Part contains a generic list of the sort of completion documents the parties would expect to see 	produced.  This should be amended on a project specific basis to reflect the particular documents required in 	each case.

Include details required in accordance with Clause 8.9 (Representatives).

This should include any restrictions on the use of any part of the Site.

This should include any rights over any part of the Site which have been or are being reserved for the Authority and/or any third party eg rights of access, wayleaves.

This should include any areas and periods within which the Contractor should have exclusive possession to parts of the Site.

This Part A of Section 1 of Schedule Part 5 should include a list of the Consents obtained as at the date of signing of the Project Agreement.

This Part B of Section 1 of Schedule Part 5 should include a list of the Consents required to be obtained by hubco/the Contractor.

The respectives roles of the Authority and hubco under the CDM Regulations should be agreed at NPR stage. The drafting may require to be amended following such agreement.

Under the current drafting, the Authority will need to appoint the principal designer under the CDM Regulations.

The contents of this Section 3 of Schedule Part 5 should include the room data sheets and will usually include the following:

• Introduction to what is comprised within the Facilities

• Architectural specification

• Civil/Structural performance specification

• Mechanical and Electrical specification

• Drawings

• Performance specification in relation to the hubco Designed Portion

The contents of this Section 4 of Schedule Part 5 will usually include the following:

- Construction Methodology

- Specification/drawings for hubco Designed Portion

This Section 5 of Schedule Part 5 should include the design that is to be developed in accordance with the principles set out in 	the Review Procedure relating to the hubco Designed Portion.

This Section 8 of Schedule Part 5 should contain the Construction Quality Plan and, if applicable, the hubco Designed Portion Design Quality Plan.

This is the Project master programme which should set out the completion of the design of the hubco Designed Portion and construction works from the Execution Date to Post Completion Commissioning.

Authorities to include any other items which are relevant on a project specific basis.

Project specific.  This table is intended to be for guidance only.

This drafting has been included as a framework for guidance and should be amended as 	appropriate on a project specific basis, including, in particular, to take account of how commissioning of the Facilities is to be carried out and any other matters that are to be left to be agreed pursuant to the Review Procedure.

Where the Authority is a health board.

This paragraph is intended as a framework only and should be developed in a project specific basis.

Where the Facilities are joint, the Contractor shall be required to grant a collateral warranty in substantially the same form as that 	set out in this Section 1 in favour of the other relevant authorities.

The Authority shall be entitled to require hubco to procure a collateral warranty from each party providing a collateral warranty to 	the Authority in favour of any future tenant of the Facilities or part of the Facilities under a FRI lease.

To be considered in light of Clauses 16 (Pre-Completion Commissioning) and 18 (Post Completion Commissioning) and the 	commissioning activities to be carried out during those periods.  This should outline who is responsible for what (and when) and 	set out the principles for all completion tests and inspections.

Schedule Part 10 set outs proposed responsibilities of the Authority and hubco respectively in respect of the Equipment. The respective responsibilities may be amended on a project-specific basis.

Ensure that parties named/defined terms match structure of particular project

Include as appropriate as this is project specific.

Additional Cover Features & Extensions may be appropriate for certain projects.

If possible, insurance should be placed on a "losses occurring" basis.

Cover should be for contractual liability, statutory liability and liability in delict.

Limit should be determined by the Authority, in conjunction with its insurance adviser, taking into account the relevant 	circumstances of the project.

For certain projects an excess may apply to personal injury claims.

For certain projects, additional Cover Features & Extensions may need to be noted.

Ensure that parties named/defined terms match structure of particular project

Additional Cover Features & Extensions may be appropriate for certain projects.

The endorsements are recommended drafting.  Whilst the parties should endeavour to obtain cover in accordance with these 	wordings, if these are not in practice available, the parties should obtain the 	best terms reasonably available in the market at the 	time.

The wording in this Section 4 of this Schedule Part 12 is recommended drafting.  If agreement to this wording is not in practice achievable, then the parties should agree the best terms reasonably available in the market at the time.

This provision under Clause 4.5 is required drafting and may not be altered.

hubco's broker may wish to limit its liability and include additional liability wording in the Broker’s Letter of Undertaking.  Whilst 	this is in principle acceptable, the Authority will need to check that (i) the scope of such additional wording is appropriate (eg 	does not extend to a limitation of liability for fraudulent acts), and (ii) the capped amount is set at a sufficiently high level.

The reference to hubco's Proposals has been included to give Authorities flexibility in circumstances where it is not possible to outline the change required solely by reference to the Authority's output specifications.  This option should be used on a 	limited basis (so that, wherever possible, the Authority's output specifications alone are used for this purpose) taking account of 	risk transfer implications if hubco's Proposals are amended by the Authority.

Consider whether provision is to be made for a longer period of time being a possibility or whether the 1 month period should be left as it is, in which case hubco may give a less detailed response.

Authorities should note that some (but not all) banks have sought and obtained their approval as an 	additional ground for 	objection.

Care must be taken to consider whether there will be Consents which, in principle, ought to be obtained by the Authority.

These provisions have been included for the purpose of providing a general framework and should be amended 	to reflect project specifics.

Where the Authority is a health board

The Records to be kept by hubco are to be determined on a project specific basis, but 	should include those 	items listed in this Section.

Provisions allowing joinder of hubco parties have not been included to prevent the Authority from getting 	embroiled in concurrent disputes running between hubco and its contractors.

Note that this agreement is likely to fall within the definition of a "Construction Contract" for the purposes of the 	Housing Grants Construction and Regeneration Act 1996, and therefore requires to contain a right to adjudicate 	without restriction.

To be completed prior to execution of the Build Only Development Agreement